## Page1
[11 empty] | 功能构建 |  | 设计评审计划 | 第一轮 | 第二轮 | 代码检查
[11 empty] | 责任人 | 开发人 | 开发地 | 完成 |  | Plan | Act | 评审人员 | 测试完成 | 改善完成 | 测试通过 | 开发改善 Day | PlanStart | PlanEnd | ActDays | ActStart | ActEnd | 开发者 | 测试完成 | 改善完成 | 测试通过 | 开发改善 Day | PlanStart | PlanEnd | ActDays | ActStart | ActEnd | 开发者 | 检查人 | 检修计划 | 完成
Main | Main | 1 | Main WIP(View Lot) | Main |  | 确定 | Phase1 | 主页 | 有 | 非 PHOTO, Sorter 机台的 Machine , Lot 监控及操作 | 申克楠 | 常刘勺 | 苏州
Carrier Mgt |  | 2 | Add Carrier Comment | Carrier | 非重点 | 确定 | Phase1 | Add Carrier Comment | 无 | 添加Carrier Comment | 杨金杰 | 郭天娇 | 无锡 |  |  | 10月18日 | [5 empty] | 2 | 10月19日 | 10月21日
|  | 3 | Cancel Clean | Carrier | 重点 | 确定 | Phase1 |  | 无 | Cancel Set Clean,Cancel Start Clean | 杨金杰 | 郭天娇 | 无锡 |  |  | 10月24日 | [5 empty] | 3 | 10月28日 | 10月31日
|  | 4 | Cancel Inspection | Carrier | 重点 | 确定 | Phase1 |  | 无 | Cacel Set Inspetion | 杨金杰 | 郭天娇 | 无锡 |  |  | 11月7日 | [5 empty] | 3 | 11月8日 | 11月11日
|  | 5 | Carrier Data Collection | Carrier |  |  |  |  | 无 |  | 李彬
|  | 6 | Disposal/Undo Disposal | Carrier | 次重点 | 确定 | Phase1 |  | 无 | Set Disposal之后的 处置,和Cancel 处置Carrier的动作 | 杨金杰 | 郭天娇 | 无锡 |  |  | 10月31日 | [5 empty] | 3 | 11月1日 | 11月4日
|  | 7 | Inspection Flow Control | Carrier |  |  |  |  | 无 |  | 杨金杰 | 郭天娇 | 无锡
|  | 8 | Start/End Inspection | Carrier | 重点 | 确定 | Phase1 |  | 无 | 开始Carrier 量测,结束Carrier量测 | 杨金杰 | 郭天娇 | 无锡 |  |  | 11月7日 | [5 empty] | 3 | 11月8日 | 11月11日
|  | 9 | Repair FOUP | Carrier | 次重点 | 确定 | Phase1 |  | 无 | 修理FOUP | 杨金杰 | 郭天娇 | 无锡 |  |  | 10月31日 | [5 empty] | 3 | 11月1日 | 11月4日
|  | 10 | Reserve Target Carrier | Carrier | 重点 | 确定 | Phase1 | Reserve Target Carrier | 无 | 预约Carrier,防止其他用途使用 | 杨金杰 | 郭天娇 | 无锡 | 完成 | [7 empty] | 3 | 1月1日 | 1月4日
|  | 11 | Set Disposal/Cancel Disposal | Carrier | 次重点 | 确定 | Phase1 |  | 无 | Repair/Scrap之前的设定处置,和Cancel 设定 处置Carrier的 | 作杨金杰 | 郭天娇 | 无锡 |  |  | 10月31日 | [5 empty] | 3 | 11月1日 | 11月4日
|  | 12 | Set Clean | Carrier | 重点 | 确定 | Phase1 |  | 无 | 设定Clean | 杨金杰 | 郭天娇 | 无锡 |  |  | 10月24日 | [5 empty] | 3 | 11月1日 | 11月4日
|  | 13 | Set Inspection | Carrier | 重点 | 确定 | Phase1 |  | 无 | 设定Carrier Inspecton | 杨金杰 | 郭天娇 | 无锡 |  |  | 11月7日 | [5 empty] | 3 | 11月8日 | 11月11日
|  | 14 | Special Transfer Lot | Carrier |  |  |  |  | 无 | 特殊Transfer Lot处理 | 杨金杰 | 郭天娇 | 无锡
|  | 15 | Start/End Clean | Carrier | 重点 | 确定 | Phase1 |  | 无 | 开始Carrier Clean,结束Carrier Clean | 杨金杰 | 郭天娇 | 无锡 |  |  | 10月24日 | [5 empty] | 3 | 11月5日 | 11月8日
|  | 16 | Update Carrier Component | Carrier |  |  |  |  | 无 | 更新Carrier组件(?) | 杨金杰 | 郭天娇 | 无锡
| View Carrier Info | 17 | View Carrier Cleaning History | Carrier | 次重点 | 确定 | Phase1 |  | 无 | 查询Carrier Cleaning 历史记录 | 杨金杰 | 郭天娇 | 无锡 |  |  | 10月18日 | [5 empty] | 2 | 10月22日 | 10月24日
| View Carrier Info | 18 | View Carrier Cycle | Carrier | 次重点 | 确定 | Phase1 |  | 无 | 查询Carrie Cycle现况 | 杨金杰 | 郭天娇 | 无锡 |  |  | 10月18日 | [5 empty] | 2 | 10月25日 | 10月27日
Eqp Mgt |  | 19 | Buffer Tool Physical Foup Maintain | Machine |  |  |  |  | 无 | 管理Buffer的FOUP | 杨金杰 | 王哲 | 无锡
| One Key Touch | 20 | Control Action History | Machine |  |  |  |  | 无 |  | 杨金杰 | 王哲 | 无锡
|  | 21 | Customize EQP Information | Machine |  |  |  |  | 无 |  | 杨金杰 | 王哲 | 无锡
|  | 22 | Delete Chamber Current Lots | Machine | 次重点 | 确定 | Phase1 |  | 无 | 删除掉chamber的Current Lot | 杨金杰 | 王哲 | 无锡 |  |  | 11月1日 | [5 empty] | 3 | 11月2日 | 11月5日
|  | 23 | Equipment Couple Port | Machine | 重点 | 确定 | Phase1 |  | 无 | Machine Couple Port | 杨金杰 | 王哲 | 无锡 |  |  | 11月8日 | [5 empty] | 3 | 11月9日 | 11月12日
|  | 24 | EQP Manual Process Configuration | Machine |  |  |  |  | 无 |  | 杨金杰 | 王哲 | 无锡
|  | 25 | MFG Eqp Security Control Maintenance | Machine |  |  |  |  | 无 |  | 杨金杰 | 王哲 | 无锡
|  | 26 | Modify Equipment Attribute | Machine | 重点 | 确定 | Phase1 |  | 无 | Modify机台属性 | 杨金杰 | 王哲 | 无锡 |  |  | 11月8日 | [5 empty] | 3 | 11月9日 | 11月12日
|  | 27 | Modify Eqp Chamber Run Count | Machine | 次重点 | 确定 | Phase1 |  | 无 | Modify Chamber进行中的Lot | 杨金杰 | 王哲 | 无锡 |  |  | 11月1日 | [5 empty] | 3 | 11月2日 | 11月5日
|  | 28 | Modify Equipment Current Lots | Machine | 次重点 | 确定 | Phase1 |  | 无 | Modify机台进行中的Lot | 杨金杰 | 王哲 | 无锡 |  |  | 11月1日 | [5 empty] | 3 | 11月2日 | 11月5日
|  | 29 | Set Equipment Capability | Machine | 次重点 | 确定 | Phase1 |  | 无 | 设定机台的Capability | 杨金杰 | 王哲 | 无锡 |  |  | 10月25日 | [5 empty] | 3 | 10月26日 | 10月29日
| One Key Touch | 30 | One Key Touch | Machine |  |  |  |  | 无 |  | 杨金杰 | 王哲 | 无锡
| One Key Touch | 31 | One Key Touch Detail History | Machine |  |  |  |  | 无 |  | 杨金杰 | 王哲 | 无锡
| One Key Touch | 32 | Power Source Setup | Machine |  |  |  |  | 无 |  | 杨金杰 | 王哲 | 无锡
| One Key Touch | 33 | Power Source Setup History | Machine |  |  |  |  | 无 |  | 杨金杰 | 王哲 | 无锡
|  | 34 | Reticle Equipment Process History | Machine | 次重点 | 确定 | Phase1 |  | 无 | Reticle Process机台的历史记录 | 杨金杰 | 王哲 | 无锡 |  |  | 10月25日 | [5 empty] | 3 | 10月26日 | 10月29日
|  | 35 | Set Chamber Capability | Machine | 次重点 | 确定 | Phase1 |  | 无 | 设定Chamber的Capability | 杨金杰 | 王哲 | 无锡 |  |  | 10月25日 | [5 empty] | 3 | 10月26日 | 10月29日
| Tank Control | 36 | Tank Count Info | Machine |  |  | Phase2 |  | 无 |  | 杨金杰 | 王哲 | 无锡
| Tank Control | 37 | Tank OOS History | Machine |  |  | Phase2 |  | 无 |  | 杨金杰 | 王哲 | 无锡
| Tank Control | 38 | Tank Running History | Machine |  |  | Phase2 |  | 无 |  | 杨金杰 | 王哲 | 无锡
|  | 39 | Tool Recovery Control System | Machine |  |  | Phase2 |  | 无 |  | 杨金杰 | 王哲 | 无锡
|  | 40 | Tool Recovery Package Setup | Machine |  |  | Phase2 |  | 无 |  | 杨金杰 | 王哲 | 无锡
| Tank Control | 41 | Wet Tank Control | Machine |  |  | Phase2 |  | 无 |  | 杨金杰 | 王哲 | 无锡
| PMS | 42 | Arrange PM | Machine |  |  | Phase2 |  | 无 |  | 杨金杰 | 王哲 | 无锡
| PMS | 43 | Conditional PM | Machine |  |  | Phase2 |  | 无 |  | 杨金杰 | 王哲 | 无锡
| PMS | 44 | Trigger Readings | Machine |  |  | Phase2 |  | 无 |  | 杨金杰 | 王哲 | 无锡
| PMS | 45 | Usage Meter | Machine |  |  | Phase2 |  | 无 |  | 杨金杰 | 王哲 | 无锡
| Tank Control | 46 | Tank Count Info | Machine |  |  | Phase2 |  | 无 |  | 杨金杰 | 王哲 | 无锡
| Tank Control | 47 | Tank Running History | Machine |  |  | Phase2 |  | 无 |  | 杨金杰 | 王哲 | 无锡
Lot Mgt | Reassign | 48 | Change Sales Order | Lot |  | 未确定 |  |  | 无 |  | 罗涛
| FeedForward Attribute | 49 | Copy FeedForward Information | Lot | 次重点 | 确定 | Phase2 | Copy FeedForward Information | 无 | 拷贝FeedForward信息 | 罗涛 | 袁浩 | 苏州 |  |  | 2023/1/1 | [5 empty] | 3 | 2023/1/2 | 2023/1/4
| FeedForward Attribute | 50 | Delete FeedForward Information | Lot | 次重点 | 确定 | Phase2 | Delete FeedForward Information | 无 | 删除FeedForward信息 | 罗涛 | 袁浩 | 苏州 |  |  | 2023/1/1 | [5 empty] | 3 | 2023/1/5 | 2023/1/9
|  | 51 | Modify Lot Attribute For QE | Lot | 非重点 | 确定 | Phase2 |  | 无 |  | 罗涛 |  |  |  |  | 2023/1/1
|  | 52 | Lot Specialization | Lot | 次重点 | 确定 | Phase1 | Lot Specialization | 无 | Lot到达指定的站点后使用该配置的新值(EQP, PPID, EDC | lan, Reti罗cle涛 ID, Recip | ID)袁浩 | 苏州 |  |  | 2022/11/1 | [5 empty] | 5 | 2022/11/2 | 2022/11/9
| FeedForward Attribute | 53 | Modify FeedForward Information | Lot | 次重点 | 确定 | Phase2 | Modify FeedForward Information | 无 | 修改FeedForward信息 | 罗涛 | 袁浩 | 苏州 |  |  | 2023/1/1 | [5 empty] | 3 | 2023/1/10 | 2023/1/12
|  | 54 | Modify Potential Attribute | Lot |  | 未确定 |  |  | 无 |  | 罗涛
|  | 55 | Maintain RMS Flag | Lot |  | 未确定 |  |  | 无 |  | 罗涛
|  | 56 | Set Stepper | Lot | 次重点 | 确定 | Phase1 | Set Stepper | 无 | 为Litho站点修改stepper | 罗涛 | 袁浩 | 苏州 |  |  | 2022/11/1
|  | 57 | Undo Finish | Lot | 重点 | 确定 | Phase1 | Undo Finish | 无 | 将finished lot reassign到指定站点 | 罗涛 | 袁浩 | 苏州 |  |  | 2022/11/1
|  | 58 | Choose Alter Step | Lot |  | 未确定 |  |  | 无 |  | 罗涛
| MixRun | 59 | View Mix Run Status | Lot |  | 未确定 |  |  | 无 |  | 罗涛
| Auto YE Review Wafer Selection Config | 60 | Wafer Selection History For Auto YE Review | Wafer Selection |  |  |  |  | 无 |  | 申克楠
| Auto YE Review Wafer Selection Config | 61 | Update Wafer List Of YE Review | Wafer Selection |  |  |  |  | 无 |  | 申克楠
| Auto YE Review Wafer Selection Config | 62 | Setting By Capability | Wafer Selection |  |  |  |  | 无 |  | 申克楠
| Auto YE Review Wafer Selection Config | 63 | Setting By Product | Wafer Selection |  |  |  |  | 无 |  | 申克楠
| Wafer Randomization | 64 | Adhoc Recover | Lot |  | 未确定 |  |  | 无 |  | 罗涛
| Reposition | 65 | Back Up Step | Lot | 次重点 | 确定 | Phase1 | Back Up Step | 无 | 返回上一站 | 罗涛 | 袁浩 | 苏州 |  |  | 2022/11/1 | [5 empty] | 3 | 2022/11/10 | 2022/11/14
| Wafer Randomization | 66 | Config Random Recipe | Lot |  | 未确定 |  |  | 无 |  | 罗涛
| Wafer Randomization | 67 | Lot Random History | Lot |  | 未确定 |  |  | 无 |  | 罗涛
| Doma Management | 68 | Doma Path Config History | Lot |  | 未确定 |  |  | 无 |  | 罗涛
| Doma Management | 69 | Doma Path Maintain | Lot |  | 未确定 |  |  | 无 |  | 罗涛
| Doma Management | 70 | Doma Path Setting | Lot |  | 未确定 |  |  | 无 |  | 罗涛
| Doma Management | 71 | DOMA RCD History | Lot |  | 未确定 |  |  | 无 |  | 罗涛
| Future | 72 | Future Hold By Customer | Lot | 次重点 | 确定 | Phase1 | Future Hold By Customer | 无 | 适应客户定制的reason code设置future hold | 罗涛 | 袁浩 | 苏州 |  |  | 2022/11/1 | [5 empty] | 2 | 2022/11/15 | 2022/11/16
| Future | 73 | Set Future Hold Step Group | Lot |  | 确定 | Phase1 | Set Future Hold Step Group | 无 |  | 罗涛 | 袁浩 | 苏州 |  |  | 2022/11/1 | [5 empty] | 2 | 2022/11/17 | 2022/11/18
| SML | 74 | Inline Split For Special Lot | Lot |  | 确定 | Phase2 |  | 无 |  | 杨金杰 | 王哲 | 无锡
| Doma Management | 75 | Lot Doma History | Lot |  | 未确定 |  |  | 无 |  | 罗涛
| Reposition | 76 | NPW Reposition | Lot | 次重点 | 确定 | Phase1 |  | 无 | NPW 的reposition | 罗涛 | 袁浩 | 苏州 |  |  | 2022/11/1 | [5 empty] | 2 | 2022/11/21 | 2022/11/22
| Reposition | 77 | Production Reposition | Lot |  | 未确定 |  |  | 无 |  | 罗涛
| Simple Lot Transfer | 78 | Cancel Transfer Lot | Lot | 次重点 | 确定 | Phase1 |  | 无 | 取消Transfer lot | 罗涛 | 王华强 | 无锡 |  |  | 2022/11/15 | [5 empty] | 3 | 2022/11/16 | 2022/11/18
| Simple Carrier Transfer | 79 | Receive Transfer Carrier | Lot | 次重点 | 确定 | Phase1 |  | 无 | 传送 carrier | 罗涛 | 王华强 | 无锡 |  |  | 2022/11/15 | [5 empty] | 5 | 2022/11/21 | 2022/11/25
| Simple Carrier Transfer | 80 | Simple Transfer Carrier | Lot | 次重点 | 确定 | Phase1 |  | 无 | 接受carrier | 罗涛 | 王华强 | 无锡 |  |  | 2022/11/15 | [5 empty] | 3 | 2022/11/28 | 2022/11/30
| Simple Lot Transfer | 81 | Receive Plan | Lot | 次重点 | 确定 | Phase2 |  | 无 |  | 罗涛 | 王华强 | 无锡 |  |  | 2023/1/1
| Doma Management | 82 | Unprocessed DOMA Path View | Lot |  | 未确定 |  |  | 无 |  | 罗涛
|  | 83 | YE Review Spec Configuration | Lot |  | 未确定 |  |  | 无 |  | 罗涛
|  | 84 | YE Review Special Reposition | Lot |  | 未确定 |  |  | 无 |  | 罗涛
|  | 85 | YE Select Wafers For Remeasure | Lot |  | 未确定 |  |  | 无 |  | 罗涛
| MixRun | 86 | Mix Run | Lot |  | 未确定 |  |  | 无 |  | 罗涛
| Pilot | 87 | Pilot Full Auto Information Setting | Lot |  | 未确定 |  |  | 无 |  | 罗涛
| Pilot | 88 | Create Adhoc Pilot | Lot |  | 未确定 |  |  | 无 |  | 罗涛
| Q'Time Control | 89 | Cancel Q'Time Reservation | Lot |  | 确定 | Phase1 |  | 无 | 删除Lot 已经触发的Q-Time | 申克楠 | 王蓬皓 | 苏州 | 完成
| Q'Time Control | 90 | Turn Off Q'Time Speed Up | Lot |  | 确定 | Phase1 |  | 无 | 关闭 Q-Time 的Speed Up 开关 | 申克楠 | 王蓬皓 | 苏州 | 完成
|  | 91 | Wafer Slot History | Lot |  |  |  |  | 无 |  | 童海潮
Lot Inventory | Inventory | 92 | Check Cust Maintain | Inventory | 次重点 | 确定 | Phase1 | Check Cust Maintain | 无 | 设置lot auto hold的规则 | 罗涛 | 王华强 | 无锡 |  |  | 2022/11/25 | [5 empty] | 5 | 2022/12/1 | 2022/12/8
| Inventory | 93 | Continue | Inventory | 次重点 | 确定 | Phase1 | Continue | 无 | move to location的逆操作 | 罗涛 | 王华强 | 无锡 |  |  | 2022/11/25 | [5 empty] | 3 | 2022/12/9 | 2022/12/13
| Inventory | 94 | Move To Location | Inventory | 次重点 | 确定 | Phase1 | Move To Location | 无 | 将zero layer flow结束的lot,从finished bank移动到start ba | k罗涛 | 王华强 | 无锡 |  |  | 2022/11/25 | [5 empty] | 3 | 2022/12/14 | 2022/12/16
WIP Tracking |  | 95 | Create Glass Lot | WIP |  | 未确定 |  |  | 无 |  | 罗涛
| N2Purge | 96 | Cancel N2Purge | WIP |  | 未确定 |  |  | 无 |  | 申克楠
| N2Purge | 97 | End N2Purge | WIP |  | 未确定 |  |  | 无 |  | 申克楠
| N2Purge | 98 | Load Port N2 Purge Flag Maintain | WIP |  | 未确定 |  |  | 无 |  | 申克楠
| N2Purge | 99 | Start N2Purge | WIP |  | 未确定 |  |  | 无 |  | 申克楠
| Run Card | 100 | Get RunCard Information | WIP | 重点 | 确定 | Phase1 | Get RunCard Information | 无 | 获得RunCard 信息 | 陈永伟 | 秦亮 | 无锡 | 未完成 | 修改
| Run Card | 101 | Merge RunCard Lot | WIP | 重点 | 确定 | Phase1 | Merge RunCard Lot | 无 | RunCard Lot merge | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| PPID Control | 102 | Edit PPID Comment | WIP |  |  |  |  | 无 |  | 李彬
| Bonding | 103 | Bonding Lot History | WIP |  | 未确定 |  | Bonding Lot History | 无 |  | 申克楠
| Bonding | 104 | Bonded Lot | WIP |  | 未确定 |  | Bonded Lot | 无 |  | 申克楠
| Bonding | 105 | Bonding Lot Skip | WIP |  | 未确定 |  | Bonding Lot Skip | 无 |  | 申克楠
| Bonding | 106 | Bonding Lot Type Mapping | WIP |  | 未确定 |  | Bonding Lot Type Mapping | 无 |  | 申克楠
| Bonding | 107 | Bonding Product Mapping | WIP |  | 未确定 |  |  | 无 |  | 申克楠
| Bonding | 108 | Bonding Step Mapping | WIP |  | 未确定 |  | Bonding Step Mapping | 无 |  | 申克楠
| Bonding | 109 | Glass Lot Information | WIP |  | 未确定 |  |  | 无 |  | 申克楠
| Bonding | 110 | Pair Port Setting | WIP |  | 未确定 |  |  | 无 |  | 申克楠
| Bonding | 111 | Pair Port Setting | WIP |  | 未确定 |  |  | 无 |  | 申克楠
| Bonding | 112 | Pre Bonding | WIP |  | 未确定 |  | Pre Bonding | 无 |  | 申克楠
|  | 113 | Lot Queue Adjustment | WIP |  | 确定 | Phase1 | Lot Queue Adjustment | 有 | After do Lot Queue Reservation , theconfirmed lot will be m | ve into申 Qu克e楠ue , andu | er ca常n 刘us勺e Lot | ueue A苏d州justme | t func完tio成nto adj | st the sequence
|  | 114 | Lot Queue Reservation | WIP |  | 确定 | Phase2 | Lot Queue Reservation | 无 | When EQP auto mode is Auto 2 , user needdo lot queue rese | vation 申fir克st.O楠therwis | system cannot | get lot list in Jo | Prep UI
|  | 115 | Query FOUP-Lot Reservation | WIP |  | 未确定 |  |  | 无 |  | 申克楠
| WaferSelectionRule | 116 | Setting By EDC Plan | WIP |  | 确定 | Phase1 | Setting By EDC Plan | 无 | 根据EDC Plan 配置ChamberCoverage 选片规则 | 申克楠/李彬
| WaferSelectionRule | 117 | Setting By EQP | WIP |  | 确定 | Phase1 | Setting By EQP | 无 | EQP Capability / EQP 别设置 WaferSelectionRule | 申克楠
|  | 118 | Setup Runtime Eqp State | WIP |  |  | Phase2 |  | 无 |  | 杨金杰 | 郭天娇 | 无锡
|  | 119 | R2R Modeling Configuration | WIP |  | 未确定 |  |  | 无 |  | 申克楠
|  | 120 | Sorter Capability Set By Carrier Type | WIP |  | 未确定 |  |  | 无 |  | 申克楠
|  | 121 | Sorter Capability Set By Wafer Kind | WIP |  | 未确定 |  |  | 无 |  | 申克楠
| Data Collection | 122 | Adhoc Data Collection | WIP |  |  |  |  | 无 |  | 李彬
| Data Collection | 123 | Cancel ReSend To Spc | WIP |  |  |  |  | 无 |  | 李彬
| Data Collection | 124 | Non-Lot Data Collection | WIP |  |  |  |  | 无 |  | 李彬
| Data Collection | 125 | ReSend To Spc | WIP |  |  |  |  | 无 |  | 李彬
| Data Collection | 126 | YE SpecID Bincode Map | WIP |  |  |  |  | 无 |  | 李彬
| Data Collection | 127 | YE SpecID Bincode Map History | WIP |  |  |  |  | 无 |  | 李彬
| Data Collection | 128 | View Non Lot Dcoll Info | WIP |  |  |  |  | 无 |  | 李彬
CSN |  | 129 | Constraint | CSN |  |  |  |  | 无 |  | 申克楠
|  | 130 | Mfg Dispatch | CSN |  |  |  |  | 无 |  | 申克楠
|  | 131 | Parts Life Time Control | CSN |  |  |  |  | 无 |  | 申克楠
|  | 132 | CSN PPID Constraint | CSN |  |  |  |  | 无 |  | 李彬
|  | 133 | Restrict Duration Recipe | CSN |  |  |  |  | 无 |  | 申克楠
Test Wafer | NPW Grade | 134 | Downgrade Wafer Quantity Limit | Test Wafer | 次重点 | 未确定 | Phase2 |  | 无 |  | 童海潮
|  | 135 | Cancel Dummy In | Test Wafer | 次重点 | 未确定 | Phase2 |  | 无 |  | 童海潮
|  | 136 | Cancel Reserve Dummy | Test Wafer | 次重点 | 未确定 | Phase2 |  | 无 |  | 童海潮
|  | 137 | Configure Wafer Stock Level | Test Wafer | 次重点 | 未确定 | Phase2 |  | 无 |  | 童海潮
|  | 138 | Query Monitor Lot | Test Wafer | 重点 | 确定 | Phase1 |  | 无 | 查询Monitor Lot信息 | 童海潮 | 高毓 | 无锡 | 未完成 | 新增 | 11月1日 | [5 empty] | 2 | 11月2日 | 11月3日
|  | 139 | Reclaim End | Test Wafer | 次重点 | 确定 | Phase1 |  | 无 | NPW Lot重新进行Recycle | 童海潮 | 高毓 | 无锡 | 未完成 | 新增 | 11月1日 | [5 empty] | 3 | 11月4日 | 11月6日
|  | 140 | Re_Create Monitor Lot | Test Wafer | 重点 | 确定 | Phase1 |  | 无 | Pre Measure Fail后重新创建Monitor Lot | 童海潮 | 高毓 | 无锡 | 未完成 | 新增 | 11月1日 | [5 empty] | 5 | 11月7日 | 11月11日
|  | 141 | Reserve Dummy | Test Wafer | 次重点 | 未确定 | Phase2 |  | 无 |  | 童海潮
OCAP |  | 142 | Complete Double Confirm | OCAP |  |  |  |  | 无 |  | 李彬
PCMS | Activity | 143 | Change Location | PCMS | 次重点 | 未确定 | Phase2 | Change Location | 无 |  | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Activity | 144 | Complete Use for RunCard | PCMS | 次重点 | 未确定 | Phase2 | Complete Use for RunCard | 无 |  | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Activity | 145 | EE Hold Card | PCMS | 次重点 | 确定 | Phase2 | EE Hold Card | 无 |  | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Activity | 146 | EE Validation | PCMS | 次重点 | 未确定 | Phase2 | EE Validation | 无 |  | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Configuration | 147 | Equipment Capability With Probe Card Grou | PCMS | 次重点 | 未确定 | Phase2 | Equipment Capability With Probe Card Grou | 无 |  | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Activity | 148 | Lend Out | PCMS | 次重点 | 未确定 | Phase2 | Lend Out | 无 |  | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Activity | 149 | MFG Receive | PCMS | 次重点 | 确定 | Phase2 | MFG Receive | 无 |  | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Run Time | 150 | Mounting Of Probe Card | PCMS | 次重点 | 未确定 | Phase2 | Mounting Of Probe Card | 无 |  | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Configuration | 151 | Probe Card Group Maintenance | PCMS | 次重点 | 未确定 | Phase2 | Probe Card Group Maintenance | 无 |  | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Configuration | 152 | Probe Card Maintenance | PCMS | 次重点 | 未确定 | Phase2 | Probe Card Maintenance | 无 |  | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Activity | 153 | PE Hold Card | PCMS | 次重点 | 未确定 | Phase2 | PE Hold Card | 无 |  | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Activity | 154 | PE Validation | PCMS | 次重点 | 未确定 | Phase2 | PE Validation | 无 |  | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Activity | 155 | Probe Card History | PCMS | 次重点 | 确定 | Phase2 | Probe Card History | 无 |  | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Activity | 156 | Release To MFG | PCMS | 次重点 | 确定 | Phase2 | Release To MFG | 无 |  | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Configuration | 157 | RCP Probe Card Group Mapping | PCMS | 次重点 | 未确定 | Phase2 | RCP Probe Card Group Mapping | 无 |  | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Activity | 158 | Release for RunCard | PCMS | 次重点 | 确定 | Phase2 | Release for RunCard | 无 |  | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Activity | 159 | Remove From Inventory | PCMS | 次重点 | 未确定 | Phase2 | Remove From Inventory | 无 |  | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Activity | 160 | Return From Repair | PCMS | 次重点 | 未确定 | Phase2 | Return From Repair | 无 |  | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Activity | 161 | Return To Inventory | PCMS | 次重点 | 未确定 | Phase2 | Return To Inventory | 无 |  | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Activity | 162 | Return To PE | PCMS | 次重点 | 未确定 | Phase2 | Return To PE | 无 |  | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Activity | 163 | Scrap | PCMS | 次重点 | 未确定 | Phase2 | Scrap | 无 |  | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Configuration | 164 | Location Maintenance | PCMS | 次重点 | 未确定 | Phase2 | Location Maintenance | 无 |  | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Run Time | 165 | UnMounting Of Probe Card | PCMS | 次重点 | 未确定 | Phase2 | UnMounting Of Probe Card | 无 |  | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Activity | 166 | UnScrap | PCMS | 次重点 | 未确定 | Phase2 | UnScrap | 无 |  | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Activity | 167 | Send To Vendor Repair | PCMS | 次重点 | 未确定 | Phase2 | Send To Vendor Repair | 无 |  | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
PRMS | MainGUI | 168 | Manage Resist Equipment Alarm | PRMS |  |  | Phase2 |  | 无 |  | 杨金杰 | 郭天娇 | 无锡
| Configuration | 169 | PR Batch Assignment And Qualification | PRMS |  |  | Phase2 |  | 无 |  | 杨金杰 | 郭天娇 | 无锡
| Activity | 170 | Change Location | PRMS |  |  | Phase2 |  | 无 |  | 杨金杰 | 郭天娇 | 无锡
| Configuration | 171 | Location Maintenance | PRMS |  |  | Phase2 |  | 无 |  | 杨金杰 | 郭天娇 | 无锡
| Activity | 172 | Photo Resist Consumable Events | PRMS |  |  | Phase2 |  | 无 |  | 杨金杰 | 郭天娇 | 无锡
| Configuration | 173 | Photo Resist Equipment Maintenance | PRMS |  |  | Phase2 |  | 无 |  | 杨金杰 | 郭天娇 | 无锡
| Activity | 174 | Photo Resist History | PRMS |  |  | Phase2 |  | 无 |  | 杨金杰 | 郭天娇 | 无锡
| Configuration | 175 | Photo Resist Location Maintenance | PRMS |  |  | Phase2 |  | 无 |  | 杨金杰 | 郭天娇 | 无锡
| Configuration | 176 | Photo Resist Part Maintenance | PRMS |  |  | Phase2 |  | 无 |  | 杨金杰 | 郭天娇 | 无锡
| Configuration | 177 | PR Recipe | PRMS |  |  | Phase2 |  | 无 |  | 杨金杰 | 郭天娇 | 无锡
| Activity | 178 | PR Recipe History | PRMS |  |  | Phase2 |  | 无 |  | 杨金杰 | 郭天娇 | 无锡
| Configuration | 179 | Resist Consumables | PRMS |  |  | Phase2 |  | 无 |  | 杨金杰 | 郭天娇 | 无锡
PTMS | Create Part | 180 | Batch Create Part | PTMS | 重点 | 确定 | Phase2 |  | 无 |  | 罗涛 | 王华强 | 无锡 |  |  | 2023/2/1 | [5 empty] | 3
| Part Main GUI | 181 | Batch Create Part Master | PTMS | 重点 | 确定 | Phase2 |  | 无 |  | 罗涛 | 王华强 | 无锡 |  |  | 2023/2/1 | [5 empty] | 5
| Create Part | 182 | Create Part | PTMS | 重点 | 确定 | Phase2 |  | 无 |  | 罗涛 | 王华强 | 无锡 |  |  | 2023/2/1 | [5 empty] | 3
| Configuration | 183 | Cost Center | PTMS | 次重点 | 确定 | Phase2 |  | 无 |  | 罗涛 | 王华强 | 无锡 |  |  | 2023/2/1 | [5 empty] | 5
| Part Group Maintain | 184 | Modify Part Group Relationship | PTMS | 次重点 | 确定 | Phase2 |  | 无 |  | 罗涛 | 王华强 | 无锡 |  |  | 2023/2/1 | [5 empty] | 3
| Configuration | 185 | Part Cycle Limit | PTMS | 重点 | 确定 | Phase2 |  | 无 |  | 罗涛 | 王华强 | 无锡 |  |  | 2023/2/1 | [5 empty] | 3
| MainGUI | 186 | Part Main Screen View | PTMS | 重点 | 确定 | Phase2 |  | 无 |  | 罗涛 | 王华强 | 无锡 |  |  | 2023/2/1 | [5 empty] | 3
| Part Main GUI | 187 | Part Master MainGUI | PTMS | 次重点 | 确定 | Phase2 |  | 无 |  | 罗涛 | 王华强 | 无锡 |  |  | 2023/2/1 | [5 empty] | 5
| Replace Parts | 188 | Replace Parts | PTMS | 重点 | 确定 | Phase2 |  | 无 |  | 罗涛 | 王华强 | 无锡 |  |  | 2023/2/1 | [5 empty] | 5
| Part Group Maintain | 189 | Query Part Group Relationship | PTMS | 次重点 | 确定 | Phase2 |  | 无 |  | 罗涛 | 王华强 | 无锡 |  |  | 2023/2/1 | [5 empty] | 3
RTD |  | 190 | Maintain Mark Lot | RTD |  | 未确定 |  |  | 无 |  | 申克楠
Reticle | Maintain | 191 | Batch Reticle Properties | Reticle | 非重点 | 确定 | Phase2 |  | 无 | 同时变更多块Reticle属性 | 杨金杰 | 郭天娇 | 无锡
| Maintain | 192 | Batch IRIS Wafer Count | Reticle | 非重点 | 确定 | Phase2 |  | 无 | 同时变更多块Reticle IRIS 的Wafer Count | 杨金杰 | 郭天娇 | 无锡
| Maintain | 193 | Batch IRIS Wafer Count Import And Export | Reticle | 非重点 | 确定 | Phase2 |  | 无 | 同时导出输入多块Reticle IRIS的 Wafer Count | 杨金杰 | 郭天娇 | 无锡
| Maintain | 194 | Batch Pod Properties | Reticle | 非重点 | 确定 | Phase2 |  | 无 | 同时变更多个Pod 属性 | 杨金杰 | 郭天娇 | 无锡
| Maintain | 195 | Batch Starlight | Reticle | 非重点 | 确定 | Phase2 |  | 无 | 同时变更多块Reticle的Starlight | 杨金杰 | 郭天娇 | 无锡
| Maintain | 196 | Batch Wafer Count | Reticle | 非重点 | 确定 | Phase2 |  | 无 | 同时变更多块Reticle进行的Wafer Count | 杨金杰 | 郭天娇 | 无锡
| Maintain | 197 | Batch XCDA Qtime | Reticle | 非重点 | 确定 | Phase2 |  | 无 | 同时变更多块Reticle的XCDA Qtime | 杨金杰 | 郭天娇 | 无锡
| Maintain | 198 | Batch XCDA Qtime Import And Export | Reticle | 非重点 | 确定 | Phase2 |  | 无 | 同时导出输入多块Reticle的XCDA Qtime | 杨金杰 | 郭天娇 | 无锡
| Reticle Activity | 199 | Change Location | Reticle | 重点 | 确定 | Phase1 |  | 无 | 变更更Reticle Location | 杨金杰 | 郭天娇 | 无锡 |  |  | 11月9日 | [5 empty] | 3 | 11月10日 | 11月13日
| Maintain | 200 | Compatible Condition | Reticle | 重点 | 确定 | Phase1 |  | 无 | Pod,Retcile Match Conditiron设定 | 杨金杰 | 郭天娇 | 无锡
| Reticle Activity | 201 | Reticle Data Collection | Reticle |  |  |  |  | 无 |  | 李彬
| Create And Delete | 202 | Delete Reticle | Reticle | 重点 | 确定 | Phase1 |  | 无 | Delete 已经Create的Reticle | 杨金杰 | 郭天娇 | 无锡 |  |  | 11月22日 | [5 empty] | 3 | 11月23日 | 11月26日
| Reticle Activity | 203 | Inspection In | Reticle | 重点 | 确定 | Phase1 |  | 无 | 开始Inspeticon | 杨金杰 | 郭天娇 | 无锡 |  |  | 11月15日 | [5 empty] | 3 | 11月16日 | 11月19日
| Reticle Activity | 204 | Inspection Out | Reticle | 重点 | 确定 | Phase1 |  | 无 | Inspection结束 | 杨金杰 | 郭天娇 | 无锡 |  |  | 11月15日 | [5 empty] | 3 | 11月16日 | 11月19日
| Maintain | 205 | IRIS Wafer Count | Reticle | 重点 | 确定 | Phase1 |  | 无 | 变更IRIS的Wafer Count | 杨金杰 | 郭天娇 | 无锡 |  |  | 11月22日 | [5 empty] | 3 | 11月23日 | 11月26日
| Reticle Activity | 206 | Load Reticle | Reticle | 重点 | 确定 | Phase1 |  | 无 | EAP未适用时,Load Reticle到机台 | 杨金杰 | 郭天娇 | 无锡 |  |  | 11月15日 | [5 empty] | 3 | 11月16日 | 11月19日
| Maintain | 207 | Maintain Equipment Type | Reticle | 重点 | 确定 | Phase1 |  | 无 | 变更Reticle的属性(Reticle Spec),涉及Reticle的各种Limit | 杨金杰 | 郭天娇 | 无锡 |  |  | 11月22日 | [5 empty] | 3 | 11月23日 | 11月26日
| Maintain | 208 | Maintain Reticle Location | Reticle | 重点 | 确定 | Phase1 |  | 无 | 变更Reticle 的Locaiton属性 | 杨金杰 | 郭天娇 | 无锡 |  |  | 11月9日 | [5 empty] | 3 | 11月10日 | 11月13日
| Maintain | 209 | Maintain Reticle LocationType | Reticle | 重点 | 确定 | Phase1 |  | 无 | 变更Reticle的 Locaiton Type | 杨金杰 | 郭天娇 | 无锡 |  |  | 11月9日 | [5 empty] | 3 | 11月10日 | 11月13日
| Maintain | 210 | Maintain Reticle Grade | Reticle | 次重点 | 确定 | Phase1 |  | 无 | 变更Reticle Grade与IRIS DC等相关联 | 杨金杰 | 郭天娇 | 无锡 |  |  | 11月22日 | [5 empty] | 3 | 11月23日 | 11月26日
| Maintain | 211 | Mask Clean | Reticle | 重点 | 确定 | Phase1 |  | 无 | 设定Reticle Clean | 杨金杰 | 郭天娇 | 无锡 |  |  | 11月15日 | [5 empty] | 3 | 11月16日 | 11月19日
| Reticle Activity | 212 | Modify Attribute | Reticle | 次重点 | 确定 | Phase1 |  | 无 |  | 杨金杰 | 郭天娇 | 无锡 |  |  | 11月22日 | [5 empty] | 3 | 11月23日 | 11月26日
| Reticle Activity | 213 | Offline Retrieve Reticle | Reticle | 次重点 | 确定 | Phase1 |  | 无 | Offline接收Reticle | 杨金杰 | 郭天娇 | 无锡 |  |  | 11月29日 | [5 empty] | 3 | 11月30日 | 12月3日
| Pod Activity | 214 | Change Location | Reticle | 重点 | 确定 | Phase1 |  | 无 | Change Pod的Location | 杨金杰 | 郭天娇 | 无锡 |  |  | 11月9日 | [5 empty] | 3 | 11月10日 | 11月13日
| Pod Activity | 215 | Confirm Quality | Reticle | 非重点 | 确定 | Phase2 |  | 无 | Pod Inline时的 Qulity Check | 杨金杰 | 郭天娇 | 无锡
| Create And Delete | 216 | Pod Mgt | Reticle | 次重点 | 确定 | Phase1 |  | 无 | Pod 管理?? | 杨金杰 | 郭天娇 | 无锡 |  |  | 11月29日 | [5 empty] | 3 | 11月30日 | 12月3日
| Maintain | 217 | Remount And Clean Count | Reticle | 重点 | 确定 | Phase1 |  | 无 | 变更Reticle Clean Count | 杨金杰 | 郭天娇 | 无锡 |  |  | 11月22日 | [5 empty] | 3 | 11月23日 | 11月26日
| Reticle Activity | 218 | Request Inspection | Reticle | 重点 | 确定 | Phase1 |  | 无 | 设置Pod Inspection | 杨金杰 | 郭天娇 | 无锡 |  |  | 11月15日 | [5 empty] | 3 | 11月16日 | 11月19日
| Pod Activity | 219 | Reserve POD | Reticle | 非重点 | 确定 | Phase2 |  | 无 |  | 杨金杰 | 郭天娇 | 无锡
| Reticle Activity | 220 | Cancel Scan | Reticle | 重点 | 确定 | Phase1 |  | 无 | Cancel 已经开始Scan的操作 | 杨金杰 | 郭天娇 | 无锡 |  |  | 11月15日 | [5 empty] | 3 | 11月16日 | 11月19日
| Reticle Activity | 221 | Return To Customer | Reticle | 重点 | 确定 | Phase1 |  | 无 | 退回客户中心 | 杨金杰 | 郭天娇 | 无锡 |  |  | 11月29日 | [5 empty] | 3 | 11月30日 | 12月3日
| Reticle Activity | 222 | Terminate | Reticle | 重点 | 确定 | Phase1 |  | 无 | 终结Reticle(不再使用)? | 杨金杰 | 郭天娇 | 无锡 |  |  | 11月29日 | [5 empty] | 3 | 11月30日 | 12月3日
| Reticle Activity | 223 | Unload Reticle | Reticle | 非重点 | 确定 | Phase2 |  | 无 | EAP未使用时,Unload Reticle的电算操作 | 杨金杰 | 郭天娇 | 无锡
| Reticle Activity | 224 | Batch XCDA Purge Time Remove | Reticle | 非重点 | 确定 | Phase2 |  | 无 | 消除多个Reticle的 XCDA Purge Time | 杨金杰 | 郭天娇 | 无锡
| Reticle Activity | 225 | Batch XCDA Qtime Remove | Reticle | 非重点 | 确定 | Phase2 |  | 无 | 消除多个Reticle的 XCDA Qtime | 杨金杰 | 郭天娇 | 无锡
Sampling |  | 226 | Step Sampling | Sampling |  | 确定 | Phase1 | Step Sampling | 无 | Step Sampling 主页,展示 Product Name + Top Plan Name | Subpl申an克 N楠ame + St | pSeq + Step ID | Capability相关 | Sampling信 | 。不支持ADD/ | EL ,只可以修 | 。新建由Defa | lt Sampling导
|  | 227 | Default Sampling | Sampling |  | 确定 | Phase1 | Default Sampling | 无 | 作为创建Step Sampling 的默认值设置。包含WaferSelecti | n Rule申克楠
|  | 228 | YE Step Sampling | Sampling |  | 确定 | Phase1 | YE Step Sampling | 有 | YE Step Sampling 主页,创建修改规则。配置属性。 | 申克楠
|  | 229 | Modify Key Lot Flag | Sampling |  | 确定 | Phase2 | Modify Key Lot Flag | 无 | 针对YE Key EQP 解绑Key Lot,系统重新选择其它Key Lot | 申克楠
|  | 230 | Lot Sampling Runtime History | Sampling |  | 确定 | Phase1 | Lot Sampling Runtime History | 无 | YE or Step Sampling history,需要支持导出Excel功能 | 申克楠
|  | 231 | Smart Sampling Special Flag | Sampling |  | 确定 | Phase2 | Smart Sampling Special Flag | 无 | 针对Key EQP 删除/添加 非YE Step Sampling Key Lot | 申克楠
|  | 232 | Smart Sampling Key Equipment | Sampling |  | 确定 | Phase1 | Smart Sampling Key Equipment | 无 | 非YE Step Key EQP 设置 | 申克楠
|  | 233 | Smart Sampling Key Step Association | Sampling |  | 确定 | Phase1 | Smart Sampling Key Step Association | 无 | Process Step 绑定非YE 量测 Step 关系 | 申克楠
| Sampling History | 234 | Smart Sampling MFG Skip History | Sampling |  | 确定 | Phase2 | Smart Sampling MFG Skip History | 无 | Smart Sampling Special Scan modeling history | 申克楠
|  | 235 | YE Key Equipment | Sampling |  | 确定 | Phase1 | YE Key Equipment | 无 | YE Step Key EQP 设置 | 申克楠
|  | 236 | YE Key Step Association | Sampling |  | 确定 | Phase1 | YE Key Step Association | 无 | Process Step 绑定 YE Step 关系 | 申克楠
|  | 237 | YE Step By Flow | Sampling |  | 确定 | Phase2 | YE Step By Flow | 无 | 针对Product ,Plan,选择Step 配置Sampling 规则 | 申克楠
|  | 238 | YE Step By Lot | Sampling |  | 确定 | Phase2 | YE Step By Lot | 无 | 根据lot设置YE Step 的Skip/Scan | 申克楠
| Sampling History | 239 | YE Step Sampling History | Sampling |  | 确定 | Phase2 | YE Step Sampling History | 无 | YE Step Sampling 历史记录 | 申克楠
Transportation |  | 240 | Cancel Reticle Transportation | Transportation |  | 未确定 | Phase2 |  | 无 |  | 罗涛
|  | 241 | Cancel Transportation | Transportation |  | 未确定 | Phase2 |  | 无 |  | 罗涛
| MCS Control | 242 | Reticle Transportation Request | Transportation |  | 未确定 | Phase2 |  | 无 |  | 罗涛
| MCS Control | 243 | Reticle Sync Stocker | Transportation |  | 未确定 | Phase2 |  | 无 |  | 罗涛
|  | 244 | MCS Inventory Info | Transportation |  | 未确定 | Phase2 |  | 无 |  | 罗涛
|  | 245 | Sync Reticle Stocker | Transportation |  | 未确定 | Phase2 |  | 无 |  | 罗涛
|  | 246 | Transportation Reticle Request | Transportation |  | 未确定 | Phase2 |  | 无 |  | 罗涛
|  | 247 | View Reticle Stocker | Transportation |  | 未确定 | Phase2 |  | 无 |  | 罗涛
|  | 248 | Sync Carrier Info | Transportation |  | 未确定 | Phase2 |  | 无 |  | 罗涛
|  | 249 | Transportation Request | Transportation |  | 未确定 | Phase2 |  | 无 |  | 罗涛
|  | 250 | Transportation Recovery | Transportation |  | 未确定 | Phase2 |  | 无 |  | 罗涛
WAT | Wafer Test | 251 | WAT Hold Information | WAT | 次重点 | 未确定 | Phase2 | WAT Hold Information | 无 |  | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
Wafer Test | 252 | WAT Result Information | WAT | 次重点 | 未确定 | Phase2 | WAT Result Information | 无 |  | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
Wafer Test | 253 | Final InkMap Prod Setting | WAT | 次重点 | 未确定 | Phase2 | Final InkMap Prod Setting | 无 |  | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
Wafer Test | 254 | Wafer Test Information | WAT | 次重点 | 未确定 | Phase2 | Wafer Test Information | 无 |  | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
Wafer Test | 255 | Wafer Test Result History | WAT | 次重点 | 未确定 | Phase2 | Wafer Test Result History | 无 |  | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
Wafer Test | 256 | WT Product Yield Setting | WAT | 次重点 | 未确定 | Phase2 | WT Product Yield Setting | 无 |  | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
Wafer Test | 257 | WT Retest Recipe Setting | WAT | 次重点 | 未确定 | Phase2 | WT Retest Recipe Setting | 无 |  | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
Wafer Test | 258 | WT Test Step Recipe Configuration | WAT | 次重点 | 未确定 | Phase2 | WT Test Step Recipe Configuration | 无 |  | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增

## Page2
完成率
|  |  |  | 对比300works | 对比B2 | 完成 | 设计中 | 开发中 | 测试中 | 未推进 | 待确认
Carrier | 29 | 0 | 18 | 62% | #DIV/0! | 18 | 1 | 1 | 0 | 0 | 3
Machine | 37 | 0 | 12 | 32% | #DIV/0! | 12 | 0 | 0 | 0 | 0 | 0
Lot | 105 | 0 | 80 | 76% | #DIV/0! | 78 | 0 | 0 | 0 | 0 | 2
Inventory | 10 | 0 | 10 | 100% | #DIV/0! | 10 | 0 | 0 | 0 | 0 | 0
WIP | 66 | 0 | 59 | 89% | #DIV/0! | 52 | 0 | 2 | 0 | 1 | 1
CSN | 6 | 3 | 3 | 50% | 100% | 3 | 0 | 0 | 0 | 0 | 0
Test Wafer | 23 | 0 | 23 | 100% | #DIV/0! | 23 | 0 | 0 | 0 | 0 | 0
Reticle | 63 | 0 | 30 | 48% | #DIV/0! | 30 | 0 | 0 | 0 | 0 | 2
Sampling | 16 | 0 | 10 | 63% | #DIV/0! | 10 | 0 | 0 | 2 | 0 | 0
Phase1 | 355 | 3 | 245 | 69% | 8167% | 236 | 1 | 3 | 2 | 1 | 8
OCAP | 2 | 0 | 1 | 50% | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0
PCMS | 36 | 0 | 0 | 0% | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0
PRMS | 12 | 0 | 0 | 0% | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0
PTMS | 10 | 0 | 0 | 0% | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0
RTD | 1 | 0 | 0 | 0% | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 11 | 0 | 0 | 0% | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0
WAT | 12 | 0 | 0 | 0% | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0
Phase2 | 84 | 0 | 1 | 1% | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0
Total | 439 | 3 | 246 | 56% | 8200% | 236 | 1 | 3 | 2 | 1 | 8

## Page3
Level1 | Level2 | No. | 300Works(Basic) | B2 Funcation | cvMES | 模块 | 功能确认 | 开发阶段 | 界面说明 | 责任人 | 开发地 | 开发人 | 交期 | 实绩 | 完成 | Remark
U U Carrier Mgt |  | 1 | Add Carrier Comment |  | Add Carrier Comment | Carrier | 设计中 | 2022 | 添加Carrier Comment | 杨金杰
|  | 2 | Assign Carrier |  | Assign Carrier | Carrier | 完成 | 2022 | Lot&Carrier逻辑 Match | 杨金杰
|  | 3 |  |  | Deassign Carrier | Carrier | 完成 | 2022 | Lot&Carrier逻辑 Divide | 杨金杰
|  | 4 | Cancel Clean |  | Cancel Clean | Carrier | 待确认 | 2022 | Cancel Set Clean,Cancel Start Clean | 杨金杰
|  | 5 | Cancel Inspection |  |  | Carrier | 未推进 | 2022 |  | 杨金杰
|  | 6 | Cancel Reserve Target Carrier |  | Cancel Reserve Target Carrier | Carrier | 完成 | 2022 | 解绑预约Carrier,其他用途可以使用 | 杨金杰
|  | 7 | Carrier Data Collection |  |  | Carrier | 待确认 | 2022 |  | 李彬
| date/Modify Carrier I | fo8 | Change Slotmap Info |  | Change Slot Map Info | Carrier | 完成 | 2022 | 改变同lot中 wafer slot信息 | 杨金杰
|  | 9 |  |  | Change Carrier Info | Carrier | 完成 | 2022 |  | 杨金杰
|  | 10 | Create Carrier |  | Create Carrier | Carrier | 完成 | 2022 | 单个或多个Carrier创建(包括Foup.F | SB)杨金杰
|  | 11 | Disposal/Undo Disposal |  |  | Carrier | 未推进 | 2022 |  | 杨金杰
|  | 12 | Exchange Carrier |  | Exchange Carrier | Carrier | 完成 | 2022 | Carrier为基准,Lot逐个传出到新的异 | Fo杨up金杰
|  | 13 | Hold Carrier |  | Hold Carrier | Carrier | 完成 | 2022 | Hold Carrier | 杨金杰
|  | 14 | Inspection Flow Control |  |  | Carrier | 未推进 | 2022 |  | 杨金杰
| date/Modify Carrier I | fo15 | Modify Carrier Attributes |  | Modify Carrier Attributes | Carrier | 完成 | 2022 |  | 杨金杰
|  | 16 | Start/End Inspection |  |  | Carrier | 未推进 | 2022 |  | 杨金杰
|  | 17 | Release Carrier |  | Release Carrier | Carrier | 完成 | 2022 | 对Hold Carrier进行Release | 杨金杰
|  | 18 | Remove Carrier |  | Scrap Carrier | Carrier | 完成 | 2022 | 报废Carrier | 杨金杰
|  | 19 | Repair FOUP |  |  | Carrier | 未推进 | 2022 |  | 杨金杰
|  | 20 | Reserve Target Carrier |  | Reserve Target Carrier | Carrier | 开发中 | 2022 | 预约Carrier,防止其他用途使用 | 杨金杰
|  | 21 | Set Disposal/Cancel Disposal |  |  | Carrier | 未推进 | 2022 |  | 杨金杰
|  | 22 |  |  | Cancel Scrap Carrier | Carrier | 完成 | 2022 | 解除报废Carrier | 杨金杰
|  | 23 |  |  | Change Carrier Clean State | Carrier | 完成 | 2022 |  | 杨金杰
|  | 24 |  |  | Carrier RFID Management | Carrier | 完成 | 2022 |  | 杨金杰
|  | 25 | Set Clean |  | Set Clean | Carrier | 待确认 | 2022 |  | 杨金杰
|  | 26 | Set Inspection |  |  | Carrier | 未推进 | 2022 |  | 杨金杰
|  | 27 | Special Transfer Lot |  |  | Carrier | 未推进 | 2022 |  | 杨金杰
|  | 28 | Start/End Clean |  | Start/End Clean | Carrier | 待确认 | 2022 |  | 杨金杰
|  | 29 | Transfer Lot |  | Transfer Lot | Carrier | 完成 | 2022 | Lot Base 传到其他同类型Foup | 杨金杰
|  | 30 | Update Carrier Component |  |  | Carrier | 未推进 | 2022 |  | 杨金杰
|  | 31 |  |  | View Carrier List | Carrier | 完成 | 2022 |  | 杨金杰
| View Carrier Info | 32 | View Carrier Cleaning History |  |  | Carrier | 未推进 | 2022 |  | 杨金杰
| View Carrier Info | 33 | View Carrier Cycle |  |  | Carrier | 未推进 | 2022 |  | 杨金杰
| View Carrier Info | 34 | View Carrier History |  | View Carrier History | Carrier | 完成 | 2022 | 查询Carrier的Detail 历史记录 | 杨金杰
| View Carrier Info | 35 | View Carrier Status |  | View Carrier Status | Carrier | 完成 | 2022 | 查询Carrier 当前状态 | 杨金杰
Eqp Mgt |  | 36 | Buffer Tool Physical Foup Maintain |  |  | Machine | 未推进 | 2022 |  | 杨金杰
| One Key Touch | 37 | Control Action History |  |  | Machine | 未推进 | 2022 |  | 杨金杰
|  | 38 | Customize EQP Information |  |  | Machine | 未推进 | 2022 |  | 杨金杰
|  | 39 | Delete Chamber Current Lots |  |  | Machine | 未推进 | 2022 |  | 杨金杰
|  | 40 | Equipment AMA Mode Change |  | Change Machine AMA Mode | Machine | 完成 | 2022 |  | 杨金杰
|  | 41 | Equipment Couple Port |  |  | Machine | 未推进 | 2022 |  | 杨金杰
|  | 42 | EQP Manual Process Configuration |  |  | Machine | 未推进 | 2022 |  | 杨金杰
|  | 43 | Equipment Port State Change |  | Change Port State | Machine | 完成 | 2022 |  | 杨金杰
|  | 44 | Equipment Process History |  | View Machine Process History | Machine | 完成 | 2022 |  | 杨金杰
|  | 45 | Equipment State Change |  | Change Machine State | Machine | 完成 | 2022 | 更改Machine Up,Down等信息 及Outo | Serv杨ic金e等杰信息 | 更
|  | 46 | MFG Eqp Security Control Maintenance |  |  | Machine | 未推进 | 2022 |  | 杨金杰
|  | 47 | Modify Equipment Attribute |  |  | Machine | 未推进 | 2022 |  | 杨金杰
|  | 48 | Modify Eqp Chamber Run Count |  |  | Machine | 未推进 | 2022 |  | 杨金杰
|  | 49 | Modify Equipment Current Lots |  |  | Machine | 未推进 | 2022 |  | 杨金杰
|  | 50 | Set Equipment Capability |  |  | Machine | 未推进 | 2022 |  | 杨金杰
|  | 51 |  |  | Change Machine Control Mode | Machine | 完成 | 2022 |  | 杨金杰
| One Key Touch | 52 | One Key Touch |  |  | Machine | 未推进 | 2022 |  | 杨金杰
| One Key Touch | 53 | One Key Touch Detail History |  |  | Machine | 未推进 | 2022 |  | 杨金杰
|  | 54 | Equipment Port Access Mode Change |  | Change Port Access Mode | Machine | 完成 | 2022 |  | 杨金杰
| One Key Touch | 55 | Power Source Setup |  |  | Machine | 未推进 | 2022 |  | 杨金杰
| One Key Touch | 56 | Power Source Setup History |  |  | Machine | 未推进 | 2022 |  | 杨金杰
|  | 57 | Reticle Equipment Process History |  |  | Machine | 未推进 | 2022 |  | 杨金杰
|  | 58 | Set Chamber Capability |  |  | Machine | 未推进 | 2022 |  | 杨金杰
| Tank Control | 59 | Tank Count Info |  |  | Machine | 未推进 | 2023 1Q |  | 杨金杰
| Tank Control | 60 | Tank OOS History |  |  | Machine | 未推进 | 2023 1Q |  | 杨金杰
| Tank Control | 61 | Tank Running History |  |  | Machine | 未推进 | 2023 1Q |  | 杨金杰
|  | 62 | Tool Recovery Control System |  |  | Machine | 未推进 | 2022 |  | 杨金杰
|  | 63 | Tool Recovery Package Setup |  |  | Machine | 未推进 | 2022 |  | 杨金杰
|  | 64 | View Equipment Auto Mode |  | View Machine Auto Mode | Machine | 完成 | 2022 |  | 杨金杰
|  | 65 | Equipment History |  | View Machine History | Machine | 完成 | 2022 | 查询Machine 的Detail 历史记录 | 杨金杰
|  | 66 | View Equipment Status |  | View Machine Status | Machine | 完成 | 2022 | 查询 Machine 的当前状态 | 杨金杰
| Tank Control | 67 | Wet Tank Control |  |  | Machine | 未推进 | 2023 1Q |  | 杨金杰
| PMS | 68 | Arrange PM |  |  | Machine | 未推进 | 2023 1Q |  | 杨金杰
| PMS | 69 | Conditional PM |  |  | Machine | 未推进 | 2023 1Q |  | 杨金杰
| PMS | 70 | Trigger Readings |  |  | Machine | 未推进 | 2023 1Q |  | 杨金杰
| PMS | 71 | Usage Meter |  |  | Machine | 未推进 | 2023 1Q |  | 杨金杰
|  | 72 |  |  | View Current Alarm | Machine | 完成 | 2022 | 根据Lot、Machine、时间等查询Alar | 信息杨金杰
|  | 73 |  |  | AlarmRun | Machine | 完成 | 2022 |  | 杨金杰
|  | 74 |  |  | View Machine Info | Machine | 完成 | 2022 |  | 杨金杰
| Tank Control | 75 | Tank Count Info |  |  | Machine | 未推进 | 2023 1Q |  | 杨金杰
| Tank Control | 76 | Tank Running History |  |  | Machine | 未推进 | 2023 1Q |  | 杨金杰
ot Customizatio |  | 77 | Modify Lot Contamination Level |  | Modify Lot Contamination Level | Lot | 完成 | 2022 | 修改lot污染等级 | 罗涛
| 78 | Add Steps |  | Add Steps | Lot | 完成 | 2022 | Add Steps | 罗涛
| 79 | Batch Modify Lot Attribute |  | Batch Modify Lot Attribute | Lot | 完成 | 2022 | 批量修改lot属性 | 罗涛
Reassign | 80 | Change Sales Order |  |  | Lot | 待确认 | 2022 |  | 罗涛
eedForward Attribut | 81 | Copy FeedForward Information |  |  | Lot | 未推进 | 2022 |  | 罗涛
eedForward Attribut | 82 | Delete FeedForward Information |  |  | Lot | 未推进 | 2022 |  | 罗涛
| 83 | Modify Lot Attribute For MFG |  | Modify Lot Attribute For MFG | Lot | 完成 | 2022 | 修改lot属性for MFG | 罗涛
| 84 | Modify Lot Attribute For QC |  | Modify Lot Attribute For QC | Lot | 完成 | 2022 | 修改lot属性for QC | 罗涛
| 85 | Modify Lot Attribute For QE |  |  | Lot | 未推进 | 2022 |  | 罗涛
| 86 | Lot Specialization |  |  | Lot | 未推进 | 2022 |  | 罗涛
eedForward Attribut | 87 | Modify FeedForward Information |  |  | Lot | 未推进 | 2022 |  | 罗涛
| 88 | Modify Lot Attribute |  | Modify Lot Attribute | Lot | 完成 | 2022 | 修改lot属性 | 罗涛
Reassign | 89 | Plan Reassign |  | Future Reassign | Lot | 完成 | 2022 |  | 罗涛
| 90 | Modify Potential Attribute |  |  | Lot | 未推进 | 2022 |  | 罗涛
Reassign | 91 | Reassign Lot |  | Reassign Lot | Lot | 完成 | 2022 | Reassign Lot to New Product Flow | 罗涛
Reassign | 92 | Reassign Lot For Monitor |  | Reassign Lot For NPW | Lot | 完成 | 2022 |  | 罗涛
| 93 | Maintain RMS Flag |  |  | Lot | 未推进 | 2022 |  | 罗涛
| 94 | Set Stepper |  |  | Lot | 未推进 | 2022 |  | 罗涛
| 95 | Undo Finish |  |  | Lot | 未推进 | 2022 |  | 罗涛
| 96 | Choose Alter Step |  |  | Lot | 未推进 | 2022 |  | 罗涛
| 97 | View Hold Lot |  | View Hold Lot Info | Lot | 完成 | 2022 |  | 罗涛
Hold | 98 | Batch Hold |  | Batch Hold | Lot | 完成 | 2022 | 根据 PFO,Capability, Stage 等条件查 | Lot L罗ist涛, 批量 | 定
| 99 | Edit Hold Comment |  | Edit Hold | Lot | 完成 | 2022 | 更改Hold 信息 | 罗涛
Hold | 100 | Hold |  | Hold Lot | Lot | 完成 | 2022 | 锁住Lot(Lot Hold State N->Y),提 | By L罗ot,涛Carrier, | atch ID 3种方
Release | 101 | Release |  | Release Lot | Lot | 完成 | 2022 | 解锁Lot(Lot Hold State Y->N) | 罗涛
| 102 |  |  | Release Action | Lot | 完成 | 2022 |  | 罗涛
MixRun | 103 | View Mix Run Status |  |  | Lot | 未推进 | 2022 |  | 罗涛
eview Wafer Selecti | n C1o0n4fig | Wafer Selection History For Auto YE Review |  |  | Lot | 未推进 | 2022 |  | 罗涛
eview Wafer Selecti | n C1o0n5fig | Update Wafer List Of YE Review |  |  | Lot | 未推进 | 2022 |  | 罗涛
eview Wafer Selecti | n C1o0n6fig | Setting By Capability |  |  | Lot | 未推进 | 2022 |  | 罗涛
eview Wafer Selecti | n C1o0n7fig | Setting By Product |  |  | Lot | 未推进 | 2022 |  | 罗涛
afer Randomizatio | 108 | Adhoc Recover |  |  | Lot | 未推进 | 2022 |  | 罗涛
Reposition | 109 | Back Up Step |  |  | Lot | 未推进 | 2022 |  | 罗涛
Release | 110 | Batch Release |  | Batch Release | Lot | 完成 | 2022 | 批量解锁Lot(Lot Hold State Y->N) | 罗涛
afer Randomizatio | 111 | Config Random Recipe |  |  | Lot | 未推进 | 2022 |  | 罗涛
afer Randomizatio | 112 | Lot Random History |  |  | Lot | 未推进 | 2022 |  | 罗涛
Pilot | 113 | Add Measurement Step |  |  | Lot | 完成 | 2022 |  | 罗涛/李彬
Pilot | 114 | Create Pilot |  | Create Pi Lot | Lot | 完成 | 2022 |  | 罗涛
Pilot | 115 | End Pilot |  | End PiLot | Lot | 完成 | 2022 |  | 罗涛
Doma Management | 116 | Doma Path Config History |  |  | Lot | 未推进 | 2022 |  | 罗涛
Doma Management | 117 | Doma Path Maintain |  |  | Lot | 未推进 | 2022 |  | 罗涛
Doma Management | 118 | Doma Path Setting |  |  | Lot | 未推进 | 2022 |  | 罗涛
Doma Management | 119 | DOMA RCD History |  |  | Lot | 未推进 | 2022 |  | 罗涛
Future | 120 | Batch Future Hold |  | Batch Future Hold | Lot | 完成 | 2022 |  | 罗涛
Future | 121 | Cancel Batch Future Hold |  | Future Action List | Lot | 完成 | 2022 |  | 罗涛
Future | 122 | Cancel Future Action |  | Future Action List | Lot | 完成 | 2022 |  | 罗涛
Future | 123 | Future Hold |  | Set Future Hold | Lot | 完成 | 2022 |  | 罗涛
Future | 124 | Future Hold By Customer |  |  | Lot | 未推进 | 2022 |  | 罗涛
Future | 125 | Future Merge |  | Set Future Merge | Lot | 完成 | 2022 |  | 罗涛
Future | 126 | Future Split |  | Set Future Split | Lot | 完成 | 2022 |  | 罗涛

## Page4
| Future | 127 | Set Future Hold Step Group |  |  | Lot | 未推进 | 2022 |  | 罗涛
| Future | 128 |  |  | Future Reserve Machine | Lot | 完成 | 2022 | 提前设置需要在后续 Step 做的机台 | 罗涛
| SML | 129 | Inline Split For Special Lot |  |  | Lot | 未推进 | 2022 |  | 杨金杰
| SML | 130 | Inline Split Setting |  | Inline Split Setting | Lot | 完成 | 2022 |  | 杨金杰
| Doma Management | 131 | Lot Doma History |  |  | Lot | 未推进 | 2022 |  | 罗涛
| Sorter | 132 | View Wafer Verification Result |  | View Wafer Verification Result | Lot | 完成 | 2022 | 查询 Sorter 读取的Wafer 的T7 Code | 果 杨金杰
| Sorter | 133 | Wafer Rotate |  | Wafer Rotate | Lot | 完成 | 2022 | 对Carrier中Wafer转角度 | 杨金杰
| Sorter | 134 | Wafer Verification |  | Wafer Verification | Lot | 完成 | 2022 |  | 杨金杰
| Sorter | 135 |  |  | Transfer Lot | Lot | 完成 | 2022 |  | 杨金杰
| Merge/Split | 136 | Merge |  | Merge Lot | Lot | 完成 | 2022 | Unscheduled Lot Merge功能,支持多 | 相同杨S金o杰urce l | t的lot 分别与 | Lot Merge
| Merge/Split | 137 | Split |  | Split Lot | Lot | 完成 | 2022 | Lot 分批(Physical Remote/Local,Logi | al) 杨金杰
|  | 138 | Rework/Split-Rework |  | Split Rework | Lot | 完成 | 2022 |  | 杨金杰
|  | 139 |  |  | Cancel Rework | Lot | 完成 | 2022 | 取消返工(Rework State:InRework- | NotIn罗Re涛work
|  | 140 |  |  | Rework | Lot | 完成 | 2022 | 计划返工/adhoc 返工(Rework State | NotI罗nR涛ework- | InRework)
| Reposition | 141 | NPW Reposition |  |  | Lot | 未推进 | 2022 |  | 罗涛
| Reposition | 142 | Production Reposition |  |  | Lot | 未推进 | 2022 |  | 罗涛
| Reposition | 143 |  |  | Reposition Oper | Lot | 完成 | 2022 |  | 罗涛
| Reposition | 144 |  |  | Fetch Oper | Lot | 完成 | 2022 |  | 罗涛
| Reposition | 145 |  |  | Back Step | Lot | 完成 | 2022 |  | 罗涛
| Reposition | 146 | Reposition Rule |  | Reposition Rule | Lot | 完成 | 2022 | Reposition Rule | 罗涛
| Reposition | 147 | Skip Step |  | Skip Step | Lot | 完成 | 2022 |  | 罗涛
| Reposition | 148 | Special Reposition Step |  | Special Reposition Oper | Lot | 完成 | 2022 |  | 罗涛
| Simple Lot Transfer | 149 | Cancel Transfer Lot |  |  | Lot | 未推进 | 2022 |  | 罗涛
| imple Carrier Transf | r150 | Receive Transfer Carrier |  |  | Lot | 未推进 | 2022 |  | 罗涛
| imple Carrier Transf | r151 | Simple Transfer Carrier |  |  | Lot | 未推进 | 2022 |  | 罗涛
| Simple Lot Transfer | 152 | Receive Plan |  |  | Lot | 未推进 | 2022 |  | 罗涛
| Simple Lot Transfer | 153 | Receive Transfer Back Lot |  | Receive Transfer Lot Back | Lot | 完成 | 2022 |  | 罗涛
| Simple Lot Transfer | 154 | Receive Transfer Lot |  | Receive Transfer Lot | Lot | 完成 | 2022 |  | 罗涛
| Simple Lot Transfer | 155 | Simple Transfer Back Lot |  | Simple Transfer Lot Back | Lot | 完成 | 2022 |  | 罗涛
| Simple Lot Transfer | 156 | Simple Transfer Lot |  | Simple Transfer Lot | Lot | 完成 | 2022 |  | 罗涛
| Simple Lot Transfer | 157 | Transfer Mapping Configuration |  | Transfer Mapping | Lot | 完成 | 2022 |  | 罗涛
|  | 158 |  |  | Transfer Table Map | Lot | 完成 | 2022 |  | 罗涛
|  | 159 |  |  | Fab Attribute Mapping Config | Lot | 完成 | 2022 | From/To FAB 属性信息Mapping | 罗涛
|  | 160 |  |  | Fab Attribute Value Mapping | Lot | 完成 | 2022 | From/To FAB 属性的值信息Mapping | 罗涛
|  | 161 |  |  | View Transfer List | Lot | 完成 | 2022 |  | 罗涛
| Doma Management | 162 | Unprocessed DOMA Path View |  |  | Lot | 未推进 | 2022 |  | 罗涛
| Scrap/Terminate | 163 |  |  | Scrap Apply | Lot | 完成 | 2022 | 报废Lot | 罗涛
| Scrap/Terminate | 164 |  |  | Cancel Scrap Apply | Lot | 完成 | 2022 | 报废申请 | 罗涛
| Scrap/Terminate | 165 | UnScrap |  | UnScrap | Lot | 完成 | 2022 |  | 罗涛
| Scrap/Terminate | 166 | Scrap |  | Scrap | Lot | 完成 | 2022 |  | 罗涛
| Scrap/Terminate | 167 | Special UnTerminate Lot |  | Special Unterminate Lot | Lot | 完成 | 2022 | Special UnTerminate Lot | 罗涛
| Scrap/Terminate | 168 | Terminate Lot |  | Terminate Lot | Lot | 完成 | 2022 |  | 罗涛
| Scrap/Terminate | 169 | Terminate By Foup |  | Terminate Lot By Carrier | Lot | 完成 | 2022 |  | 罗涛
| Scrap/Terminate | 170 | Terminate Finish Lot |  | Terminate Finish Lot | Lot | 完成 | 2022 |  | 罗涛
| Scrap/Terminate | 171 | UnTerminate Lot |  | Unterminate Lot | Lot | 完成 | 2022 | UnTerminate Lot | 罗涛
| Pilot | 172 | View Pilot |  | View Pi Lot | Lot | 完成 | 2022 | 查看Pi Lot信息 | 罗涛
|  | 173 | YE Review Spec Configuration |  |  | Lot | 未推进 | 2022 |  | 罗涛
|  | 174 | YE Review Special Reposition |  |  | Lot | 未推进 | 2022 |  | 罗涛
|  | 175 | YE Select Wafers For Remeasure |  |  | Lot | 未推进 | 2022 |  | 罗涛
| MixRun | 176 | Mix Run |  |  | Lot | 未推进 | 2022 |  | 罗涛
| Pilot | 177 | Release Hold Pilot |  | Release Hold Pilot | Lot | 完成 | 2022 |  | 罗涛
| Pilot | 178 | Pilot Full Auto Information Setting |  |  | Lot | 未推进 | 2022 |  | 罗涛
| Pilot | 179 | Create Adhoc Pilot |  |  | Lot | 未推进 | 2022 |  | 罗涛
| Pilot | 180 | On Demand Pilot |  | On Demand Pilot Condition | Lot | 完成 | 2022 |  | 罗涛 |  |  | Modeler
| Pilot | 181 | Pilot Success Condition |  | Pilot Success Condition | Lot | 完成 | 2022 |  | 罗涛 |  |  | Modeler
| Pilot | 182 | Pilot Target Condition |  | Pilot Target Condition | Lot | 完成 | 2022 |  | 罗涛 |  |  | Modeler
| Pilot | 183 | Stop Pilot |  | Stop Pilot | Lot | 完成 | 2022 |  | 罗涛
| Q'Time Control | 184 | Cancel Q'Time Reservation |  |  | Lot | 未推进 | 2022 |  | 申克楠
| Q'Time Control | 185 | Turn Off Q'Time Speed Up |  |  | Lot | 未推进 | 2022 |  | 申克楠
|  | 186 |  |  | Q-Time List | Lot | 完成 | 2022 |  | 申克楠
|  | 187 |  |  | Q-Time Control | Lot | 完成 | 2022 |  | 申克楠
| Dedication | 188 |  |  |  | Lot | 完成 | 2022 |  | 童海潮
|  | 189 | Full Lot Report |  | Full Lot Report | Lot | 完成 | 2022 |  | 童海潮
|  | 190 |  |  | View Lot Info | Lot | 完成 | 2022 |  | 童海潮
|  | 191 |  |  | View Lot List | Lot | 完成 | 2022 | 按照TPFO别查询Lot List | 童海潮
|  | 192 |  |  | Data Collect Lot History | Lot | 完成 | 2022 |  | 童海潮
|  | 193 |  |  | View Lot History | Lot | 完成 | 2022 |  | 童海潮
|  | 194 | Add Comment |  | Add Comment | Lot | 完成 | 2022 | 增加comment | 罗涛
|  | 195 | T7 Code Query |  | View T7 Code | Lot | 完成 | 2022 |  | 罗涛
|  | 196 | Furnace Batch History |  | View Furnace Batch History | Lot | 完成 | 2022 |  | 罗涛
|  | 197 | View Component Information |  | View Component Info | Lot | 完成 | 2022 |  | 罗涛
|  | 198 | Wafer Chamber Tracking History |  | View Wafer Chamber Tracking Histor | Lot | 完成 | 2022 |  | 罗涛
|  | 199 | Wafer History |  | View Wafer History | Lot | 完成 | 2022 |  | 罗涛
|  | 200 | Wafer Slot History |  |  | Lot | 未推进 | 2022 |  | 罗涛
Lot Inventory |  | 201 | Bank In |  | Bank In | Inventory | 完成 | 2022 | 对选择的Lot进行移入Bank的操作(Ba | kStat罗e:O涛nFloor | >InBank),支 | 批量操作
| 202 | Bank Out |  | Bank Out | Inventory | 完成 | 2022 | 对选择的Lot进行移出Bank的操作(Ba | kStat罗e:I涛nBank- | OnFloor),支 | 批量操作
| 203 | Batch Bank In |  | Bank In | Inventory | 完成 | 2022 | 对选择的Lot进行移入Bank的操作(Ba | kStat罗e:O涛nFloor | >InBank),支 | 批量操作
| 204 | Check Cust Maintain |  |  | Inventory | 未推进 | 2022 |  | 罗涛
| 205 | Continue |  |  | Inventory | 未推进 | 2022 |  | 罗涛
| 206 | Move Bank |  | Move Bank | Inventory | 完成 | 2022 | 将Lot在不同Bank之间进行转移 | 罗涛
| 207 | Move To Location |  |  | Inventory | 未推进 | 2022 |  | 罗涛
| 208 | Query Bank Info |  | View Bank Info | Inventory | 完成 | 2022 |  | 罗涛
| 209 | Ship |  | Ship | Inventory | 完成 | 2022 |  | 罗涛
| 210 | UnShipByWafer |  | Unship | Inventory | 完成 | 2022 |  | 罗涛
| 211 |  |  | RSP Label | Inventory | 完成 | 2022 |  | 罗涛
| 212 |  |  | Lot Card | Inventory |  | 2022 | Input Lot Print and Mapping FOUP ID( | alidat罗io涛n条件 | 虑)
| 213 |  |  | Lot Label | Inventory |  | 2022 |  | 罗涛
| 214 |  |  | Reticle Label | Inventory | 完成 | 2022 |  | 罗涛
| 215 |  |  | FOSB Label | Inventory | 完成 | 2022 |  | 罗涛
Plan | 216 |  |  | Product Order | WIP | 完成 | 2022 |  | 罗涛
Plan | 217 |  |  | Work Order | WIP | 完成 | 2022 | 查询 Work Order, 可修改/删除/查询 | Comp罗lt涛e PM C | rd
Plan | 218 |  |  | View PO/WO History | WIP | 完成 | 2022 | 查询 PO/WO 的操作履历 | 罗涛
Plan | 219 | Create Production Lot |  | Create Lot | WIP | 完成 | 2022 |  | 罗涛
Plan | 220 | Create NPW Lot |  | Create NPW Lot | WIP | 完成 | 2022 | 生成 NPW Lot | 罗涛
Plan | 221 | Create Engineer Lot |  | Create Engineer Lot | WIP | 完成 | 2022 | 生成 Engineer Lot | 罗涛
Plan | 222 |  |  | View Create Lot List | WIP | 完成 | 2022 |  | 罗涛
Plan | 223 |  |  | View Transaction Raw Wafer List | WIP | 完成 | 2022 | 查询 ERP Raw Wafer 清单,需要手 | Crea罗te涛(ERP IF | 接口没有时
Plan | 224 | Query Raw Material Info |  | View Raw Wafer List | WIP | 待确认 | 2022 | 查看当前库存,Confirm 时累加,Cre | te So罗ur涛ce Ven | or Lot时消耗
Plan | 225 |  |  | FOSB Generate | WIP | 完成 | 2022 |  | 罗涛
Plan | 226 | Create Source Lot |  | Create Source Vendor Lot | WIP | 完成 | 2022 | 基于 Raw Wafer 进行 Source Vendor L | t 生成罗(涛FOSB | 配)
Plan | 227 | Query Source Lot Info |  | View Source Lot List | WIP | 完成 | 2022 |  | 罗涛
Plan | 228 |  |  | FOSB Generate Scan | WIP | 完成 | 2022 |  | 罗涛
Plan | 229 |  |  | Start Lot Reserve | WIP | 完成 | 2022 |  | 罗涛
Plan | 230 | Start Lot |  | Start Lot | WIP | 完成 | 2022 | 将Source Vendor Lot. Lot ID, Carrier ID | 者匹罗配涛生成L | t/wafer的功 | ,支持Sort Loca
Plan | 231 |  |  | Insert T7 Code | WIP | 完成 | 2022 |  | 罗涛
Plan | 232 |  |  | Start Lot Auto | WIP | 完成 | 2022 |  | 罗涛
Plan | 233 |  |  | Wafer Start Reserve | WIP | 完成 | 2022 | Start Lot的自动模式,支持Sort Remo | e + 手罗动涛Load | 取RFID,Sort | 动读取T7 Co | e 保存
Plan | 234 |  |  | View Start Lot | WIP | 完成 | 2022 |  | 罗涛
Plan | 235 |  |  | Skip Started Lot | WIP | 完成 | 2022 |  | 罗涛
| 236 | Confirm Raw Wafers |  | View Raw Wafer List | WIP | 完成 | 2022 | 查看当前库存,Confirm 时累加,Cre | te So罗ur涛ce Ven | or Lot时消耗
| 237 | Create Glass Lot |  |  | WIP | 未推进 | 2022 |  | 罗涛
| 238 | Modify/Cancel Create Lot |  | View Create Lot List | WIP | 完成 | 2022 |  | 罗涛
N2Purge | 239 | Cancel N2Purge |  |  | WIP | 未推进 | 2023 1Q |  | 申克楠
N2Purge | 240 | End N2Purge |  |  | WIP | 未推进 | 2023 1Q |  | 申克楠
N2Purge | 241 | Load Port N2 Purge Flag Maintain |  |  | WIP | 未推进 | 2023 1Q |  | 申克楠
N2Purge | 242 | Start N2Purge |  |  | WIP | 未推进 | 2023 1Q |  | 申克楠
Run Card | 243 | Change RunCard Status |  | View/Change Run Card State | WIP | 完成 | 2022 |  | 申克楠
Run Card | 244 | Create Recover RunCard |  | Recover Run Card | WIP | 完成 | 2022 |  | 申克楠
Run Card | 245 | Create Split Run Card |  | Split Run Card | WIP | 完成 | 2022 |  | 申克楠
Run Card | 246 | Get RunCard Information |  |  | WIP | 未推进 | 2022 |  | 申克楠
Run Card | 247 |  |  | Release Split RunCard | WIP | 完成 | 2022
Run Card | 248 | Merge RunCard Lot |  |  | WIP | 待确认 | 2022 |  | 申克楠
PPID Control | 249 | Edit PPID Comment |  |  | WIP | 待确认 | 2022 |  | 李彬
PPID Control | 250 | Hold/Release LayoutRecipe |  |  | WIP | 完成 | 2022 |  | 李彬
PPID Control | 251 | Hold/Release LayoutRecipe History |  |  | WIP | 完成 | 2022 |  | 李彬
PPID Control | 252 | Hold/Release PPID |  |  | WIP | 完成 | 2022 |  | 李彬
PPID Control | 253 | Hold/Release PPID History |  |  | WIP | 完成 | 2022 |  | 李彬
PPID Control | 254 | PPID Resolution History |  |  | WIP | 完成 | 2022 |  | 李彬
PPID Control | 255 | Release PPID Constraint |  |  | WIP | 完成 | 2022 |  | 李彬
PPID Control | 256 | Release PPID Constraint History |  |  | WIP | 完成 | 2022 |  | 李彬

## Page5
| PPID Control | 257 |  |  | Machine Recipe Management | WIP | 完成 | 2022 |  | 李彬
| PPID Control | 258 |  |  | Machine Recipe Management Histor | WIP | 完成 | 2022 |  | 李彬
| PPID Control | 259 |  |  | Machine Recipe Constraint Release | WIP | 完成 | 2022 |  | 李彬
| PPID Control | 260 |  |  | Machine Recipe Constraint Release | istoryWIP | 完成 | 2022 |  | 李彬
| Bonding | 261 | Bonding Lot History |  |  | WIP | 待确认 | 2022 |  | 申克楠
| Bonding | 262 | Bonded Lot |  |  | WIP | 待确认 | 2022 |  | 申克楠
| Bonding | 263 | Bonding Lot Skip |  |  | WIP | 待确认 | 2022 |  | 申克楠
| Bonding | 264 | Bonding Lot Type Mapping |  |  | WIP | 待确认 | 2022 |  | 申克楠
| Bonding | 265 | Bonding Product Mapping |  |  | WIP | 待确认 | 2022 |  | 申克楠
| Bonding | 266 | Bonding Step Mapping |  |  | WIP | 待确认 | 2022 |  | 申克楠
| Bonding | 267 | Glass Lot Information |  |  | WIP | 待确认 | 2022 |  | 申克楠
| Bonding | 268 | Pair Port Setting |  |  | WIP | 待确认 | 2022 |  | 申克楠
| Bonding | 269 | Pair Port Setting |  |  | WIP | 待确认 | 2022 |  | 申克楠
| Bonding | 270 | Pre Bonding |  |  | WIP | 待确认 | 2022 |  | 申克楠
| Cancel Job | 271 | Cancel Sorter Reservation |  | Cancel Prepared Lot | WIP | 完成 | 2022 | 取消Prepare Lot | 申克楠
| Cancel Job | 272 | Cancel Job In |  | Cancel Track In | WIP | 完成 | 2022 |  | 申克楠
| Non-Sorter Job | 273 | Job Out |  | Track Out | WIP | 完成 | 2022 | Track Out UI | 申克楠
| Non-Sorter Job | 274 | Job In |  | Track In | WIP | 完成 | 2022 | Track In 作业 | 申克楠
| Non-Sorter Job | 275 | Job Out |  | Track Out | WIP | 完成 | 2022 | Track Out UI | 申克楠
| Non-Sorter Job | 276 | Job Preparation |  | Prepare Lot | WIP | 完成 | 2022 | Lot 预约 | 申克楠
| Cancel Job | 277 | Cancel Job Preparation |  | Cancel Prepare Lot | WIP | 完成 | 2022 |  | 申克楠
|  | 278 | Lot Queue Adjustment |  | Lot Queue Adjustment | WIP | 开发中 | 2022 |  | 申克楠
|  | 279 | Lot Queue Reservation |  | Lot Queue Reservation | WIP | 开发中 | 2022 |  | 申克楠
|  | 280 | Query FOUP-Lot Reservation |  |  | WIP | 待确认 | 2022 |  | 申克楠
|  | 281 |  |  | Reserve Machine In Current Step | WIP | 完成 | 2022 | Preprae Lot前手动将Lot绑定Machine | 申克楠
|  | 282 |  |  | Cancel Reserve Machine In Current S | epWIP | 完成 | 2022 | 取消Lot对Machine 的绑定 | 申克楠
|  | 283 |  |  | Restriction Machine | WIP | 完成 | 2022 |  | 申克楠
|  | 284 |  |  | View Cj And Pj | WIP | 完成 | 2022 |  | 申克楠
|  | 285 |  |  | Furnace Prepare Lot | WIP | 完成 | 2022 |  | 申克楠
|  | 286 |  |  | Create Batch | WIP | 完成 | 2022 | 1) Lot别Position 调整;2)Recipe Res | luti申on克; 3)楠Bat | h ID 生成
|  | 287 |  |  | Cancel Create Batch | WIP | 完成 | 2022 | Batch ID 生成取消 | 申克楠
| WaferSelectionRule | 288 | Setting By EDC Plan |  | 设置EDC Plan 的Wafer Selection Rul | WIP | 未推进 | 2022 |  | 申克楠/李彬
| WaferSelectionRule | 289 | Setting By EQP |  |  | WIP | 未推进 | 2022 |  | 申克楠
|  | 290 | Setup Runtime Eqp State |  |  | WIP | 未推进 | 2022 |  | 杨金杰
|  | 291 | R2R Modeling Configuration |  |  | WIP | 未推进 | 2022 |  | 申克楠
|  | 292 | Sorter Capability Set By Carrier Type |  |  | WIP | 未推进 | 2023 1Q |  | 申克楠
|  | 293 | Sorter Capability Set By Wafer Kind |  |  | WIP | 未推进 | 2023 1Q |  | 申克楠
| Sorter Job | 294 | Sorter Job In |  | Sorter Track In | WIP | 完成 | 2022 | Sorter设备已经预约的lot 进行Track In | 处理申克楠
| Sorter Job | 295 | Sorter Job Out |  | Sorter Track Out | WIP | 完成 | 2022 | Sorter设备Track Out | 申克楠
| Sorter Job | 296 | Sorter Job Preparation |  | Sorter Job Prepare | WIP | 完成 | 2022 |  | 申克楠
|  | 297 |  |  | Sorter Cancel Job Prepare | WIP | 完成 | 2022 |  | 申克楠
|  | 298 |  |  | Sorter Cancel Track In | WIP | 完成 | 2022 |  | 申克楠
|  | 299 |  |  | Sorter Job Cancel | WIP | 完成 | 2022 |  | 申克楠
| Data Collection | 302 | Adhoc Data Collection |  |  | WIP | 待确认 | 2023 1Q | 对机台Lot的数据收集。 | 李彬 | 苏州 | 顾圣培 |  |  | 未进行
| Data Collection | 303 | Cancel ReSend To Spc |  |  | WIP | 未推进 | 2022 | 取消重新发送数据到SPC | 李彬 | 苏州 |  |  |  | 未进行
| Data Collection | 304 | Lot Data Collection |  | Data Collect Lot | WIP | 完成 | 2022 | Data Collect Lot | 李彬 | 苏州 |  |  |  | 进行中
| Data Collection | 305 | HoldPPID Action Setting |  | Data Collect Spec | WIP | 完成 | 2022 | OOS/OOC/DataMissing Hold Machine | ecipe李 的彬Action | 配置苏州 |  |  |  | 完成 | Modeler
| Data Collection | 306 | Non-Lot Data Collection |  |  | WIP | 待确认 | 2022 | 对Machine进行的数据收集 | 李彬 | 苏州 |  |  |  | 未进行
| Data Collection | 307 | ReSend To Spc |  |  | WIP | 未推进 | 2022 | 重新发送EDC 数据到SPC | 李彬 | 苏州 |  |  |  | 未进行
| Data Collection | 308 | YE SpecID Bincode Map |  |  | WIP | 未推进 | 2022 | 绑定EDC Spec 到 process Operation | 李彬 | 苏州 |  |  |  | 完成
| Data Collection | 309 | YE SpecID Bincode Map History |  |  | WIP | 未推进 | 2022 | 绑定EDC Spec 到 process Operation历 | 记录李查彬询页 | 苏州 |  |  |  | 未进行
| Data Collection | 310 | View Non Lot Dcoll Info |  |  | WIP | 待确认 | 2022 | 查询Non-Lot 数据收集页面 | 李彬 | 苏州 |  |  |  | 未进行
CSN |  | 311 | Constraint |  | Constraint Setting | CSN | 完成 | 2022 |  | 申克楠 | 北京 | 鲁绍根 | 2022/8/30 | 2022/9/10 | 进行中 | Modeler
|  | 312 | Golden Tool |  | Golden Tool Setting | CSN | 完成 | 2022 |  | 申克楠 | 北京 | 鲁绍根 | 2022/8/30 | 2022/9/10 | 完成 | Modeler
|  | 313 | Mfg Dispatch |  | MFG Dispatch Setting | CSN | 完成 | 2022 |  | 申克楠 | 北京 | 鲁绍根 | 2022/8/30 | 2022/9/10 | 进行中 | Modeler
|  | 314 | Parts Life Time Control |  |  | CSN | 未推进 | 2022 |  | 申克楠
|  | 315 | CSN PPID Constraint |  |  | CSN | 未推进 | 2022 |  | 李彬
|  | 316 | Restrict Duration Recipe |  |  | CSN | 未推进 | 2022 |  | 申克楠
Test Wafer | NPW Grade | 317 | Downgrade Wafer Quantity Limit |  |  | Test Wafer | 未推进 | 2022 |  | 童海潮
|  | 318 |  |  | Downgrade | Test Wafer | 完成 | 2022 |  | 童海潮
|  | 319 |  |  | Modify Wafer Information | Test Wafer | 完成 | 2022 |  | 童海潮
|  | 320 | Break Furnace Batch |  | Break Batch | Test Wafer | 完成 | 2022 |  | 童海潮
|  | 321 | Cancel Dummy In |  |  | Test Wafer | 未推进 | 2022 |  | 童海潮
|  | 322 | Cancel Reserve Dummy |  |  | Test Wafer | 未推进 | 2022 |  | 童海潮
|  | 323 |  |  | Downgrade Setting | Test Wafer | 完成 | 2022 |  | 童海潮
|  | 324 |  |  | NPW Inventory Setting | Test Wafer | 完成 | 2022 |  | 童海潮
|  | 325 | Configure Control ID |  | Furnace Monitor/Monitor/Dummy/S | asToens/tP WMa Sfear s | n Con完tro成l Rule | ettin2g022 |  | 童海潮
|  | 326 |  |  | PM Season Group | Test Wafer | 完成 | 2022 |  | 童海潮
|  | 327 | Configure Wafer Stock Level |  |  | Test Wafer | 未推进 | 2022 |  | 童海潮
|  | 328 | Dummy In |  | Dummy Load | Test Wafer | 完成 | 2022 |  | 童海潮
|  | 329 | Dummy Out |  | Dummy UnLoad | Test Wafer | 完成 | 2022 |  | 童海潮
|  | 330 | Furance Batch Waiting In Tool |  | View Furnace Wait Batch | Test Wafer | 完成 | 2022 |  | 童海潮
|  | 331 | InUse End |  | In Use End(Merge) | Test Wafer | 完成 | 2022 |  | 童海潮
|  | 332 |  |  | View In Use Start Lot | Test Wafer |  | 2022 |  | 童海潮
|  | 333 | Inuse Start With Split |  | In Use Start(Split) | Test Wafer | 完成 | 2022 |  | 童海潮
|  | 334 | Query Monitor Lot |  |  | Test Wafer | 未推进 | 2022 |  | 童海潮
|  | 335 | Reclaim End |  |  | Test Wafer | 未推进 | 2022 |  | 童海潮
|  | 336 | Re_Create Monitor Lot |  |  | Test Wafer | 未推进 | 2022 |  | 童海潮
|  | 337 | Recycle End |  | View Recycle End Lot List | Test Wafer | 完成 | 2022 |  | 童海潮
|  | 338 | Reserve Dummy |  |  | Test Wafer | 未推进 | 2022 |  | 童海潮
|  | 339 | Set Furnace batch boat information |  | Furnace Batch Boat Info Setting | WIP | 完成 | 2022 |  | 童海潮
|  | 340 | Reset Equipment Control State |  | View Machine Control Status | Test Wafer | 完成 | 2022 |  | 童海潮
|  | 341 |  |  | View NPW Inventory Status | Test Wafer | 完成 | 2022 |  | 童海潮
|  | 342 | View Equipment Control Status |  | View Machine Control Status | Test Wafer | 完成 | 2022 |  | 童海潮
|  | 343 | View Equipment Dummy Lot History |  | View Machine Dummy Lot History | Test Wafer | 完成 | 2022 |  | 童海潮
|  | 344 | View Equipment Dummy Status |  | View Machine Dummy Information | Test Wafer | 完成 | 2022 |  | 童海潮
|  | 345 | View Equipment Dummy Wafer History |  | View Machine Dummy Wafer History | Test Wafer | 完成 | 2022 |  | 童海潮
|  | 346 |  |  | View Monitor Status | Test Wafer | 完成 | 2022 |  | 童海潮
|  | 347 |  |  | View NPW PFO | Test Wafer | 完成 | 2022 |  | 童海潮
|  | 348 | View Monitor Lot History |  | View Monitor Lot History | Test Wafer | 完成 | 2022 |  | 童海潮
|  | 349 | View Season Lot History |  | View Season History | Test Wafer | 完成 | 2022 |  | 童海潮
OCAP |  | 350 | Complete Double Confirm |  |  | OCAP | 未推进 | 2023 1Q |  | 李彬 |  |  |  |  | 未进行
| 351 | QUERY UI |  |  | OCAP | 完成 | 2023 1Q | 查询正在执行的OCAP逻辑 | 李彬 |  |  |  |  | 完成
Activity | 352 | Change Location |  |  | PCMS | 待确认
Activity | 353 | Complete Use for RunCard |  |  | PCMS | 待确认
Activity | 354 | EE Hold Card |  |  | PCMS | 待确认
Activity | 355 | EE Validation |  |  | PCMS | 待确认
Configuration | 356 | Equipment Capability With Probe Card Group |  |  | PCMS | 待确认
Activity | 357 | Lend Out |  |  | PCMS | 待确认
Activity | 358 | MFG Receive |  |  | PCMS | 待确认
Run Time | 359 | Mounting Of Probe Card |  |  | PCMS | 待确认
Configuration | 360 | Probe Card Group Maintenance |  |  | PCMS | 待确认
Configuration | 361 | Probe Card Group Maintenance |  |  | PCMS | 待确认
Configuration | 362 | Probe Card Group Maintenance |  |  | PCMS | 待确认
Configuration | 363 | Probe Card Maintenance |  |  | PCMS | 待确认
Configuration | 364 | Probe Card Maintenance |  |  | PCMS | 待确认
Configuration | 365 | Probe Card Maintenance |  |  | PCMS | 待确认
Configuration | 366 | Probe Card Maintenance |  |  | PCMS | 待确认
Configuration | 367 | Probe Card Maintenance |  |  | PCMS | 待确认
Activity | 368 | PE Hold Card |  |  | PCMS | 待确认
Activity | 369 | PE Validation |  |  | PCMS | 待确认
Configuration | 370 | Probe Card Group Maintenance |  |  | PCMS | 待确认
Activity | 371 | Probe Card History |  |  | PCMS | 待确认
Configuration | 372 | Probe Card Maintenance |  |  | PCMS | 待确认
Configuration | 373 | RCP Probe Card Group Mapping |  |  | PCMS | 待确认
Configuration | 374 | RCP Probe Card Group Mapping |  |  | PCMS | 待确认
Configuration | 375 | RCP Probe Card Group Mapping |  |  | PCMS | 待确认
Configuration | 376 | RCP Probe Card Group Mapping |  |  | PCMS | 待确认
Configuration | 377 | RCP Probe Card Group Mapping |  |  | PCMS | 待确认
Activity | 378 | Release To MFG |  |  | PCMS | 待确认
Configuration | 379 | RCP Probe Card Group Mapping |  |  | PCMS | 待确认
Activity | 380 | Release for RunCard |  |  | PCMS | 待确认
Activity | 381 | Remove From Inventory |  |  | PCMS | 待确认
Activity | 382 | Return From Repair |  |  | PCMS | 待确认
Activity | 383 | Return To Inventory |  |  | PCMS | 待确认
Activity | 384 | Return To PE |  |  | PCMS | 待确认
Activity | 385 | Scrap |  | Scrap | Lot | 待确认
Configuration | 386 | Location Maintenance |  |  | PCMS | 待确认
Run Time | 387 | UnMounting Of Probe Card |  |  | PCMS | 待确认
Activity | 388 | UnScrap |  | UnScrap | Lot | 待确认

## Page6
| Activity | 389 | Send To Vendor Repair |  | PCMS | 待确认
PRMS | MainGUI | 390 | Manage Resist Equipment Alarm |  | PRMS | 未推进 | 2023 2Q
| Configuration | 391 | PR Batch Assignment And Qualification |  | PRMS | 未推进 | 2023 2Q
| Activity | 392 | Change Location |  | PRMS | 未推进 | 2023 2Q
| Configuration | 393 | Location Maintenance |  | PRMS | 未推进 | 2023 2Q
| Activity | 394 | Photo Resist Consumable Events |  | PRMS | 未推进 | 2023 2Q
| Configuration | 395 | Photo Resist Equipment Maintenance |  | PRMS | 未推进 | 2023 2Q
| Activity | 396 | Photo Resist History |  | PRMS | 未推进 | 2023 2Q
| Configuration | 397 | Photo Resist Location Maintenance |  | PRMS | 未推进 | 2023 2Q
| Configuration | 398 | Photo Resist Part Maintenance |  | PRMS | 未推进 | 2023 2Q
| Configuration | 399 | PR Recipe |  | PRMS | 未推进 | 2023 2Q
| Activity | 400 | PR Recipe History |  | PRMS | 未推进 | 2023 2Q
| Configuration | 401 | Resist Consumables |  | PRMS | 未推进 | 2023 2Q
PTMS | Create Part | 402 | Batch Create Part |  | PTMS | 未推进 | 2023 2Q
| Part Main GUI | 403 | Batch Create Part Master |  | PTMS | 未推进 | 2023 2Q
| Create Part | 404 | Create Part |  | PTMS | 未推进 | 2023 2Q
| Configuration | 405 | Cost Center |  | PTMS | 未推进 | 2023 2Q
| Part Group Maintain | 406 | Modify Part Group Relationship |  | PTMS | 未推进 | 2023 2Q
| Configuration | 407 | Part Cycle Limit |  | PTMS | 未推进 | 2023 2Q
| MainGUI | 408 | Part Main Screen View |  | PTMS | 未推进 | 2023 2Q
| Part Main GUI | 409 | Part Master MainGUI |  | PTMS | 未推进 | 2023 2Q
| Replace Parts | 410 | Replace Parts |  | PTMS | 未推进 | 2023 2Q
| Part Group Maintain | 411 | Query Part Group Relationship |  | PTMS | 未推进 | 2023 2Q
RTD |  | 412 | Maintain Mark Lot |  | RTD | 未推进 | 2023 2Q
Reticle | Maintain | 413 | Batch Reticle Properties |  | Reticle | 未推进 | 2022 |  | 杨金杰
| Create And Delete | 414 | Create Reticle | Create Reticle | Reticle | 完成 | 2022 |  | 杨金杰
| Reticle Activity | 415 | Scan In | Reticle Scan In | Reticle | 完成 | 2022 |  | 杨金杰
| Reticle Activity | 416 | Bank In | Bank In | Reticle | 完成 | 2022 |  | 杨金杰
| Reticle Activity | 417 | Bank Out | Reticle Bank Out | Reticle | 完成 | 2022 |  | 杨金杰
| Maintain | 418 | Batch IRIS Wafer Count |  | Reticle | 未推进 | 2022 |  | 杨金杰
| Maintain | 419 | Batch IRIS Wafer Count Import And Export |  | Reticle | 未推进 | 2022 |  | 杨金杰
| Maintain | 420 | Batch Pod Properties |  | Reticle | 未推进 | 2022 |  | 杨金杰
| Maintain | 421 | Batch Starlight |  | Reticle | 未推进 | 2022 |  | 杨金杰
| Maintain | 422 | Batch Wafer Count |  | Reticle | 未推进 | 2022 |  | 杨金杰
| Maintain | 423 | Batch XCDA Qtime |  | Reticle | 未推进 | 2022 |  | 杨金杰
| Maintain | 424 | Batch XCDA Qtime Import And Export |  | Reticle | 未推进 | 2022 |  | 杨金杰
| Reticle Activity | 425 | Change Location |  | Reticle | 未推进 | 2022 |  | 杨金杰
| Reticle Activity | 426 | Clean | View Reticle List | Reticle | 完成 | 2022 |  | 杨金杰
| Reticle Activity | 427 | Clean Complete | Reticle Clean Complete | Reticle | 完成 | 2022 |  | 杨金杰
| Maintain | 428 | Compatible Condition |  | Reticle | 未推进 | 2022 |  | 杨金杰
| Reticle Activity | 429 | Confirm Mask Quality | Quality Check | Reticle | 完成 | 2022 |  | 杨金杰
| Reticle Activity | 430 | Reticle Data Collection |  | Reticle | 未推进 | 2023 1Q | 对Reticle的数据收集 | 李彬 | 苏州
| Create And Delete | 431 | Delete Reticle |  | Reticle | 未推进 | 2022 |  | 杨金杰
| Reticle Activity | 432 | Hold Reticle | View Reticle List | Reticle | 完成 | 2022 |  | 杨金杰
| Reticle Activity | 433 | Inspection In |  | Reticle | 待确认 | 2022 |  | 杨金杰
| Reticle Activity | 434 | Inspection Out |  | Reticle | 待确认 | 2022 |  | 杨金杰
| Maintain | 435 | IRIS Wafer Count |  | Reticle | 未推进 | 2022 |  | 杨金杰
| Kit And Unkit | 436 | Kit And UnKit | View Pod List | Reticle | 完成 | 2022 |  | 杨金杰
| Reticle Activity | 437 | Load Reticle |  | Reticle | 待确认 | 2022 |  | 杨金杰
|  | 438 | Reticle Main Screen | View Reticle List | Reticle | 完成 | 2022 |  | 杨金杰
| Maintain | 439 | Maintain Equipment Type |  | Reticle | 未推进 | 2022 |  | 杨金杰
| Maintain | 440 | Maintain Reticle Location |  | Reticle | 未推进 | 2022 |  | 杨金杰
| Maintain | 441 | Maintain Reticle LocationType |  | Reticle | 未推进 | 2022 |  | 杨金杰
| Maintain | 442 | Maintain Reticle Grade |  | Reticle | 未推进 | 2022 |  | 杨金杰
| Maintain | 443 | Mask Clean |  | Reticle | 未推进 | 2022 |  | 杨金杰
| Reticle Activity | 444 | Modify Attribute |  | Reticle | 未推进 | 2022 |  | 杨金杰
| Reticle Activity | 445 | Offline Retrieve Reticle |  | Reticle | 未推进 | 2022 |  | 杨金杰
| Pod Activity | 446 | Change Location |  | Reticle | 未推进 | 2022 |  | 杨金杰
| Pod Activity | 447 | Change State | View Pod List | Reticle | 完成 | 2022 |  | 杨金杰
| Pod Activity | 448 | Clean | View Pod List | Reticle | 完成 | 2022 |  | 杨金杰
| Pod Activity | 449 | Clean Complete | Pod Clean Complete | Reticle | 完成 | 2022 |  | 杨金杰
| Pod Activity | 450 | Confirm Quality |  | Reticle | 未推进 | 2022 |  | 杨金杰
| Pod Activity | 451 | Exchange | Pod Exchange | Reticle | 完成 | 2022 |  | 杨金杰
| Pod Activity | 452 | Hold | View Pod List | Reticle | 完成 | 2022 |  | 杨金杰
|  | 453 | Pod Main Screen | View Pod List | Reticle | 完成 | 2022 |  | 杨金杰
| Create And Delete | 454 | Pod Mgt |  | Reticle | 未推进 | 2022 |  | 杨金杰
| Pod Activity | 455 | Release | Pod Release | Reticle | 完成 | 2022 |  | 杨金杰
| Pod Activity | 456 | Scrap | View Pod List | Reticle | 完成 | 2022 |  | 杨金杰
| Pod Activity | 457 | UnScrap | Pod Cancel Scrap | Reticle | 完成 | 2022 |  | 杨金杰
| Reticle Activity | 458 | Release Reticle | Reticle Release | Reticle | 完成 | 2022 |  | 杨金杰
| Maintain | 459 | Remount And Clean Count |  | Reticle | 未推进 | 2022 |  | 杨金杰
| Reticle Activity | 460 | Request Inspection | Inspection Request | Reticle | 待确认 | 2022 |  | 杨金杰
| Reticle Activity | 461 | Request Scan | View Reticle List | Reticle | 完成 | 2022 |  | 杨金杰
| Pod Activity | 462 | Reserve POD |  | Reticle | 未推进 | 2022 |  | 杨金杰
|  | 463 | History | Material History | Reticle | 完成 | 2022 |  | 杨金杰
| Reticle Activity | 464 | Cancel Scan |  | Reticle | 未推进 | 2022 |  | 杨金杰
| Reticle Activity | 465 | Reticle Scrap | View Reticle List | Reticle | 完成 | 2022 |  | 杨金杰
| Reticle Activity | 466 | Return To Customer |  | Reticle | 未推进 | 2022 |  | 杨金杰
| Reticle Activity | 467 | Scan Complete | Reticle Scan Out | Reticle | 完成 | 2022 |  | 杨金杰
| Maintain | 468 | Starlight | View Reticle List | Reticle | 完成 | 2022 | Inspection(Scan)周期 | 杨金杰
| Reticle Activity | 469 | Terminate |  | Reticle | 未推进 | 2022 |  | 杨金杰
| Reticle Activity | 470 | Unload Reticle | Reticle Unload | Reticle | 待确认 | 2022 |  | 杨金杰
| Reticle Activity | 471 | Reticle UnScrap | Cancel Scrap Reticle | Reticle | 完成 | 2022 |  | 杨金杰
|  |  |  | View Reticle List | Reticle | 完成 | 2022 | Reticle Transfer In | 杨金杰
|  |  |  | View Reticle List | Reticle | 完成 | 2022 | Reticle Transfer Out | 杨金杰
| Maintain | 472 | Wafer Count | View Reticle List | Reticle | 完成 | 2022 | Reticle Wafer Count | 杨金杰
| Reticle Activity | 473 | Batch XCDA Purge Time Remove |  | Reticle | 未推进 | 2022 |  | 杨金杰
| Maintain | 474 | XCDA Qtime | View Reticle List | Reticle | 完成 | 2022 | XCDA Time.Purge Time Spec | 杨金杰
| Reticle Activity | 475 | Batch XCDA Qtime Remove |  | Reticle | 未推进 | 2022 |  | 杨金杰
Sampling |  | 476 |  | Set Scan Lot | Sampling | 完成 | 2022 |  | 申克楠 |  | Modeler
|  | 477 |  | Set Sampling Skip Lot | Sampling | 完成 | 2022 |  | 申克楠 |  | Modeler
|  | 478 |  | Sampling Reserve Lot List | Sampling | 完成 | 2022 |  | 申克楠 |  | Modeler
|  | 479 |  | Sampling Skip Lot List | Sampling | 完成 | 2022 |  | 申克楠 |  | Modeler
|  | 480 |  | Lot Sampling Run Time History | Sampling | 完成 | 2022 |  | 申克楠 |  | Modeler
|  | 481 |  | Wafer Selection Rule | Sampling | 完成
|  | 482 |  | Machine Sampling | Sampling | 完成
|  | 483 |  | Pre-Post Sampling | Sampling | 完成
|  | 484 |  | Layer Change Sampling | Sampling | 完成
|  | 485 | Step Sampling |  | Sampling | 未推进 | 2022 |  | 申克楠 |  | Modeler
|  | 486 | Default Sampling |  | Sampling | 待确认 | 2022 |  | 申克楠 |  | Modeler
|  | 487 | Default Sampling |  | Sampling | 待确认 | 2022 |  | 申克楠 |  | Modeler
|  | 488 | Furnace Monitor Sampling | FML Sampling | Sampling | 完成 | 2022 |  | 童海潮 |  | Modeler
|  | 489 | YE Step Sampling | YE Step Sampling | Sampling | 测试中 | 2022 |  | 申克楠 |  | Modeler
|  | 490 | Modify Key Lot Flag |  | Sampling | 待确认 | 2022 |  | 申克楠 |  | Modeler
|  | 491 | Lot Sampling Runtime History | Lot Sampling Run Time History | Sampling | 测试中 | 2022 |  | 申克楠 |  | Modeler
|  | 492 | Smart Sampling Special Flag |  | Sampling | 待确认 | 2022 |  | 申克楠 |  | Modeler
|  | 493 | Smart Sampling Key Equipment |  | Sampling | 待确认 | 2022 |  | 申克楠 |  | Modeler
|  | 494 | Smart Sampling Key Step Association |  | Sampling | 待确认 | 2022 |  | 申克楠 |  | Modeler
| Sampling History | 495 | Smart Sampling MFG Skip History |  | Sampling | 待确认 | 2022 |  | 申克楠 |  | Modeler
|  | 496 | YE Key Equipment |  | Sampling | 待确认 | 2022 |  | 申克楠 |  | Modeler
|  | 497 | YE Key Step Association |  | Sampling | 待确认 | 2022 |  | 申克楠 |  | Modeler
|  | 498 | YE Step By Flow |  | Sampling | 待确认 | 2022 |  | 申克楠 |  | Modeler
|  | 499 | YE Step By Lot |  | Sampling | 待确认 | 2022 |  | 申克楠 |  | Modeler
| Sampling History | 500 | YE Step Sampling History |  | Sampling | 待确认 | 2022 |  | 申克楠 |  | Modeler
Transportation |  | 501 | Cancel Reticle Transportation |  | Transportation | 未推进 | 2023 2Q
| 502 | Cancel Transportation |  | Transportation | 未推进 | 2023 2Q
MCS Control | 503 | Reticle Transportation Request |  | Transportation | 未推进 | 2023 2Q
MCS Control | 504 | Reticle Sync Stocker |  | Transportation | 未推进 | 2023 2Q
| 505 | MCS Inventory Info |  | Transportation | 未推进 | 2023 2Q
| 506 | Sync Reticle Stocker |  | Transportation | 未推进 | 2023 2Q
| 507 | Transportation Reticle Request |  | Transportation | 未推进 | 2023 2Q
| 508 | View Reticle Stocker |  | Transportation | 未推进 | 2023 2Q
| 509 | Sync Carrier Info |  | Transportation | 未推进 | 2023 2Q
| 510 | Transportation Request |  | Transportation | 未推进 | 2023 2Q
| 511 | Transportation Recovery |  | Transportation | 未推进 | 2023 2Q
| 512 | WAT Hold Information |  | WAT | 未推进 | 2023 2Q
| 513 | WAT Result Information |  | WAT | 未推进 | 2023 2Q
Wafer Test | 514 | Final InkMap Prod Setting |  | WAT | 未推进 | 2023 2Q
Wafer Test | 515 | Final InkMap Prod Setting |  | WAT | 未推进 | 2023 2Q
Wafer Test | 516 | Wafer Test Information |  | WAT | 未推进 | 2023 2Q

## Page7
Wafer Test | 517 | Wafer Test Information | WAT | 未推进 | 2023 2Q
Wafer Test | 518 | Wafer Test Result History | WAT | 未推进 | 2023 2Q
Wafer Test | 519 | WT Hold Information | WAT | 未推进 | 2023 2Q
Wafer Test | 520 | WT Product Yield Setting | WAT | 未推进 | 2023 2Q
Wafer Test | 521 | WT Product Yield Setting | WAT | 未推进 | 2023 2Q
Wafer Test | 522 | WT Retest Recipe Setting | WAT | 未推进 | 2023 2Q
Wafer Test | 523 | WT Test Step Recipe Configuration | WAT | 未推进 | 2023 2Q

## Page8
一级名字 | 二级名字 | 三级名字
WIP | Plan | Product Order
WIP | Plan | Work Order
WIP | Plan | View PO/WO History
WIP | Plan | Create Lot
WIP | Plan | Create NPW Lot
WIP | Plan | Create Engineer Lot
WIP | Plan | View Create Lot List
WIP | Source Lot | View Transaction Raw Wafer List
WIP | Source Lot | View Raw Wafer List
WIP | Source Lot | FOSB Generate
WIP | Source Lot | Create Source Vendor Lot
WIP | Source Lot | View Source Lot List
WIP | Source Lot | FOSB Generate Scan
WIP | Wafer Start | Start Lot Reserve
WIP | Wafer Start | Start Lot
WIP | Wafer Start | Insert T7 Code
WIP | Wafer Start | Start Lot Auto
WIP | Wafer Start | Wafer Start Reserve
WIP | Wafer Start | View Start Lot
WIP | Wafer Start | Skip Started Lot
WIP | Tracking | Prepare Lot
WIP | Tracking | Prepare Lot
WIP | Tracking | Cancel Prepared Lot
WIP | Tracking | Track In
WIP | Tracking | Cancel Track In
WIP | Tracking | Track Out
WIP | Tracking | Reserve Machine In Current Step
WIP | Tracking | Cancel Reserve Machine In Current Step
WIP | Tracking | Restriction Machine
WIP | Tracking | View Cj And Pj
WIP | Tracking | Test
WIP | Tracking | Lot Queue
WIP | Tracking | Furnace Prepare Lot
WIP | Batch | Cancel Create Batch
WIP | Batch | Break Batch
WIP | Batch | Create Batch
WIP | Run Card | Split Run Card
WIP | Run Card | Recover Run Card
WIP | Run Card | Release Split Run Card
WIP | Run Card | View/Change Run Card State
WIP | Run Card | Run Card Reform
WIP | Sorter | Sorter Track In
WIP | Sorter | Sorter Track Out
WIP | Sorter | Sorter Job Prepare
WIP | Sorter | Sorter Cancel Job Prepare
WIP | Sorter | Sorter Cancel Track In
WIP | Sorter | Sorter Job Cancel
WIP | Machine Recipe Control | Machine Recipe Management
WIP | Machine Recipe Control | Machine Recipe Management History
WIP | Machine Recipe Control | Machine Recipe Constraint Release
WIP | Machine Recipe Control | Machine Recipe Constraint Release History

## Page9
Lot | Hold Lot | Hold Lot
Lot | Hold Lot | Batch Release
Lot | Hold Lot | Batch Hold
Lot | Hold Lot | Release Lot
Lot | Hold Lot | Edit Hold
Lot | Hold Lot | Release Action
Lot | Future Action | Future Reserve Machine
Lot | Future Action | Set Future Hold
Lot | Future Action | Set Future Merge
Lot | Future Action | Batch Future Hold
Lot | Future Action | Set Future Split
Lot | Future Action | Future Action List
Lot | Rework | Rework
Lot | Rework | Cancel Rework
Lot | Rework | Split Rework
Lot | Reposition | Reposition Oper
Lot | Reposition | Special Reposition Oper
Lot | Reposition | Fetch Oper
Lot | Reposition | Skip Step
Lot | Reposition | Back Step
Lot | Reposition | Reposition Rule
Lot | Sorter | Split Lot
Lot | Sorter | Merge Lot
Lot | Sorter | Transfer Lot
Lot | Sorter | Exchange Carrier
Lot | Sorter | Change Slot Map Info
Lot | Sorter | Wafer Rotate
Lot | Sorter | Wafer Verification
Lot | Reassign | Reassign Lot
Lot | Reassign | Reassign Lot For NPW
Lot | Reassign | Future Reassign
Lot | Terminate | Terminate Lot
Lot | Terminate | Terminate Lot By Carrier
Lot | Terminate | Unterminate Lot
Lot | Terminate | Terminate Finish Lot
Lot | Terminate | Special Unterminate Lot
Lot | Scrap Lot | Scrap Apply
Lot | Scrap Lot | Cancel Scrap Apply
Lot | Scrap Lot | Scrap
Lot | Scrap Lot | UnScrap
Lot | Pilot | Create Pi Lot
Lot | Pilot | View Pi Lot
Lot | Pilot | Stop Pilot
Lot | Pilot | Release Hold Pilot
Lot | Pilot | End PiLot
Lot | Lot Attribute | Add Steps
Lot | Lot Attribute | Add Comment
Lot | Lot Attribute | Modify Lot Attribute
Lot | Lot Attribute | Batch Modify Lot Attribute
Lot | Lot Attribute | Modify Lot Attribute For MFG
Lot | Lot Attribute | Modify Lot Attribute For QC
Lot | Lot Attribute | Modify Lot Contamination Level

## Page10
Lot | Sampling | Set Scan Lot
Lot | Sampling | Set Sampling Skip Lot
Lot | Sampling | Sampling Reserve Lot List
Lot | Sampling | Sampling Skip Lot List
Lot | Sampling | Lot Sampling Run Time History
Lot | Dedication | Break Dedication
Machine | Port | Change Port Access Mode
Machine | Machine | Change Machine Control Mode
Machine | Machine | View Machine Auto Mode
Machine | Port | Change Port State
Machine | Machine | Change Machine State
Machine | Machine | Change Machine AMA Mode
Machine | PMS | Create Work Order
Machine | PMS | View Work Order
Machine | PMS | Work Order Approval
Machine | PMS | Calendar
Carrier | Management | View Carrier List
Carrier | Management | Create Carrier
Carrier | Management | Change Carrier Info
Carrier | Management | Scrap Carrier
Carrier | Management | Cancel Scrap Carrier
Carrier | Management | Change Carrier Clean State
Carrier | Management | Carrier RFID Management
Carrier | Management | Modify Carrier Attributes
Carrier | Management | Hold Carrier
Carrier | Management | Release Carrier
Carrier | Management | Assign Carrier
Carrier | Management | Deassign Carrier
Carrier | Management | Cancel Reserve Target Carrier
Transport | Transport | View Transport Queue
Transport | Stocker | Stocker Capacity
Transport | Stocker | Stocker Inventory
Transport | Transport | Re Transport Failed Lot
Transport | View | Transport Storage Info
Transport | View | Transfer Job List
Transport | View | Inventory List
Transport | View | Machine State List
Transport | View | Stocker CAPA.
Transport | View | Default Storage
Transport | Command | Manual Transfer
Transport | Command | Change Destination
Transport | Command | Change Transfer Priority
Transport | Command | Cancel Transfer Job
Transport | Command | Retry Alternative Job
Transport | Command | Synchronization
Inventory | Bank | Bank In
Inventory | Bank | Move Bank
Inventory | Bank | View Bank Info
Inventory | Bank | Bank Out
Inventory | Transfer | Transfer Mapping
Inventory | Transfer | Transfer Table Map
Inventory | Transfer | Fab Attribute Mapping Config

## Page11
Inventory | Transfer | Fab Attribute Value Mapping
Inventory | Transfer | Simple Transfer Lot
Inventory | Transfer | Receive Transfer Lot Back
Inventory | Transfer | Receive Transfer Lot
Inventory | Transfer | Simple Transfer Lot Back
Inventory | Transfer | View Transfer List
Inventory | Ship | Ship
Inventory | Ship | Unship
Inventory | Label Print | RSP Label
Inventory | Label Print | Lot Card
Inventory | Label Print | Lot Label
Inventory | Label Print | Reticle Label
Inventory | Label Print | FOSB Label
NPW | Spec | Furnace Monitor Control Rule Setting
NPW | Spec | Dummy Control Rule Setting
NPW | Spec | Monitor Control Rule Setting
NPW | Spec | Season Control Rule Setting
NPW | Spec | Downgrade Setting
NPW | Spec | NPW Inventory Setting
NPW | NPW Main Flow | In Use Start(Split)
NPW | NPW Main Flow | View In Use Start Lot
NPW | NPW Main Flow | In Use End
NPW | NPW Main Flow | Downgrade
NPW | NPW Main Flow | Modify Wafer Information
NPW | Dummy | Dummy Load
NPW | Dummy | Dummy UnLoad
NPW | Furnace Monitor | View Furnace Wait Batch
NPW | Furnace Monitor | Furnace Batch Boat Info Setting
NPW | Season | PM Season Group
NPW | Season | PM Season Control Rule Setting
NPW | Inquiry | View NPW Inventory Status
NPW | Inquiry | View Machine Dummy Information
NPW | Inquiry | View Season History
NPW | Inquiry | View Machine Control Status
NPW | Inquiry | View Recycle End Lot List
Reticle | Reticle | View Reticle List
Reticle | Reticle | Create Reticle
Reticle | Reticle | Quality Check
Reticle | Reticle | Reticle Clean Complete
Reticle | Reticle | Reticle Release
Reticle | Reticle | Reticle Bank Out
Reticle | Reticle | Cancel Scrap Reticle
Reticle | Reticle | Reticle Scan In
Reticle | Reticle | Reticle Scan Out
Reticle | Reticle | Material History
Reticle | Pod | View Pod List
Reticle | Pod | Pod Exchange
Reticle | Pod | Pod Cancel Scrap
Reticle | Pod | Pod Release
Reticle | Pod | Pod Clean Complete
Inquiry | Lot | View Lot Info
Inquiry | Lot | View Lot List

## Page12
Inquiry | Lot | Data Collect Lot History
Inquiry | Lot | View Lot History
Inquiry | Carrier | View Carrier Status
Inquiry | Carrier | View Carrier History
Inquiry | Lot | View Hold Lot Info
Inquiry | Lot | View T7 Code
Inquiry | Lot | Full Lot Report
Inquiry | Alarm | View Current Alarm
Inquiry | Alarm | AlarmRun
Inquiry | Machine | View Machine Info
Inquiry | Machine | View Machine Process History
Inquiry | Machine | View Machine History
Inquiry | Machine | View Machine Status
Inquiry | Wafer | View Wafer History
Inquiry | Wafer | View Wafer Chamber Tracking History
Inquiry | Wafer | View Component Info
Inquiry | Q-Time | Q-Time List
Inquiry | Q-Time | Q-Time Control
Inquiry | NPW | View Monitor Status
Inquiry | NPW | View Monitor Lot History
Inquiry | NPW | View NPW PFO
Inquiry | NPW | View Machine Dummy Lot History
Inquiry | NPW | View Machine Dummy Wafer History
Inquiry | NPW | View Furnace Batch History

## P13_T1
序号 | 一级模块 | 二级模块 | 三级模块(Function Name) | UI | Access String Full Name

## P13_T2
Create Lot
Create NPW Lot
Create Engineer Lot
View Create Lot List
View Transaction Raw Wafer List
View Raw Wafer List
Create Source Vendor Lot
View Source Vendor Lot List
Start Lot

## P13_T3
Cancel Prepared Lot
Track In
Cancel TrackIn
Track Out
Sorter Prepare Lot
Sorter Cancel Prepared Lot
Sorter Track In
Sorter Cancel TrackIn
Sorter Track Out
Cancel Sorter Job

## P13_T4
Set Furnace batch boat information

## P13_T5
Create Split Run Card

## P13_T6
View Run Card State
Change Run Card State
Create Recover Run Card

## Page14
Lot
192 |  |  | Lot Process Version | #N/A
193 |  |  | Lot Specialization | #N/A
Lot Attribute
194 |  |  | Maintain RMS Flag | #N/A
195 |  |  | Modify Lot Attribute | Modify Lot Attribute | Confirm:Modify Lot Attribute
196 |  |  | Batch Modify Lot Attribute | Batch Modify Lot Attribute | Confirm:对批量Lot 进行Modify Lot Attribute
197 |  |  | Modify Lot Attribute For QC | Modify Lot Attribute For QC | Confirm:权限管控QC 可Modify
198 |  |  | Modify Lot Attribute For MFG | Modify Lot Attribute For MFG | Confirm:权限管控MFG 可Modify
199 |  |  | Modify Lot Contamination Level | Modify Lot Contamination Level | Confirm:Modify Contamination Level
200 |  |  | Bank In | Bank In | Confirm:Bank In
201 |  |  | Batch Bank In | #N/A
202 |  | Bank | Bank Out | Bank Out | Confirm:Bank Out
203 |  |  | View Bank Info. | #N/A | Search:查看Bank 信息
204 |  |  | Move Bank | Move Bank | Confirm:Move Bank
205 |  |  |  | #N/A | Create:创建Plan
206 |  |  | Transfer Lot Plan | #N/A | Remove:删除Plan
207 |  |  |  | #N/A | Modify :修改Plan
208 |  |  | Transfer Lot Report | #N/A | Confirm:更改day Plan数量
209 |  |  |  | Fab Attribute Mapping Config | Create:创建
210 |  |  | FAB Attribute Mapping Config | #N/A | Remove:删除
Transfer
211 |  |  |  | #N/A | Modify :修改
Inventory
212 |  |  | FAB Attribute Value Mapping | Fab Attribute Value Mapping | Modify:更改Value及MappingValue
213 |  |  | Transfer Lot To Other FAB | #N/A | Confirm:Transfer Lot To Other FAB
214 |  |  | Recieve Own FAB Transfer Lot | #N/A | Confirm:Recieve Own FAB Transfer Lot
215 |  |  | Recieve Other FAB Lot | #N/A | Confirm:Recieve Other FAB Lot
216 |  |  | Cancel Transfer | #N/A | Confirm:Cancel Transfer
217 |  |  | View Transfer Lot List | #N/A
218 |  |  | Lot Label | #N/A | Confirm:Lot Label
219 |  |  | Lot Card | Lot Card | Confirm:生成Barcode
220 |  | Label | RSP Label | #N/A | Confirm:RSP Label
221 |  |  | Reticle Label | #N/A | Confirm:Reticle Label
222 |  |  | FOSB Label | #N/A | Confirm:生成FOSB ID
223 |  |  | Ship | Ship | Confirm:fab out
Ship
224 |  |  | Cancel Ship | #N/A | Confirm:cancel fab out
225 |  |  | Change Machine State | Change Machine State | Comfirm: 数据提交
226 |  |  | Change Port State | Change Port State | Comfirm: 数据提交
EQP State
227 |  |  | Change Machine Mode | #N/A | Comfirm: 数据提交
228 |  |  | Change Port Mode | #N/A | Comfirm: 数据提交
229 |  |  | Set Machine Capability | #N/A
Capability
230 |  |  | Set Chamber Capability | #N/A
231 |  |  | Tank Control | #N/A
232 |  |  | Wet Tank Control | #N/A
233 |  | Tank Control | Tank Count Info | #N/A
234 |  |  | Tank Running History | #N/A
235 |  |  | Tank OOS History | #N/A
236 |  |  | Create Work Order | Create Work Order
237 |  |  | Work Order | Work Order
238 |  |  | Work Order Approval | Work Order Approval
239 |  |  | PM Card | #N/A
PMS
240 |  |  | Calendar | Calendar
241 |  |  | Manual CBM | #N/A
242 |  |  | Reset CBM | #N/A
243 | Machine |  | EC Work Order | #N/A
244 |  |  | Inform Note | #N/A
245 |  |  | [Inform Type Data Tab] | #N/A
Inform Note
246 |  |  | [History Type Data Tab] | #N/A
247 |  |  | Inform Notice | #N/A
248 |  |  | Control Action History | #N/A
249 |  |  | One Key Touch | #N/A
250 |  | One Key Touch | One Key Touch Detail History | #N/A
251 |  |  | Power Source Setup | #N/A
252 |  |  | Power Source Setup History | #N/A
253 |  |  | View Equipment Auto Mode | #N/A
254 |  |  | Modify Equipment Current Lots | #N/A
255 |  |  | Delete Chamber Current Lots | #N/A
256 |  |  | Modify Equipment Attribute | #N/A
257 |  | Other | Modify Eqp Chamber Run Count | #N/A
258 |  |  | Buffer Tool Physical Foup Maintain | #N/A
259 |  |  | MFG Eqp Security Control Maintenance | #N/A
260 |  |  | Customize(定制) EQP Information | #N/A
261 |  |  | Equipment Couple Port | #N/A
262 |  |  | Create Carrier | Create Carrier | Create:创建Carrier Name
263 |  |  | Carrier RFID Managerment | #N/A | Print: 打印标签RFID Clear: 清除RFID上Carrier信息Confirm: 数据提交
264 |  |  | Assign Carrier | Assign Carrier | Assign: Lot与Carrier绑定
265 |  |  | Deassign Carrier | Deassign Carrier | Deassign: Lot与Carrier解绑
266 |  |  | Hold Carrier | Hold Carrier | Hold: 锁定Carrier
267 |  | Carrier Management | Release Carrier | Release Carrier | Release: 解锁Carrier
268 |  |  | Reserve Target Carrier | #N/A
269 |  |  | Cancel Reserve Target Carrier | Cancel Reserve Target Carrier
270 |  |  | Scrap Carrier | Scrap Carrier | Scrap: 报废Carrier
271 |  |  | Cancel Scrap Carrier | Cancel Scrap Carrier | Confirm: 数据提交,取消报废Carrier
272 |  |  | Change Carrer Info | #N/A | Confirm: 数据提交,更改Carrier信息
273 |  |  | Set Carrier Clean | #N/A | Confirm: 数据提交,手动预约Carrier Clean
274 |  |  | Start Carrier Clean | #N/A | Confirm: 数据提交,手动Start Carrier CleanCancel Carrier Clean: 跳转到Cancel Carrier Clean页面
Carrier Clean
275 |  |  | End Carrier Clean | #N/A | Confirm: 数据提交,手动End Carrier CleanCancel Carrier Clean: 跳转到Cancel Carrier Clean页面
276 |  |  | Change Carrier Clean State | #N/A | Confirm: 数据提交,更改Clean State
277 | Carrier |  | Cancel Clean | #N/A | Cancel Start Carrier Clean: 手动Cancel Start Carrier Clean数据Cancel Set Carrier Clean: 手动Cancel Set Carrier Clean数据
278 |  |  | Carrier Downgrade Maps | #N/A
Carrier Down Grade
279 |  |  | Carrier Model Number Maps | #N/A
280 |  |  | Carrier Part | #N/A
281 |  |  | Carrier Part & Carrier Part Maps | #N/A
282 |  |  | View Carrier Part Info | #N/A
Carrier Parts Management
283 |  |  | Repair FOUP | #N/A
284 |  |  | Update Carrier Component | #N/A
285 |  |  | Add Carrier Comment | #N/A
286 |  |  | Set Inspection | #N/A
287 |  |  | Cancel Inspection | #N/A
288 |  |  | Start Inspection | #N/A
289 |  |  | Set Disposal | #N/A
Carrier Inspection
290 |  |  | Cancel Disposal | #N/A
291 |  |  | End Inspection | #N/A
292 |  |  | Carrier Data Collection | #N/A
293 |  |  | Inspection Flow Control | #N/A
294 |  |  | Monitor Control Rule Setting | Monitor Control Rule Setting | Create,Modify,Remove,Copy,Confirm
295 |  |  | Dummy Control Rule Setting | Dummy Control Rule Setting | Create,Modify,Remove,Copy,Confirm
296 |  |  | Season Control Rule Setting | Season Control Rule Setting | Create,Modify,Remove,Copy,Confirm
SPEC
297 |  |  | Furnace Monitor Control Rule Setting | #N/A | Create,Modify,Remove,Copy,Confirm
298 |  |  | NPW Inventory Setting | NPW Inventory Setting | Create,Modify,Remove,Copy,Confirm
299 |  |  | Downgrade Setting | Downgrade Setting | Create,Modify,Remove,Confirm
300 |  |  |  | #N/A | Split: Split Lot
In Use Start
301 |  |  |  | #N/A | Confirm: Split & In Use Start
302 |  |  | In Use Start Auto Split Sorter Job Create(Time) | #N/A
303 |  |  | Auto Change Control ID Flag N->Y(Time) | #N/A
304 |  |  |  | #N/A | Complete Monitor
View Machine Monitor Status
305 |  |  |  | #N/A | Delay Monitor
306 |  |  | Complete Monitor Control | #N/A
307 |  |  | Delay Monitor Control | #N/A
308 |  |  | NPW In Use Start Adhoc Merge Sorter Job Create (Time) | #N/A
309 |  |  | In Use End | In Use End | Confirm: Merge Lot (In Use End站点), 25张后Skip当前站点
NPW Main Flow
310 |  |  | Auto In Use End Merge Sorter Job Create | #N/A
311 |  |  | In Use Start (Adhoc Merge) | #N/A | Confirm: Merge Lot (In Use Start 站点)
312 |  |  |  | #N/A | Downgrade
313 |  |  | View Recycle End Lot List | #N/A | Scrap Apply
314 |  |  |  | #N/A | Reuse
315 | NPW |  | Make Recycle End Lot To Re Use | #N/A
316 |  |  | Downgrade | Downgrade | Confirm: Downgrade Lot
317 |  |  | Change NPW Product Spec | #N/A | Confirm
318 |  |  | Modify Wafer Information | Modify Wafer Information | Confirm: 修改Wafer信息
319 |  |  | Time Auto Change Wafer Clean State Clean->Dirty | #N/A
320 |  |  |  | View Furnace Wait Batch | Reset DC Result,
View Furnace Wait Batch
321 |  | Furnace Monitor |  | #N/A | REQ Track In
322 |  |  | FML Safety Inventory 维护功能(Time) | #N/A
323 |  |  |  | Dummy Load | Modify MC Dummy Info
Dummy Load
324 |  |  |  | #N/A | Confirm
Dummy
325 |  |  |  | Dummy UnLoad | Modify MC Dummy Info
Dummy UnLoad
326 |  |  |  | #N/A | Confirm
327 |  |  | Recipe Group | #N/A
328 |  |  | View Machine Control Status(Season) | #N/A
329 |  |  | View Season History | View Season History | Search
Season
330 |  |  | PM Season Control ID | #N/A
331 |  |  |  | PM Season Group | Reset DC Result,
PM Season Group
332 |  |  |  | #N/A | REQ Track In
333 |  |  | View Machine Dummy Infomation | #N/A | Search
334 |  |  | View NPW Lot Information | #N/A
Inquiry
335 |  |  | View Machine Dummy Wafer History | #N/A | Search
336 |  |  | Farnace Batch History | #N/A
337 |  |  | Reticle List | #N/A | Hold: 锁住Reticle Inspect Request: 检测请求Clean: 更改Reticle Clean StateScan Request: 扫描请求Scrap: 报废ReticleBank In:Bank In
338 |  |  | Create Reticle | #N/A | Generate: 创建生成Reticle NameConfirm:数据提交
339 |  |  | Quallity Check | #N/A | Confirm:数据提交
340 |  |  | Reticle Process Attach | #N/A | Add:新增Reticle与机台绑定Modify:编辑Reticle与机台绑定信息Remove: 删除Reticle与机台绑定
341 |  |  | Reticle Load/Unload | #N/A | Load: Load ReticleUnload: Uload Reticle
342 |  |  | Reticle Transport | #N/A | Reticle Out: 将Reticle调出Stocker
Reticle
Reticle

## Page15
343 |  |  | Special Dismount | #N/A
344 |  |  | Reticle Inspect In | #N/A | Inspect In: Manual Inspect Start
345 |  |  | Reticle Inspect Out | #N/A | Inspect Out: Manual Inspect End
346 |  | Reticle | Reticle Clean Complete | Reticle Clean Complete | Clean Complete: Manual Clean End
347 |  |  | Reticle Release | #N/A | Release: Reticle解锁
348 |  |  | BankOut | #N/A | Bank Out:Bank Out
349 |  |  | Cancel Scrap Reticle | #N/A | Confirm:数据提交,取消报废Reticle
350 |  |  | Reticle Scran In | #N/A | Scran In: Manual Scan Start
351 |  |  | Reticle Scan Out | Reticle Scan Out | Scan Out: Manual Scan End
352 |  |  | Return | #N/A
Reticle
353 |  |  | Retrive | #N/A
354 |  |  | Maual Data Collection | #N/A
355 |  |  | Reticle Info. Maintenence | #N/A
356 |  |  | RSPList | #N/A | Create: 弹框操作,创建生成RSP NameChange Info: 弹框操作,更改RSP InfoAssign: 弹框操作,Rsp 与Reticle绑定Deassign: 弹框操作,Rsp 与Reticle解绑Hold: 弹框操作,锁住RSPClean: 弹框操作,更改Rsp Clean StateScrap:弹框操作,报废RSP
357 |  |  | Create RSP | #N/A | Confirm:数据提交Cancel: 关掉页面
358 |  |  | Change RSP Info | #N/A | Confirm:数据提交Cancel: 关掉页面
359 |  |  | Assign reticle to RSP | #N/A | Confirm:数据提交Cancel: 关掉页面
360 |  |  | Deassign reticle from RSP | #N/A | Confirm:数据提交Cancel: 关掉页面
361 |  |  | Hold RSP | #N/A | Confirm:数据提交Cancel: 关掉页面
362 |  | RSP | Clean RSP | #N/A | Confirm:数据提交Cancel: 关掉页面
363 |  |  | Scrap RSP | #N/A | Confirm:数据提交Cancel: 关掉页面
364 |  |  | RSP Clean Complete | #N/A | Confirm:数据提交,Manual Clean Complete
365 |  |  | Exchange RSP | #N/A | Exchange: 给两个Reticle交换RSP
366 |  |  | Release RSP | #N/A | Release: RSP解锁
367 |  |  | RSP Cancel Scrap | #N/A | RSP Cancel Scrap: 取消报废
368 |  |  | Repair RSP | #N/A
369 |  |  | Add Comment | Add Comment
370 |  |  | Lot Info. | #N/A
371 |  |  | ViewLotList | #N/A
372 |  |  | View Wafer Info. | #N/A
373 |  |  | T7 Code View | #N/A
374 |  |  | Lot History | #N/A
Lot/Wafer
375 |  |  | Wafer History | #N/A
376 |  |  | View Wafer Verification Result | #N/A
377 |  |  | View Component Information | #N/A
378 |  |  | Wafer Chamber Tracking History | #N/A
379 |  |  | Wafer Slot History | #N/A
Inquiry
380 |  |  | Furnace Batch History | #N/A
381 |  |  | View Machine Status | View Machine Status
382 |  |  | View Machine History | View Machine History
Machine
383 |  |  | PM,BM History | #N/A
384 |  |  | Equipment Process History | #N/A
385 |  |  | View Carrier List | #N/A | Scrap Carrier:跳转按钮,跳转到Scrap Carrier页面Cancel Scrap Carrier:跳转按钮,跳转到Cancel Scrap Carrier页面Change Carrier Info: 跳转按钮,跳转至Change Carrier Info页面Clean Carrier: 跳转按钮,跳转至Change Carrier Clean StateRelease Carrier: 跳转按钮,跳转至Release Carrier页面Hold Carrier;跳转按钮,跳转至Hold Carrier页面
386 |  |  | View Carrier Cycle | #N/A
Carrier
387 |  |  | View Carrier Status | View Carrier Status | Search: 页面数据搜索Reset: 清空搜索栏内数据
388 |  |  | View Carrier History | View Carrier History | Search: 页面数据搜索Reset: 清空搜索栏内数据
389 |  |  | Lot Sampling Runtime History | #N/A
Sampling
390 |  |  | YE Step Sampling History | #N/A
391 | CSN | CSN | JP Fail Lot List | #N/A
392 |  |  | OCAP MGMT | #N/A
393 |  |  | Show OCAP Detail Info | #N/A
394 |  |  | Change Measure Machine | #N/A
395 |  |  | Modify Reason Code | #N/A
396 |  |  | Dispatch | #N/A
OCAP
397 |  |  | Change Flow | #N/A
398 |  |  | Change Step | #N/A
399 |  |  | Remeasurement | #N/A
400 |  |  | Add Measurement | #N/A
401 |  |  | Engineer Confirm | #N/A