## OIC Function List
Phase1: Now~2022/12/31
* Cowin MES(OIC) Function List (Scope定义) | [6 empty] | Phase2: 2023/1/1~2023/3/31
Level 1 | Level 2 | NO | Level 3 | 模块 | 重点关注 | 功能确定 | Phase | 参考系统 | 参考UI | 有无 | 接口 | [7 empty] | 界面说明 | 功能构建 |  |  |  | 设计通过 | 设计评审计划 |  |  | 第一轮 | [9 empty] | 第二轮 | [9 empty] | 代码检查
[11 empty] | ERP | EAP | MCS | RTD | RMS | FDC | R2R | Fab |  | 责任人 | 开发人 | 开发地 | 完成 |  | Plan | Act | 评审人员 | 测试完成 | 改善完成 | 测试通过 | 开发改善 Day | PlanStart | PlanEnd | ActDays | ActStart | ActEnd | 开发者 | 测试完成 | 改善完成 | 测试通过 | 开发改善 Day | PlanStart | PlanEnd | ActDays | ActStart | ActEnd | 开发者 | 检查人 | 检修计划 | 完成
Main | Main | 1 | Main WIP（View Lot） | Main |  | 确定 | Phase1 | AMAT | 主页 | 有 | [8 empty] | 非 PHOTO, Sorter 机台的 Machine , Lot 监控及操作 | 申克楠 | 常刘勺 | 苏州
Carrier Mgt |  | 2 | Add Carrier Comment | Carrier | 非重点 | 确定 | Phase1 | AMAT | Add Carrier Comment | 无 | [8 empty] | 添加Carrier Comment | 杨金杰 | 郭天娇 | 无锡 |  |  | 2022-10-18 | [5 empty] | 2 | 2022-10-19 | 2022-10-21
|  | 3 | Cancel Clean | Carrier | 重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | Cancel Set Clean,Cancel Start Clean | 杨金杰 | 郭天娇 | 无锡 |  |  | 2022-10-24 | [5 empty] | 3 | 2022-10-28 | 2022-10-31
|  | 4 | Cancel Inspection | Carrier | 重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | Cacel Set Inspetion | 杨金杰 | 郭天娇 | 无锡 |  |  | 2022-11-07 | [5 empty] | 3 | 2022-11-08 | 2022-11-11
|  | 5 | Carrier Data Collection | Carrier |  |  |  | AMAT |  | 无 | [9 empty] | 李彬
|  | 6 | Disposal/Undo Disposal | Carrier | 次重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | Set Disposal之后的 处置,和Cancel 处置Carrier的动作 | 杨金杰 | 郭天娇 | 无锡 |  |  | 2022-10-31 | [5 empty] | 3 | 2022-11-01 | 2022-11-04
|  | 7 | Inspection Flow Control | Carrier |  |  |  | AMAT |  | 无 | [9 empty] | 杨金杰 | 郭天娇 | 无锡
|  | 8 | Start/End Inspection | Carrier | 重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | 开始Carrier 量测，结束Carrier量测 | 杨金杰 | 郭天娇 | 无锡 |  |  | 2022-11-07 | [5 empty] | 3 | 2022-11-08 | 2022-11-11
|  | 9 | Repair FOUP | Carrier | 次重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | 修理FOUP | 杨金杰 | 郭天娇 | 无锡 |  |  | 2022-10-31 | [5 empty] | 3 | 2022-11-01 | 2022-11-04
|  | 10 | Reserve Target Carrier | Carrier | 重点 | 确定 | Phase1 | AMAT | Reserve Target Carrier | 无 | [8 empty] | 预约Carrier,防止其他用途使用 | 杨金杰 | 郭天娇 | 无锡 | 完成 | [7 empty] | 3 | 1899-12-31 | 1900-01-03
|  | 11 | Set Disposal/Cancel Disposal | Carrier | 次重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | Repair/Scrap之前的设定处置,和Cancel 设定 处置Carrier的动作 | 杨金杰 | 郭天娇 | 无锡 |  |  | 2022-10-31 | [5 empty] | 3 | 2022-11-01 | 2022-11-04
|  | 12 | Set Clean | Carrier | 重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | 设定Clean | 杨金杰 | 郭天娇 | 无锡 |  |  | 2022-10-24 | [5 empty] | 3 | 2022-11-01 | 2022-11-04
|  | 13 | Set Inspection | Carrier | 重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | 设定Carrier Inspecton | 杨金杰 | 郭天娇 | 无锡 |  |  | 2022-11-07 | [5 empty] | 3 | 2022-11-08 | 2022-11-11
|  | 14 | Special Transfer Lot | Carrier |  |  |  | AMAT |  | 无 | [8 empty] | 特殊Transfer Lot处理 | 杨金杰 | 郭天娇 | 无锡
|  | 15 | Start/End Clean | Carrier | 重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | 开始Carrier Clean,结束Carrier Clean | 杨金杰 | 郭天娇 | 无锡 |  |  | 2022-10-24 | [5 empty] | 3 | 2022-11-05 | 2022-11-08
|  | 16 | Update Carrier Component | Carrier |  |  |  | AMAT |  | 无 | [8 empty] | 更新Carrier组件(?) | 杨金杰 | 郭天娇 | 无锡
| View Carrier Info | 17 | View Carrier Cleaning History | Carrier | 次重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | 查询Carrier Cleaning 历史记录 | 杨金杰 | 郭天娇 | 无锡 |  |  | 2022-10-18 | [5 empty] | 2 | 2022-10-22 | 2022-10-24
| View Carrier Info | 18 | View Carrier Cycle | Carrier | 次重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | 查询Carrie Cycle现况 | 杨金杰 | 郭天娇 | 无锡 |  |  | 2022-10-18 | [5 empty] | 2 | 2022-10-25 | 2022-10-27
Eqp Mgt |  | 19 | Buffer Tool Physical Foup Maintain | Machine |  |  |  | AMAT |  | 无 | [8 empty] | 管理Buffer的FOUP | 杨金杰 | 王哲 | 无锡
| One Key Touch | 20 | Control Action History | Machine |  |  |  | AMAT |  | 无 | [9 empty] | 杨金杰 | 王哲 | 无锡
|  | 21 | Customize EQP Information | Machine |  |  |  | AMAT |  | 无 | [9 empty] | 杨金杰 | 王哲 | 无锡
|  | 22 | Delete Chamber Current Lots | Machine | 次重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | 删除掉chamber的Current Lot | 杨金杰 | 王哲 | 无锡 |  |  | 2022-11-01 | [5 empty] | 3 | 2022-11-02 | 2022-11-05
|  | 23 | Equipment Couple Port | Machine | 重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | Machine Couple Port | 杨金杰 | 王哲 | 无锡 |  |  | 2022-11-08 | [5 empty] | 3 | 2022-11-09 | 2022-11-12
|  | 24 | EQP Manual Process Configuration | Machine |  |  |  | AMAT |  | 无 | [9 empty] | 杨金杰 | 王哲 | 无锡
|  | 25 | MFG Eqp Security Control Maintenance | Machine |  |  |  | AMAT |  | 无 | [9 empty] | 杨金杰 | 王哲 | 无锡
|  | 26 | Modify Equipment Attribute | Machine | 重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | Modify机台属性 | 杨金杰 | 王哲 | 无锡 |  |  | 2022-11-08 | [5 empty] | 3 | 2022-11-09 | 2022-11-12
|  | 27 | Modify Eqp Chamber Run Count | Machine | 次重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | Modify Chamber进行中的Lot | 杨金杰 | 王哲 | 无锡 |  |  | 2022-11-01 | [5 empty] | 3 | 2022-11-02 | 2022-11-05
|  | 28 | Modify Equipment Current Lots | Machine | 次重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | Modify机台进行中的Lot | 杨金杰 | 王哲 | 无锡 |  |  | 2022-11-01 | [5 empty] | 3 | 2022-11-02 | 2022-11-05
|  | 29 | Set Equipment Capability | Machine | 次重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | 设定机台的Capability | 杨金杰 | 王哲 | 无锡 |  |  | 2022-10-25 | [5 empty] | 3 | 2022-10-26 | 2022-10-29
| One Key Touch | 30 | One Key Touch | Machine |  |  |  | AMAT |  | 无 | [9 empty] | 杨金杰 | 王哲 | 无锡
| One Key Touch | 31 | One Key Touch Detail History | Machine |  |  |  | AMAT |  | 无 | [9 empty] | 杨金杰 | 王哲 | 无锡
| One Key Touch | 32 | Power Source Setup | Machine |  |  |  | AMAT |  | 无 | [9 empty] | 杨金杰 | 王哲 | 无锡
| One Key Touch | 33 | Power Source Setup History | Machine |  |  |  | AMAT |  | 无 | [9 empty] | 杨金杰 | 王哲 | 无锡
|  | 34 | Reticle Equipment Process History | Machine | 次重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | Reticle Process机台的历史记录 | 杨金杰 | 王哲 | 无锡 |  |  | 2022-10-25 | [5 empty] | 3 | 2022-10-26 | 2022-10-29
|  | 35 | Set Chamber Capability | Machine | 次重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | 设定Chamber的Capability | 杨金杰 | 王哲 | 无锡 |  |  | 2022-10-25 | [5 empty] | 3 | 2022-10-26 | 2022-10-29
| Tank Control | 36 | Tank Count Info | Machine |  |  | Phase2 | AMAT |  | 无 | [9 empty] | 杨金杰 | 王哲 | 无锡
| Tank Control | 37 | Tank OOS History | Machine |  |  | Phase2 | AMAT |  | 无 | [9 empty] | 杨金杰 | 王哲 | 无锡
| Tank Control | 38 | Tank Running History | Machine |  |  | Phase2 | AMAT |  | 无 | [9 empty] | 杨金杰 | 王哲 | 无锡
|  | 39 | Tool Recovery Control System | Machine |  |  | Phase2 | AMAT |  | 无 | [9 empty] | 杨金杰 | 王哲 | 无锡
|  | 40 | Tool Recovery Package Setup | Machine |  |  | Phase2 | AMAT |  | 无 | [9 empty] | 杨金杰 | 王哲 | 无锡
| Tank Control | 41 | Wet Tank Control | Machine |  |  | Phase2 | AMAT |  | 无 | [9 empty] | 杨金杰 | 王哲 | 无锡
| PMS | 42 | Arrange PM | Machine |  |  | Phase2 | AMAT |  | 无 | [9 empty] | 杨金杰 | 王哲 | 无锡
| PMS | 43 | Conditional PM | Machine |  |  | Phase2 | AMAT |  | 无 | [9 empty] | 杨金杰 | 王哲 | 无锡
| PMS | 44 | Trigger Readings | Machine |  |  | Phase2 | AMAT |  | 无 | [9 empty] | 杨金杰 | 王哲 | 无锡
| PMS | 45 | Usage Meter | Machine |  |  | Phase2 | AMAT |  | 无 | [9 empty] | 杨金杰 | 王哲 | 无锡
| Tank Control | 46 | Tank Count Info | Machine |  |  | Phase2 | AMAT |  | 无 | [9 empty] | 杨金杰 | 王哲 | 无锡
| Tank Control | 47 | Tank Running History | Machine |  |  | Phase2 | AMAT |  | 无 | [9 empty] | 杨金杰 | 王哲 | 无锡
Lot Mgt | Reassign | 48 | Change Sales Order | Lot |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 罗涛
| FeedForward Attribute | 49 | Copy FeedForward Information | Lot | 次重点 | 确定 | Phase2 | AMAT | Copy FeedForward Information | 无 | [8 empty] | 拷贝FeedForward信息 | 罗涛 | 袁浩 | 苏州 |  |  | 2023-01-01 | [5 empty] | 3 | 2023-01-02 | 2023-01-04
| FeedForward Attribute | 50 | Delete FeedForward Information | Lot | 次重点 | 确定 | Phase2 | AMAT | Delete FeedForward Information | 无 | [8 empty] | 删除FeedForward信息 | 罗涛 | 袁浩 | 苏州 |  |  | 2023-01-01 | [5 empty] | 3 | 2023-01-05 | 2023-01-09
|  | 51 | Modify Lot Attribute For QE | Lot | 非重点 | 确定 | Phase2 | AMAT |  | 无 | [9 empty] | 罗涛 |  |  |  |  | 2023-01-01
|  | 52 | Lot Specialization | Lot | 次重点 | 确定 | Phase1 | AMAT | Lot Specialization | 无 | [8 empty] | Lot到达指定的站点后使用该配置的新值（EQP, PPID, EDCPlan, Reticle ID, Recipe ID） | 罗涛 | 袁浩 | 苏州 |  |  | 2022-11-01 | [5 empty] | 5 | 2022-11-02 | 2022-11-09
| FeedForward Attribute | 53 | Modify FeedForward Information | Lot | 次重点 | 确定 | Phase2 | AMAT | Modify FeedForward Information | 无 | [8 empty] | 修改FeedForward信息 | 罗涛 | 袁浩 | 苏州 |  |  | 2023-01-01 | [5 empty] | 3 | 2023-01-10 | 2023-01-12
|  | 54 | Modify Potential Attribute | Lot |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 罗涛
|  | 55 | Maintain RMS Flag | Lot |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 罗涛
|  | 56 | Set Stepper | Lot | 次重点 | 确定 | Phase1 | AMAT | Set Stepper | 无 | [8 empty] | 为Litho站点修改stepper | 罗涛 | 袁浩 | 苏州 |  |  | 2022-11-01
|  | 57 | Undo Finish | Lot | 重点 | 确定 | Phase1 | AMAT | Undo Finish | 无 | [8 empty] | 将finished lot reassign到指定站点 | 罗涛 | 袁浩 | 苏州 |  |  | 2022-11-01
|  | 58 | Choose Alter Step | Lot |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 罗涛
| MixRun | 59 | View Mix Run Status | Lot |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 罗涛
| Auto YE Review Wafer Selection Config | 60 | Wafer Selection History For Auto YE Review | Wafer Selection |  |  |  | AMAT |  | 无 | [9 empty] | 申克楠
| Auto YE Review Wafer Selection Config | 61 | Update Wafer List Of YE Review | Wafer Selection |  |  |  | AMAT |  | 无 | [9 empty] | 申克楠
| Auto YE Review Wafer Selection Config | 62 | Setting By Capability | Wafer Selection |  |  |  | AMAT |  | 无 | [9 empty] | 申克楠
| Auto YE Review Wafer Selection Config | 63 | Setting By Product | Wafer Selection |  |  |  | AMAT |  | 无 | [9 empty] | 申克楠
| Wafer Randomization | 64 | Adhoc Recover | Lot |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 罗涛
| Reposition | 65 | Back Up Step | Lot | 次重点 | 确定 | Phase1 | AMAT | Back Up Step | 无 | [8 empty] | 返回上一站 | 罗涛 | 袁浩 | 苏州 |  |  | 2022-11-01 | [5 empty] | 3 | 2022-11-10 | 2022-11-14
| Wafer Randomization | 66 | Config Random Recipe | Lot |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 罗涛
| Wafer Randomization | 67 | Lot Random History | Lot |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 罗涛
| Doma Management | 68 | Doma Path Config History | Lot |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 罗涛
| Doma Management | 69 | Doma Path Maintain | Lot |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 罗涛
| Doma Management | 70 | Doma Path Setting | Lot |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 罗涛
| Doma Management | 71 | DOMA RCD History | Lot |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 罗涛
| Future | 72 | Future Hold By Customer | Lot | 次重点 | 确定 | Phase1 | AMAT | Future Hold By Customer | 无 | [8 empty] | 适应客户定制的reason code设置future hold | 罗涛 | 袁浩 | 苏州 |  |  | 2022-11-01 | [5 empty] | 2 | 2022-11-15 | 2022-11-16
| Future | 73 | Set Future Hold Step Group | Lot |  | 确定 | Phase1 | AMAT | Set Future Hold Step Group | 无 | [9 empty] | 罗涛 | 袁浩 | 苏州 |  |  | 2022-11-01 | [5 empty] | 2 | 2022-11-17 | 2022-11-18
| SML | 74 | Inline Split For Special Lot | Lot |  | 确定 | Phase2 | AMAT |  | 无 | [9 empty] | 杨金杰 | 王哲 | 无锡
| Doma Management | 75 | Lot Doma History | Lot |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 罗涛
| Reposition | 76 | NPW Reposition | Lot | 次重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | NPW 的reposition | 罗涛 | 袁浩 | 苏州 |  |  | 2022-11-01 | [5 empty] | 2 | 2022-11-21 | 2022-11-22
| Reposition | 77 | Production Reposition | Lot |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 罗涛
| Simple Lot Transfer | 78 | Cancel Transfer Lot | Lot | 次重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | 取消Transfer lot | 罗涛 | 王华强 | 无锡 |  |  | 2022-11-15 | [5 empty] | 3 | 2022-11-16 | 2022-11-18
| Simple Carrier Transfer | 79 | Receive Transfer Carrier | Lot | 次重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | 传送 carrier | 罗涛 | 王华强 | 无锡 |  |  | 2022-11-15 | [5 empty] | 5 | 2022-11-21 | 2022-11-25
| Simple Carrier Transfer | 80 | Simple Transfer Carrier | Lot | 次重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | 接受carrier | 罗涛 | 王华强 | 无锡 |  |  | 2022-11-15 | [5 empty] | 3 | 2022-11-28 | 2022-11-30
| Simple Lot Transfer | 81 | Receive Plan | Lot | 次重点 | 确定 | Phase2 | AMAT |  | 无 | [9 empty] | 罗涛 | 王华强 | 无锡 |  |  | 2023-01-01
| Doma Management | 82 | Unprocessed DOMA Path View | Lot |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 罗涛
|  | 83 | YE Review Spec Configuration | Lot |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 罗涛
|  | 84 | YE Review Special Reposition | Lot |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 罗涛
|  | 85 | YE Select Wafers For Remeasure | Lot |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 罗涛
| MixRun | 86 | Mix Run | Lot |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 罗涛
| Pilot | 87 | Pilot Full Auto Information Setting | Lot |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 罗涛
| Pilot | 88 | Create Adhoc Pilot | Lot |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 罗涛
| Q'Time Control | 89 | Cancel Q'Time Reservation | Lot |  | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | 删除Lot 已经触发的Q-Time | 申克楠 | 王蓬皓 | 苏州 | 完成
| Q'Time Control | 90 | Turn Off Q'Time Speed Up | Lot |  | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | 关闭 Q-Time 的Speed Up 开关 | 申克楠 | 王蓬皓 | 苏州 | 完成
|  | 91 | Wafer Slot History | Lot |  |  |  | AMAT |  | 无 | [9 empty] | 童海潮
Lot Inventory | Inventory | 92 | Check Cust Maintain | Inventory | 次重点 | 确定 | Phase1 | AMAT | Check Cust Maintain | 无 | [8 empty] | 设置lot auto hold的规则 | 罗涛 | 王华强 | 无锡 |  |  | 2022-11-25 | [5 empty] | 5 | 2022-12-01 | 2022-12-08
| Inventory | 93 | Continue | Inventory | 次重点 | 确定 | Phase1 | AMAT | Continue | 无 | [8 empty] | move to location的逆操作 | 罗涛 | 王华强 | 无锡 |  |  | 2022-11-25 | [5 empty] | 3 | 2022-12-09 | 2022-12-13
| Inventory | 94 | Move To Location | Inventory | 次重点 | 确定 | Phase1 | AMAT | Move To Location | 无 | [8 empty] | 将zero layer flow结束的lot，从finished bank移动到start bank | 罗涛 | 王华强 | 无锡 |  |  | 2022-11-25 | [5 empty] | 3 | 2022-12-14 | 2022-12-16
WIP Tracking |  | 95 | Create Glass Lot | WIP |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 罗涛
| N2Purge | 96 | Cancel N2Purge | WIP |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 申克楠
| N2Purge | 97 | End N2Purge | WIP |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 申克楠
| N2Purge | 98 | Load Port N2 Purge Flag Maintain | WIP |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 申克楠
| N2Purge | 99 | Start N2Purge | WIP |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 申克楠
| Run Card | 100 | Get RunCard Information | WIP | 重点 | 确定 | Phase1 | AMAT | Get RunCard Information | 无 | [8 empty] | 获得RunCard 信息 | 陈永伟 | 秦亮 | 无锡 | 未完成 | 修改
| Run Card | 101 | Merge RunCard Lot | WIP | 重点 | 确定 | Phase1 | AMAT | Merge RunCard Lot | 无 | [8 empty] | RunCard Lot merge | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| PPID Control | 102 | Edit PPID Comment | WIP |  |  |  | AMAT |  | 无 | [9 empty] | 李彬
| Bonding | 103 | Bonding Lot History | WIP |  | 未确定 |  | AMAT | Bonding Lot History | 无 | [9 empty] | 申克楠
| Bonding | 104 | Bonded Lot | WIP |  | 未确定 |  | AMAT | Bonded Lot | 无 | [9 empty] | 申克楠
| Bonding | 105 | Bonding Lot Skip | WIP |  | 未确定 |  | AMAT | Bonding Lot Skip | 无 | [9 empty] | 申克楠
| Bonding | 106 | Bonding Lot Type Mapping | WIP |  | 未确定 |  | AMAT | Bonding Lot Type Mapping | 无 | [9 empty] | 申克楠
| Bonding | 107 | Bonding Product Mapping | WIP |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 申克楠
| Bonding | 108 | Bonding Step Mapping | WIP |  | 未确定 |  | AMAT | Bonding Step Mapping | 无 | [9 empty] | 申克楠
| Bonding | 109 | Glass Lot Information | WIP |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 申克楠
| Bonding | 110 | Pair Port Setting | WIP |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 申克楠
| Bonding | 111 | Pair Port Setting | WIP |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 申克楠
| Bonding | 112 | Pre Bonding | WIP |  | 未确定 |  | AMAT | Pre Bonding | 无 | [9 empty] | 申克楠
|  | 113 | Lot Queue Adjustment | WIP |  | 确定 | Phase1 | AMAT | Lot Queue Adjustment | 有 | [8 empty] | After do Lot Queue Reservation , the confirmed lot will be move into Queue , and user can use Lot queue Adjustment function to adjust the sequence. | 申克楠 | 常刘勺 | 苏州 | 完成
|  | 114 | Lot Queue Reservation | WIP |  | 确定 | Phase2 | AMAT | Lot Queue Reservation | 无 | [8 empty] | When EQP auto mode is Auto 2 , user need do lot queue reservation first. Otherwise system cannot get lot list in Job Prep UI | 申克楠
|  | 115 | Query FOUP-Lot Reservation | WIP |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 申克楠
| WaferSelectionRule | 116 | Setting By EDC Plan | WIP |  | 确定 | Phase1 | AMAT | Setting By EDC Plan | 无 | [8 empty] | 根据EDC Plan 配置ChamberCoverage 选片规则 | 申克楠/李彬
| WaferSelectionRule | 117 | Setting By EQP | WIP |  | 确定 | Phase1 | AMAT | Setting By EQP | 无 | [8 empty] | EQP Capability / EQP 别设置 WaferSelectionRule | 申克楠
|  | 118 | Setup Runtime Eqp State | WIP |  |  | Phase2 | AMAT |  | 无 | [9 empty] | 杨金杰 | 郭天娇 | 无锡
|  | 119 | R2R Modeling Configuration | WIP |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 申克楠
|  | 120 | Sorter Capability Set By Carrier Type | WIP |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 申克楠
|  | 121 | Sorter Capability Set By Wafer Kind | WIP |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 申克楠
| Data Collection | 122 | Adhoc Data Collection | WIP |  |  |  | AMAT |  | 无 | [9 empty] | 李彬
| Data Collection | 123 | Cancel ReSend To Spc | WIP |  |  |  | AMAT |  | 无 | [9 empty] | 李彬
| Data Collection | 124 | Non-Lot Data Collection | WIP |  |  |  | AMAT |  | 无 | [9 empty] | 李彬
| Data Collection | 125 | ReSend To Spc | WIP |  |  |  | AMAT |  | 无 | [9 empty] | 李彬
| Data Collection | 126 | YE SpecID Bincode Map | WIP |  |  |  | AMAT |  | 无 | [9 empty] | 李彬
| Data Collection | 127 | YE SpecID Bincode Map History | WIP |  |  |  | AMAT |  | 无 | [9 empty] | 李彬
| Data Collection | 128 | View Non Lot Dcoll Info | WIP |  |  |  | AMAT |  | 无 | [9 empty] | 李彬
CSN |  | 129 | Constraint | CSN |  |  |  | AMAT |  | 无 | [9 empty] | 申克楠
|  | 130 | Mfg Dispatch | CSN |  |  |  | AMAT |  | 无 | [9 empty] | 申克楠
|  | 131 | Parts Life Time Control | CSN |  |  |  | AMAT |  | 无 | [9 empty] | 申克楠
|  | 132 | CSN PPID Constraint | CSN |  |  |  | AMAT |  | 无 | [9 empty] | 李彬
|  | 133 | Restrict Duration Recipe | CSN |  |  |  | AMAT |  | 无 | [9 empty] | 申克楠
Test Wafer | NPW Grade | 134 | Downgrade Wafer Quantity Limit | Test Wafer | 次重点 | 未确定 | Phase2 | AMAT |  | 无 | [9 empty] | 童海潮
|  | 135 | Cancel Dummy In | Test Wafer | 次重点 | 未确定 | Phase2 | AMAT |  | 无 | [9 empty] | 童海潮
|  | 136 | Cancel Reserve Dummy | Test Wafer | 次重点 | 未确定 | Phase2 | AMAT |  | 无 | [9 empty] | 童海潮
|  | 137 | Configure Wafer Stock Level | Test Wafer | 次重点 | 未确定 | Phase2 | AMAT |  | 无 | [9 empty] | 童海潮
|  | 138 | Query Monitor Lot | Test Wafer | 重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | 查询Monitor Lot信息 | 童海潮 | 高毓 | 无锡 | 未完成 | 新增 | 2022-11-01 | [5 empty] | 2 | 2022-11-02 | 2022-11-03
|  | 139 | Reclaim End | Test Wafer | 次重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | NPW Lot重新进行Recycle | 童海潮 | 高毓 | 无锡 | 未完成 | 新增 | 2022-11-01 | [5 empty] | 3 | 2022-11-04 | 2022-11-06
|  | 140 | Re_Create Monitor Lot | Test Wafer | 重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | Pre Measure Fail后重新创建Monitor Lot | 童海潮 | 高毓 | 无锡 | 未完成 | 新增 | 2022-11-01 | [5 empty] | 5 | 2022-11-07 | 2022-11-11
|  | 141 | Reserve Dummy | Test Wafer | 次重点 | 未确定 | Phase2 | AMAT |  | 无 | [9 empty] | 童海潮
OCAP |  | 142 | Complete Double Confirm | OCAP |  |  |  | AMAT |  | 无 | [9 empty] | 李彬
PCMS | Activity | 143 | Change Location | PCMS | 次重点 | 未确定 | Phase2 | AMAT | Change Location | 无 | [9 empty] | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Activity | 144 | Complete Use for RunCard | PCMS | 次重点 | 未确定 | Phase2 | AMAT | Complete Use for RunCard | 无 | [9 empty] | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Activity | 145 | EE Hold Card | PCMS | 次重点 | 确定 | Phase2 | AMAT | EE Hold Card | 无 | [9 empty] | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Activity | 146 | EE Validation | PCMS | 次重点 | 未确定 | Phase2 | AMAT | EE Validation | 无 | [9 empty] | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Configuration | 147 | Equipment Capability With Probe Card Group | PCMS | 次重点 | 未确定 | Phase2 | AMAT | Equipment Capability With Probe Card Group | 无 | [9 empty] | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Activity | 148 | Lend Out | PCMS | 次重点 | 未确定 | Phase2 | AMAT | Lend Out | 无 | [9 empty] | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Activity | 149 | MFG Receive | PCMS | 次重点 | 确定 | Phase2 | AMAT | MFG Receive | 无 | [9 empty] | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Run Time | 150 | Mounting Of Probe Card | PCMS | 次重点 | 未确定 | Phase2 | AMAT | Mounting Of Probe Card | 无 | [9 empty] | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Configuration | 151 | Probe Card Group Maintenance | PCMS | 次重点 | 未确定 | Phase2 | AMAT | Probe Card Group Maintenance | 无 | [9 empty] | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Configuration | 152 | Probe Card Maintenance | PCMS | 次重点 | 未确定 | Phase2 | AMAT | Probe Card Maintenance | 无 | [9 empty] | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Activity | 153 | PE Hold Card | PCMS | 次重点 | 未确定 | Phase2 | AMAT | PE Hold Card | 无 | [9 empty] | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Activity | 154 | PE Validation | PCMS | 次重点 | 未确定 | Phase2 | AMAT | PE Validation | 无 | [9 empty] | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Activity | 155 | Probe Card History | PCMS | 次重点 | 确定 | Phase2 | AMAT | Probe Card History | 无 | [9 empty] | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Activity | 156 | Release To MFG | PCMS | 次重点 | 确定 | Phase2 | AMAT | Release To MFG | 无 | [9 empty] | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Configuration | 157 | RCP Probe Card Group Mapping | PCMS | 次重点 | 未确定 | Phase2 | AMAT | RCP Probe Card Group Mapping | 无 | [9 empty] | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Activity | 158 | Release for RunCard | PCMS | 次重点 | 确定 | Phase2 | AMAT | Release for RunCard | 无 | [9 empty] | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Activity | 159 | Remove From Inventory | PCMS | 次重点 | 未确定 | Phase2 | AMAT | Remove From Inventory | 无 | [9 empty] | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Activity | 160 | Return From Repair | PCMS | 次重点 | 未确定 | Phase2 | AMAT | Return From Repair | 无 | [9 empty] | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Activity | 161 | Return To Inventory | PCMS | 次重点 | 未确定 | Phase2 | AMAT | Return To Inventory | 无 | [9 empty] | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Activity | 162 | Return To PE | PCMS | 次重点 | 未确定 | Phase2 | AMAT | Return To PE | 无 | [9 empty] | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Activity | 163 | Scrap | PCMS | 次重点 | 未确定 | Phase2 | AMAT | Scrap | 无 | [9 empty] | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Configuration | 164 | Location Maintenance | PCMS | 次重点 | 未确定 | Phase2 | AMAT | Location Maintenance | 无 | [9 empty] | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Run Time | 165 | UnMounting Of Probe Card | PCMS | 次重点 | 未确定 | Phase2 | AMAT | UnMounting Of Probe Card | 无 | [9 empty] | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Activity | 166 | UnScrap | PCMS | 次重点 | 未确定 | Phase2 | AMAT | UnScrap | 无 | [9 empty] | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Activity | 167 | Send To Vendor Repair | PCMS | 次重点 | 未确定 | Phase2 | AMAT | Send To Vendor Repair | 无 | [9 empty] | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
PRMS | MainGUI | 168 | Manage Resist Equipment Alarm | PRMS |  |  | Phase2 | AMAT |  | 无 | [9 empty] | 杨金杰 | 郭天娇 | 无锡
| Configuration | 169 | PR Batch Assignment And Qualification | PRMS |  |  | Phase2 | AMAT |  | 无 | [9 empty] | 杨金杰 | 郭天娇 | 无锡
| Activity | 170 | Change Location | PRMS |  |  | Phase2 | AMAT |  | 无 | [9 empty] | 杨金杰 | 郭天娇 | 无锡
| Configuration | 171 | Location Maintenance | PRMS |  |  | Phase2 | AMAT |  | 无 | [9 empty] | 杨金杰 | 郭天娇 | 无锡
| Activity | 172 | Photo Resist Consumable Events | PRMS |  |  | Phase2 | AMAT |  | 无 | [9 empty] | 杨金杰 | 郭天娇 | 无锡
| Configuration | 173 | Photo Resist Equipment Maintenance | PRMS |  |  | Phase2 | AMAT |  | 无 | [9 empty] | 杨金杰 | 郭天娇 | 无锡
| Activity | 174 | Photo Resist History | PRMS |  |  | Phase2 | AMAT |  | 无 | [9 empty] | 杨金杰 | 郭天娇 | 无锡
| Configuration | 175 | Photo Resist Location Maintenance | PRMS |  |  | Phase2 | AMAT |  | 无 | [9 empty] | 杨金杰 | 郭天娇 | 无锡
| Configuration | 176 | Photo Resist Part Maintenance | PRMS |  |  | Phase2 | AMAT |  | 无 | [9 empty] | 杨金杰 | 郭天娇 | 无锡
| Configuration | 177 | PR Recipe | PRMS |  |  | Phase2 | AMAT |  | 无 | [9 empty] | 杨金杰 | 郭天娇 | 无锡
| Activity | 178 | PR Recipe History | PRMS |  |  | Phase2 | AMAT |  | 无 | [9 empty] | 杨金杰 | 郭天娇 | 无锡
| Configuration | 179 | Resist Consumables | PRMS |  |  | Phase2 | AMAT |  | 无 | [9 empty] | 杨金杰 | 郭天娇 | 无锡
PTMS | Create Part | 180 | Batch Create Part | PTMS | 重点 | 确定 | Phase2 | AMAT |  | 无 | [9 empty] | 罗涛 | 王华强 | 无锡 |  |  | 2023-02-01 | [5 empty] | 3
| Part Main GUI | 181 | Batch Create Part Master | PTMS | 重点 | 确定 | Phase2 | AMAT |  | 无 | [9 empty] | 罗涛 | 王华强 | 无锡 |  |  | 2023-02-01 | [5 empty] | 5
| Create Part | 182 | Create Part | PTMS | 重点 | 确定 | Phase2 | AMAT |  | 无 | [9 empty] | 罗涛 | 王华强 | 无锡 |  |  | 2023-02-01 | [5 empty] | 3
| Configuration | 183 | Cost Center | PTMS | 次重点 | 确定 | Phase2 | AMAT |  | 无 | [9 empty] | 罗涛 | 王华强 | 无锡 |  |  | 2023-02-01 | [5 empty] | 5
| Part Group Maintain | 184 | Modify Part Group Relationship | PTMS | 次重点 | 确定 | Phase2 | AMAT |  | 无 | [9 empty] | 罗涛 | 王华强 | 无锡 |  |  | 2023-02-01 | [5 empty] | 3
| Configuration | 185 | Part Cycle Limit | PTMS | 重点 | 确定 | Phase2 | AMAT |  | 无 | [9 empty] | 罗涛 | 王华强 | 无锡 |  |  | 2023-02-01 | [5 empty] | 3
| MainGUI | 186 | Part Main Screen View | PTMS | 重点 | 确定 | Phase2 | AMAT |  | 无 | [9 empty] | 罗涛 | 王华强 | 无锡 |  |  | 2023-02-01 | [5 empty] | 3
| Part Main GUI | 187 | Part Master MainGUI | PTMS | 次重点 | 确定 | Phase2 | AMAT |  | 无 | [9 empty] | 罗涛 | 王华强 | 无锡 |  |  | 2023-02-01 | [5 empty] | 5
| Replace Parts | 188 | Replace Parts | PTMS | 重点 | 确定 | Phase2 | AMAT |  | 无 | [9 empty] | 罗涛 | 王华强 | 无锡 |  |  | 2023-02-01 | [5 empty] | 5
| Part Group Maintain | 189 | Query Part Group Relationship | PTMS | 次重点 | 确定 | Phase2 | AMAT |  | 无 | [9 empty] | 罗涛 | 王华强 | 无锡 |  |  | 2023-02-01 | [5 empty] | 3
RTD |  | 190 | Maintain Mark Lot | RTD |  | 未确定 |  | AMAT |  | 无 | [9 empty] | 申克楠
Reticle | Maintain | 191 | Batch Reticle Properties | Reticle | 非重点 | 确定 | Phase2 | AMAT |  | 无 | [8 empty] | 同时变更多块Reticle属性 | 杨金杰 | 郭天娇 | 无锡
| Maintain | 192 | Batch IRIS Wafer Count | Reticle | 非重点 | 确定 | Phase2 | AMAT |  | 无 | [8 empty] | 同时变更多块Reticle IRIS 的Wafer Count | 杨金杰 | 郭天娇 | 无锡
| Maintain | 193 | Batch IRIS Wafer Count Import And Export | Reticle | 非重点 | 确定 | Phase2 | AMAT |  | 无 | [8 empty] | 同时导出输入多块Reticle IRIS的 Wafer Count | 杨金杰 | 郭天娇 | 无锡
| Maintain | 194 | Batch Pod Properties | Reticle | 非重点 | 确定 | Phase2 | AMAT |  | 无 | [8 empty] | 同时变更多个Pod 属性 | 杨金杰 | 郭天娇 | 无锡
| Maintain | 195 | Batch Starlight | Reticle | 非重点 | 确定 | Phase2 | AMAT |  | 无 | [8 empty] | 同时变更多块Reticle的Starlight | 杨金杰 | 郭天娇 | 无锡
| Maintain | 196 | Batch Wafer Count | Reticle | 非重点 | 确定 | Phase2 | AMAT |  | 无 | [8 empty] | 同时变更多块Reticle进行的Wafer Count | 杨金杰 | 郭天娇 | 无锡
| Maintain | 197 | Batch XCDA Qtime | Reticle | 非重点 | 确定 | Phase2 | AMAT |  | 无 | [8 empty] | 同时变更多块Reticle的XCDA Qtime | 杨金杰 | 郭天娇 | 无锡
| Maintain | 198 | Batch XCDA Qtime Import And Export | Reticle | 非重点 | 确定 | Phase2 | AMAT |  | 无 | [8 empty] | 同时导出输入多块Reticle的XCDA Qtime | 杨金杰 | 郭天娇 | 无锡
| Reticle Activity | 199 | Change Location | Reticle | 重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | 变更更Reticle Location | 杨金杰 | 郭天娇 | 无锡 |  |  | 2022-11-09 | [5 empty] | 3 | 2022-11-10 | 2022-11-13
| Maintain | 200 | Compatible Condition | Reticle | 重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | Pod,Retcile Match Conditiron设定 | 杨金杰 | 郭天娇 | 无锡
| Reticle Activity | 201 | Reticle Data Collection | Reticle |  |  |  | AMAT |  | 无 | [9 empty] | 李彬
| Create And Delete | 202 | Delete Reticle | Reticle | 重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | Delete 已经Create的Reticle | 杨金杰 | 郭天娇 | 无锡 |  |  | 2022-11-22 | [5 empty] | 3 | 2022-11-23 | 2022-11-26
| Reticle Activity | 203 | Inspection In | Reticle | 重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | 开始Inspeticon | 杨金杰 | 郭天娇 | 无锡 |  |  | 2022-11-15 | [5 empty] | 3 | 2022-11-16 | 2022-11-19
| Reticle Activity | 204 | Inspection Out | Reticle | 重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | Inspection结束 | 杨金杰 | 郭天娇 | 无锡 |  |  | 2022-11-15 | [5 empty] | 3 | 2022-11-16 | 2022-11-19
| Maintain | 205 | IRIS Wafer Count | Reticle | 重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | 变更IRIS的Wafer Count | 杨金杰 | 郭天娇 | 无锡 |  |  | 2022-11-22 | [5 empty] | 3 | 2022-11-23 | 2022-11-26
| Reticle Activity | 206 | Load Reticle | Reticle | 重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | EAP未适用时，Load Reticle到机台 | 杨金杰 | 郭天娇 | 无锡 |  |  | 2022-11-15 | [5 empty] | 3 | 2022-11-16 | 2022-11-19
| Maintain | 207 | Maintain Equipment Type | Reticle | 重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | 变更Reticle的属性（Reticle Spec),涉及Reticle的各种Limit值 | 杨金杰 | 郭天娇 | 无锡 |  |  | 2022-11-22 | [5 empty] | 3 | 2022-11-23 | 2022-11-26
| Maintain | 208 | Maintain Reticle Location | Reticle | 重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | 变更Reticle 的Locaiton属性 | 杨金杰 | 郭天娇 | 无锡 |  |  | 2022-11-09 | [5 empty] | 3 | 2022-11-10 | 2022-11-13
| Maintain | 209 | Maintain Reticle LocationType | Reticle | 重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | 变更Reticle的 Locaiton Type | 杨金杰 | 郭天娇 | 无锡 |  |  | 2022-11-09 | [5 empty] | 3 | 2022-11-10 | 2022-11-13
| Maintain | 210 | Maintain Reticle Grade | Reticle | 次重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | 变更Reticle Grade与IRIS DC等相关联 | 杨金杰 | 郭天娇 | 无锡 |  |  | 2022-11-22 | [5 empty] | 3 | 2022-11-23 | 2022-11-26
| Maintain | 211 | Mask Clean | Reticle | 重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | 设定Reticle Clean | 杨金杰 | 郭天娇 | 无锡 |  |  | 2022-11-15 | [5 empty] | 3 | 2022-11-16 | 2022-11-19
| Reticle Activity | 212 | Modify Attribute | Reticle | 次重点 | 确定 | Phase1 | AMAT |  | 无 | [9 empty] | 杨金杰 | 郭天娇 | 无锡 |  |  | 2022-11-22 | [5 empty] | 3 | 2022-11-23 | 2022-11-26
| Reticle Activity | 213 | Offline Retrieve Reticle | Reticle | 次重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | Offline接收Reticle | 杨金杰 | 郭天娇 | 无锡 |  |  | 2022-11-29 | [5 empty] | 3 | 2022-11-30 | 2022-12-03
| Pod Activity | 214 | Change Location | Reticle | 重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | Change Pod的Location | 杨金杰 | 郭天娇 | 无锡 |  |  | 2022-11-09 | [5 empty] | 3 | 2022-11-10 | 2022-11-13
| Pod Activity | 215 | Confirm Quality | Reticle | 非重点 | 确定 | Phase2 | AMAT |  | 无 | [8 empty] | Pod Inline时的 Qulity Check | 杨金杰 | 郭天娇 | 无锡
| Create And Delete | 216 | Pod Mgt | Reticle | 次重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | Pod 管理？？ | 杨金杰 | 郭天娇 | 无锡 |  |  | 2022-11-29 | [5 empty] | 3 | 2022-11-30 | 2022-12-03
| Maintain | 217 | Remount And Clean Count | Reticle | 重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | 变更Reticle Clean Count | 杨金杰 | 郭天娇 | 无锡 |  |  | 2022-11-22 | [5 empty] | 3 | 2022-11-23 | 2022-11-26
| Reticle Activity | 218 | Request Inspection | Reticle | 重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | 设置Pod Inspection | 杨金杰 | 郭天娇 | 无锡 |  |  | 2022-11-15 | [5 empty] | 3 | 2022-11-16 | 2022-11-19
| Pod Activity | 219 | Reserve POD | Reticle | 非重点 | 确定 | Phase2 | AMAT |  | 无 | [9 empty] | 杨金杰 | 郭天娇 | 无锡
| Reticle Activity | 220 | Cancel Scan | Reticle | 重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | Cancel 已经开始Scan的操作 | 杨金杰 | 郭天娇 | 无锡 |  |  | 2022-11-15 | [5 empty] | 3 | 2022-11-16 | 2022-11-19
| Reticle Activity | 221 | Return To Customer | Reticle | 重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | 退回客户中心 | 杨金杰 | 郭天娇 | 无锡 |  |  | 2022-11-29 | [5 empty] | 3 | 2022-11-30 | 2022-12-03
| Reticle Activity | 222 | Terminate | Reticle | 重点 | 确定 | Phase1 | AMAT |  | 无 | [8 empty] | 终结Reticle(不再使用）？ | 杨金杰 | 郭天娇 | 无锡 |  |  | 2022-11-29 | [5 empty] | 3 | 2022-11-30 | 2022-12-03
| Reticle Activity | 223 | Unload Reticle | Reticle | 非重点 | 确定 | Phase2 | AMAT |  | 无 | [8 empty] | EAP未使用时，Unload Reticle的电算操作 | 杨金杰 | 郭天娇 | 无锡
| Reticle Activity | 224 | Batch XCDA Purge Time Remove | Reticle | 非重点 | 确定 | Phase2 | AMAT |  | 无 | [8 empty] | 消除多个Reticle的 XCDA Purge Time | 杨金杰 | 郭天娇 | 无锡
| Reticle Activity | 225 | Batch XCDA Qtime Remove | Reticle | 非重点 | 确定 | Phase2 | AMAT |  | 无 | [8 empty] | 消除多个Reticle的 XCDA Qtime | 杨金杰 | 郭天娇 | 无锡
Sampling |  | 226 | Step Sampling | Sampling |  | 确定 | Phase1 | AMAT | Step Sampling | 无 | [8 empty] | Step Sampling 主页，展示 Product Name + Top Plan Name + Subplan Name + StepSeq + Step ID + Capability相关的Sampling信息。不支持ADD/DEL ，只可以修改。新建由Default Sampling导入 | 申克楠
|  | 227 | Default Sampling | Sampling |  | 确定 | Phase1 | AMAT | Default Sampling | 无 | [8 empty] | 作为创建Step Sampling 的默认值设置。包含WaferSelection Rule | 申克楠
|  | 228 | YE Step Sampling | Sampling |  | 确定 | Phase1 | AMAT | YE Step Sampling | 有 | [8 empty] | YE Step Sampling 主页，创建修改规则。配置属性。 | 申克楠
|  | 229 | Modify Key Lot Flag | Sampling |  | 确定 | Phase2 | AMAT | Modify Key Lot Flag | 无 | [8 empty] | 针对YE Key EQP 解绑Key Lot，系统重新选择其它Key Lot | 申克楠
|  | 230 | Lot Sampling Runtime History | Sampling |  | 确定 | Phase1 | AMAT | Lot Sampling Runtime History | 无 | [8 empty] | YE or Step Sampling history，需要支持导出Excel功能 | 申克楠
|  | 231 | Smart Sampling Special Flag | Sampling |  | 确定 | Phase2 | AMAT | Smart Sampling Special Flag | 无 | [8 empty] | 针对Key EQP 删除/添加 非YE Step Sampling Key Lot | 申克楠
|  | 232 | Smart Sampling Key Equipment | Sampling |  | 确定 | Phase1 | AMAT | Smart Sampling Key Equipment | 无 | [8 empty] | 非YE Step Key EQP 设置 | 申克楠
|  | 233 | Smart Sampling Key Step Association | Sampling |  | 确定 | Phase1 | AMAT | Smart Sampling Key Step Association | 无 | [8 empty] | Process Step 绑定非YE 量测 Step 关系 | 申克楠
| Sampling History | 234 | Smart Sampling MFG Skip History | Sampling |  | 确定 | Phase2 | AMAT | Smart Sampling MFG Skip History | 无 | [8 empty] | Smart Sampling Special Scan modeling history | 申克楠
|  | 235 | YE Key Equipment | Sampling |  | 确定 | Phase1 | AMAT | YE Key Equipment | 无 | [8 empty] | YE Step Key EQP 设置 | 申克楠
|  | 236 | YE Key Step Association | Sampling |  | 确定 | Phase1 | AMAT | YE Key Step Association | 无 | [8 empty] | Process Step 绑定 YE Step 关系 | 申克楠
|  | 237 | YE Step By Flow | Sampling |  | 确定 | Phase2 | AMAT | YE Step By Flow | 无 | [8 empty] | 针对Product ，Plan，选择Step 配置Sampling 规则 | 申克楠
|  | 238 | YE Step By Lot | Sampling |  | 确定 | Phase2 | AMAT | YE Step By Lot | 无 | [8 empty] | 根据lot设置YE Step 的Skip/Scan | 申克楠
| Sampling History | 239 | YE Step Sampling History | Sampling |  | 确定 | Phase2 | AMAT | YE Step Sampling History | 无 | [8 empty] | YE Step Sampling 历史记录 | 申克楠
Transportation |  | 240 | Cancel Reticle Transportation | Transportation |  | 未确定 | Phase2 | AMAT |  | 无 | [9 empty] | 罗涛
|  | 241 | Cancel Transportation | Transportation |  | 未确定 | Phase2 | AMAT |  | 无 | [9 empty] | 罗涛
| MCS Control | 242 | Reticle Transportation Request | Transportation |  | 未确定 | Phase2 | AMAT |  | 无 | [9 empty] | 罗涛
| MCS Control | 243 | Reticle Sync Stocker | Transportation |  | 未确定 | Phase2 | AMAT |  | 无 | [9 empty] | 罗涛
|  | 244 | MCS Inventory Info | Transportation |  | 未确定 | Phase2 | AMAT |  | 无 | [9 empty] | 罗涛
|  | 245 | Sync Reticle Stocker | Transportation |  | 未确定 | Phase2 | AMAT |  | 无 | [9 empty] | 罗涛
|  | 246 | Transportation Reticle Request | Transportation |  | 未确定 | Phase2 | AMAT |  | 无 | [9 empty] | 罗涛
|  | 247 | View Reticle Stocker | Transportation |  | 未确定 | Phase2 | AMAT |  | 无 | [9 empty] | 罗涛
|  | 248 | Sync Carrier Info | Transportation |  | 未确定 | Phase2 | AMAT |  | 无 | [9 empty] | 罗涛
|  | 249 | Transportation Request | Transportation |  | 未确定 | Phase2 | AMAT |  | 无 | [9 empty] | 罗涛
|  | 250 | Transportation Recovery | Transportation |  | 未确定 | Phase2 | AMAT |  | 无 | [9 empty] | 罗涛
WAT | Wafer Test | 251 | WAT Hold Information | WAT | 次重点 | 未确定 | Phase2 | AMAT | WAT Hold Information | 无 | [9 empty] | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Wafer Test | 252 | WAT Result Information | WAT | 次重点 | 未确定 | Phase2 | AMAT | WAT Result Information | 无 | [9 empty] | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Wafer Test | 253 | Final InkMap Prod Setting | WAT | 次重点 | 未确定 | Phase2 | AMAT | Final InkMap Prod Setting | 无 | [9 empty] | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Wafer Test | 254 | Wafer Test Information | WAT | 次重点 | 未确定 | Phase2 | AMAT | Wafer Test Information | 无 | [9 empty] | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Wafer Test | 255 | Wafer Test Result History | WAT | 次重点 | 未确定 | Phase2 | AMAT | Wafer Test Result History | 无 | [9 empty] | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Wafer Test | 256 | WT Product Yield Setting | WAT | 次重点 | 未确定 | Phase2 | AMAT | WT Product Yield Setting | 无 | [9 empty] | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Wafer Test | 257 | WT Retest Recipe Setting | WAT | 次重点 | 未确定 | Phase2 | AMAT | WT Retest Recipe Setting | 无 | [9 empty] | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
| Wafer Test | 258 | WT Test Step Recipe Configuration | WAT | 次重点 | 未确定 | Phase2 | AMAT | WT Test Step Recipe Configuration | 无 | [9 empty] | 陈永伟 | 秦亮 | 无锡 | 未完成 | 新增
Formulas:
PlanStart = [设计评审计划]+1
PlanStart = [PlanEnd, row above]+1
PlanEnd = [PlanStart]+[开发改善 Day]
PlanEnd = [PlanStart]+[开发改善 Day]-1

## Summary
* cvMES Function List R&D Status(对比 300Works Basic Function)
Type | 300Works(Basic) | B2 Funcation(Basic) | 完成 | 完成率
|  |  |  | 对比300works | 对比B2 | 完成 | 设计中 | 开发中 | 测试中 | 未推进 | 待确认
Carrier | 29 | 0 | 18 | 62.07% | #DIV/0! | 18 | 1 | 1 | 0 | 0 | 3
Machine | 37 | 0 | 12 | 32.43% | #DIV/0! | 12 | 0 | 0 | 0 | 0 | 0
Lot | 105 | 0 | 80 | 76.19% | #DIV/0! | 78 | 0 | 0 | 0 | 0 | 2
Inventory | 10 | 0 | 10 | 100% | #DIV/0! | 10 | 0 | 0 | 0 | 0 | 0
WIP | 66 | 0 | 59 | 89.39% | #DIV/0! | 52 | 0 | 2 | 0 | 1 | 1
CSN | 6 | 3 | 3 | 50% | 100% | 3 | 0 | 0 | 0 | 0 | 0
Test Wafer | 23 | 0 | 23 | 100% | #DIV/0! | 23 | 0 | 0 | 0 | 0 | 0
Reticle | 63 | 0 | 30 | 47.62% | #DIV/0! | 30 | 0 | 0 | 0 | 0 | 2
Sampling | 16 | 0 | 10 | 62.5% | #DIV/0! | 10 | 0 | 0 | 2 | 0 | 0
Phase1 | 355 | 3 | 245 | 69.01% | 8167% | 236 | 1 | 3 | 2 | 1 | 8
OCAP | 2 | 0 | 1 | 50% | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0
PCMS | 36 | 0 | 0 | 0% | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0
PRMS | 12 | 0 | 0 | 0% | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0
PTMS | 10 | 0 | 0 | 0% | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0
RTD | 1 | 0 | 0 | 0% | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0
Transportation | 11 | 0 | 0 | 0% | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0
WAT | 12 | 0 | 0 | 0% | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0
Phase2 | 84 | 0 | 1 | 1.19% | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0
Total | 439 | 3 | 246 | 56.04% | 8200% | 236 | 1 | 3 | 2 | 1 | 8

## cvMES Function List 定义
* Cpwin（MES）Function List
|  |  | Level1 | Level2 | No. | 300Works(Basic) | B2 Funcation | cvMES | 模块 | 功能确认 | 开发阶段 | 界面说明 | 责任人 | 开发地 | 开发人 | 交期 | 实绩 | 完成 | Remark
11 | 1 | 1 | Carrier Mgt |  | 1 | Add Carrier Comment |  | Add Carrier Comment | Carrier | 设计中 | 2022 | 添加Carrier Comment | 杨金杰
11 | 1 | 1 |  |  | 2 | Assign Carrier |  | Assign Carrier | Carrier | 完成 | 2022 | Lot&Carrier逻辑 Match | 杨金杰
1 |  | 1 |  |  | 3 |  |  | Deassign Carrier | Carrier | 完成 | 2022 | Lot&Carrier逻辑 Divide | 杨金杰
11 | 1 | 1 |  |  | 4 | Cancel Clean |  | Cancel Clean | Carrier | 待确认 | 2022 | Cancel Set Clean,Cancel Start Clean | 杨金杰
1 | 1 |  |  |  | 5 | Cancel Inspection |  |  | Carrier | 未推进 | 2022 |  | 杨金杰
11 | 1 | 1 |  |  | 6 | Cancel Reserve Target Carrier |  | Cancel Reserve Target Carrier | Carrier | 完成 | 2022 | 解绑预约Carrier,其他用途可以使用 | 杨金杰
1 | 1 |  |  |  | 7 | Carrier Data Collection |  |  | Carrier | 待确认 | 2022 |  | 李彬
11 | 1 | 1 |  | Update/Modify Carrier Info | 8 | Change Slotmap Info |  | Change Slot Map Info | Carrier | 完成 | 2022 | 改变同lot中 wafer slot信息 | 杨金杰
1 |  | 1 |  |  | 9 |  |  | Change Carrier Info | Carrier | 完成 | 2022 |  | 杨金杰
11 | 1 | 1 |  |  | 10 | Create Carrier |  | Create Carrier | Carrier | 完成 | 2022 | 单个或多个Carrier创建（包括Foup.FOSB) | 杨金杰
1 | 1 |  |  |  | 11 | Disposal/Undo Disposal |  |  | Carrier | 未推进 | 2022 |  | 杨金杰
11 | 1 | 1 |  |  | 12 | Exchange Carrier |  | Exchange Carrier | Carrier | 完成 | 2022 | Carrier为基准，Lot逐个传出到新的异种Foup | 杨金杰
11 | 1 | 1 |  |  | 13 | Hold Carrier |  | Hold Carrier | Carrier | 完成 | 2022 | Hold Carrier | 杨金杰
1 | 1 |  |  |  | 14 | Inspection Flow Control |  |  | Carrier | 未推进 | 2022 |  | 杨金杰
11 | 1 | 1 |  | Update/Modify Carrier Info | 15 | Modify Carrier Attributes |  | Modify Carrier Attributes | Carrier | 完成 | 2022 |  | 杨金杰
1 | 1 |  |  |  | 16 | Start/End Inspection |  |  | Carrier | 未推进 | 2022 |  | 杨金杰
11 | 1 | 1 |  |  | 17 | Release Carrier |  | Release Carrier | Carrier | 完成 | 2022 | 对Hold Carrier进行Release | 杨金杰
11 | 1 | 1 |  |  | 18 | Remove Carrier |  | Scrap Carrier | Carrier | 完成 | 2022 | 报废Carrier | 杨金杰
1 | 1 |  |  |  | 19 | Repair FOUP |  |  | Carrier | 未推进 | 2022 |  | 杨金杰
11 | 1 | 1 |  |  | 20 | Reserve Target Carrier |  | Reserve Target Carrier | Carrier | 开发中 | 2022 | 预约Carrier,防止其他用途使用 | 杨金杰
1 | 1 |  |  |  | 21 | Set Disposal/Cancel Disposal |  |  | Carrier | 未推进 | 2022 |  | 杨金杰
1 |  | 1 |  |  | 22 |  |  | Cancel Scrap Carrier | Carrier | 完成 | 2022 | 解除报废Carrier | 杨金杰
1 |  | 1 |  |  | 23 |  |  | Change Carrier Clean State | Carrier | 完成 | 2022 |  | 杨金杰
1 |  | 1 |  |  | 24 |  |  | Carrier RFID Management | Carrier | 完成 | 2022 |  | 杨金杰
11 | 1 | 1 |  |  | 25 | Set Clean |  | Set Clean | Carrier | 待确认 | 2022 |  | 杨金杰
1 | 1 |  |  |  | 26 | Set Inspection |  |  | Carrier | 未推进 | 2022 |  | 杨金杰
1 | 1 |  |  |  | 27 | Special Transfer Lot |  |  | Carrier | 未推进 | 2022 |  | 杨金杰
11 | 1 | 1 |  |  | 28 | Start/End Clean |  | Start/End Clean | Carrier | 待确认 | 2022 |  | 杨金杰
11 | 1 | 1 |  |  | 29 | Transfer Lot |  | Transfer Lot | Carrier | 完成 | 2022 | Lot Base 传到其他同类型Foup | 杨金杰
1 | 1 |  |  |  | 30 | Update Carrier Component |  |  | Carrier | 未推进 | 2022 |  | 杨金杰
1 |  | 1 |  |  | 31 |  |  | View Carrier List | Carrier | 完成 | 2022 |  | 杨金杰
1 | 1 |  |  | View Carrier Info | 32 | View Carrier Cleaning History |  |  | Carrier | 未推进 | 2022 |  | 杨金杰
1 | 1 |  |  | View Carrier Info | 33 | View Carrier Cycle |  |  | Carrier | 未推进 | 2022 |  | 杨金杰
11 | 1 | 1 |  | View Carrier Info | 34 | View Carrier History |  | View Carrier History | Carrier | 完成 | 2022 | 查询Carrier的Detail 历史记录 | 杨金杰
11 | 1 | 1 |  | View Carrier Info | 35 | View Carrier Status |  | View Carrier Status | Carrier | 完成 | 2022 | 查询Carrier 当前状态 | 杨金杰
1 | 1 |  | Eqp Mgt |  | 36 | Buffer Tool Physical Foup Maintain |  |  | Machine | 未推进 | 2022 |  | 杨金杰
1 | 1 |  |  | One Key Touch | 37 | Control Action History |  |  | Machine | 未推进 | 2022 |  | 杨金杰
1 | 1 |  |  |  | 38 | Customize EQP Information |  |  | Machine | 未推进 | 2022 |  | 杨金杰
1 | 1 |  |  |  | 39 | Delete Chamber Current Lots |  |  | Machine | 未推进 | 2022 |  | 杨金杰
11 | 1 | 1 |  |  | 40 | Equipment AMA Mode Change |  | Change Machine AMA Mode | Machine | 完成 | 2022 |  | 杨金杰
1 | 1 |  |  |  | 41 | Equipment Couple Port |  |  | Machine | 未推进 | 2022 |  | 杨金杰
1 | 1 |  |  |  | 42 | EQP Manual Process Configuration |  |  | Machine | 未推进 | 2022 |  | 杨金杰
11 | 1 | 1 |  |  | 43 | Equipment Port State Change |  | Change Port State | Machine | 完成 | 2022 |  | 杨金杰
11 | 1 | 1 |  |  | 44 | Equipment Process History |  | View Machine Process History | Machine | 完成 | 2022 |  | 杨金杰
11 | 1 | 1 |  |  | 45 | Equipment State Change |  | Change Machine State | Machine | 完成 | 2022 | 更改Machine Up,Down等信息 及Outof Service等信息变更 | 杨金杰
1 | 1 |  |  |  | 46 | MFG Eqp Security Control Maintenance |  |  | Machine | 未推进 | 2022 |  | 杨金杰
1 | 1 |  |  |  | 47 | Modify Equipment Attribute |  |  | Machine | 未推进 | 2022 |  | 杨金杰
1 | 1 |  |  |  | 48 | Modify Eqp Chamber Run Count |  |  | Machine | 未推进 | 2022 |  | 杨金杰
1 | 1 |  |  |  | 49 | Modify Equipment Current Lots |  |  | Machine | 未推进 | 2022 |  | 杨金杰
1 | 1 |  |  |  | 50 | Set Equipment Capability |  |  | Machine | 未推进 | 2022 |  | 杨金杰
1 |  | 1 |  |  | 51 |  |  | Change Machine Control Mode | Machine | 完成 | 2022 |  | 杨金杰
1 | 1 |  |  | One Key Touch | 52 | One Key Touch |  |  | Machine | 未推进 | 2022 |  | 杨金杰
1 | 1 |  |  | One Key Touch | 53 | One Key Touch Detail History |  |  | Machine | 未推进 | 2022 |  | 杨金杰
11 | 1 | 1 |  |  | 54 | Equipment Port Access Mode Change |  | Change Port Access Mode | Machine | 完成 | 2022 |  | 杨金杰
1 | 1 |  |  | One Key Touch | 55 | Power Source Setup |  |  | Machine | 未推进 | 2022 |  | 杨金杰
1 | 1 |  |  | One Key Touch | 56 | Power Source Setup History |  |  | Machine | 未推进 | 2022 |  | 杨金杰
1 | 1 |  |  |  | 57 | Reticle Equipment Process History |  |  | Machine | 未推进 | 2022 |  | 杨金杰
1 | 1 |  |  |  | 58 | Set Chamber Capability |  |  | Machine | 未推进 | 2022 |  | 杨金杰
1 | 1 |  |  | Tank Control | 59 | Tank Count Info |  |  | Machine | 未推进 | 2023 1Q |  | 杨金杰
1 | 1 |  |  | Tank Control | 60 | Tank OOS History |  |  | Machine | 未推进 | 2023 1Q |  | 杨金杰
1 | 1 |  |  | Tank Control | 61 | Tank Running History |  |  | Machine | 未推进 | 2023 1Q |  | 杨金杰
1 | 1 |  |  |  | 62 | Tool Recovery Control System |  |  | Machine | 未推进 | 2022 |  | 杨金杰
1 | 1 |  |  |  | 63 | Tool Recovery Package Setup |  |  | Machine | 未推进 | 2022 |  | 杨金杰
11 | 1 | 1 |  |  | 64 | View Equipment Auto Mode |  | View Machine Auto Mode | Machine | 完成 | 2022 |  | 杨金杰
11 | 1 | 1 |  |  | 65 | Equipment History |  | View Machine History | Machine | 完成 | 2022 | 查询Machine 的Detail 历史记录 | 杨金杰
11 | 1 | 1 |  |  | 66 | View Equipment Status |  | View Machine Status | Machine | 完成 | 2022 | 查询 Machine 的当前状态 | 杨金杰
1 | 1 |  |  | Tank Control | 67 | Wet Tank Control |  |  | Machine | 未推进 | 2023 1Q |  | 杨金杰
1 | 1 |  |  | PMS | 68 | Arrange PM |  |  | Machine | 未推进 | 2023 1Q |  | 杨金杰
1 | 1 |  |  | PMS | 69 | Conditional PM |  |  | Machine | 未推进 | 2023 1Q |  | 杨金杰
1 | 1 |  |  | PMS | 70 | Trigger Readings |  |  | Machine | 未推进 | 2023 1Q |  | 杨金杰
1 | 1 |  |  | PMS | 71 | Usage Meter |  |  | Machine | 未推进 | 2023 1Q |  | 杨金杰
1 |  | 1 |  |  | 72 |  |  | View Current Alarm | Machine | 完成 | 2022 | 根据Lot、Machine、时间等查询Alarm信息 | 杨金杰
1 |  | 1 |  |  | 73 |  |  | AlarmRun | Machine | 完成 | 2022 |  | 杨金杰
1 |  | 1 |  |  | 74 |  |  | View Machine Info | Machine | 完成 | 2022 |  | 杨金杰
1 | 1 |  |  | Tank Control | 75 | Tank Count Info |  |  | Machine | 未推进 | 2023 1Q |  | 杨金杰
1 | 1 |  |  | Tank Control | 76 | Tank Running History |  |  | Machine | 未推进 | 2023 1Q |  | 杨金杰
11 | 1 | 1 | Lot Customization |  | 77 | Modify Lot Contamination Level |  | Modify Lot Contamination Level | Lot | 完成 | 2022 | 修改lot污染等级 | 罗涛
11 | 1 | 1 |  |  | 78 | Add Steps |  | Add Steps | Lot | 完成 | 2022 | Add Steps | 罗涛
11 | 1 | 1 |  |  | 79 | Batch Modify Lot Attribute |  | Batch Modify Lot Attribute | Lot | 完成 | 2022 | 批量修改lot属性 | 罗涛
1 | 1 |  |  | Reassign | 80 | Change Sales Order |  |  | Lot | 待确认 | 2022 |  | 罗涛
1 | 1 |  |  | FeedForward Attribute | 81 | Copy FeedForward Information |  |  | Lot | 未推进 | 2022 |  | 罗涛
1 | 1 |  |  | FeedForward Attribute | 82 | Delete FeedForward Information |  |  | Lot | 未推进 | 2022 |  | 罗涛
11 | 1 | 1 |  |  | 83 | Modify Lot Attribute For MFG |  | Modify Lot Attribute For MFG | Lot | 完成 | 2022 | 修改lot属性for MFG | 罗涛
11 | 1 | 1 |  |  | 84 | Modify Lot Attribute For QC |  | Modify Lot Attribute For QC | Lot | 完成 | 2022 | 修改lot属性for QC | 罗涛
1 | 1 |  |  |  | 85 | Modify Lot Attribute For QE |  |  | Lot | 未推进 | 2022 |  | 罗涛
1 | 1 |  |  |  | 86 | Lot Specialization |  |  | Lot | 未推进 | 2022 |  | 罗涛
1 | 1 |  |  | FeedForward Attribute | 87 | Modify FeedForward Information |  |  | Lot | 未推进 | 2022 |  | 罗涛
11 | 1 | 1 |  |  | 88 | Modify Lot Attribute |  | Modify Lot Attribute | Lot | 完成 | 2022 | 修改lot属性 | 罗涛
11 | 1 | 1 |  | Reassign | 89 | Plan Reassign |  | Future Reassign | Lot | 完成 | 2022 |  | 罗涛
1 | 1 |  |  |  | 90 | Modify Potential Attribute |  |  | Lot | 未推进 | 2022 |  | 罗涛
11 | 1 | 1 |  | Reassign | 91 | Reassign Lot |  | Reassign Lot | Lot | 完成 | 2022 | Reassign Lot to New Product Flow | 罗涛
11 | 1 | 1 |  | Reassign | 92 | Reassign Lot For Monitor |  | Reassign Lot For NPW | Lot | 完成 | 2022 |  | 罗涛
1 | 1 |  |  |  | 93 | Maintain RMS Flag |  |  | Lot | 未推进 | 2022 |  | 罗涛
1 | 1 |  |  |  | 94 | Set Stepper |  |  | Lot | 未推进 | 2022 |  | 罗涛
1 | 1 |  |  |  | 95 | Undo Finish |  |  | Lot | 未推进 | 2022 |  | 罗涛
1 | 1 |  |  |  | 96 | Choose Alter Step |  |  | Lot | 未推进 | 2022 |  | 罗涛
11 | 1 | 1 | Lot Mgt |  | 97 | View Hold Lot |  | View Hold Lot Info | Lot | 完成 | 2022 |  | 罗涛
11 | 1 | 1 |  | Hold | 98 | Batch Hold |  | Batch Hold | Lot | 完成 | 2022 | 根据 PFO,Capability, Stage 等条件查询 Lot List, 批量锁定 | 罗涛
11 | 1 | 1 |  |  | 99 | Edit Hold Comment |  | Edit Hold | Lot | 完成 | 2022 | 更改Hold 信息 | 罗涛
11 | 1 | 1 |  | Hold | 100 | Hold |  | Hold Lot | Lot | 完成 | 2022 | 锁住Lot（Lot Hold State N->Y），提供 By Lot,Carrier,Batch ID 3种方法 | 罗涛
11 | 1 | 1 |  | Release | 101 | Release |  | Release Lot | Lot | 完成 | 2022 | 解锁Lot（Lot Hold State Y->N） | 罗涛
1 |  | 1 |  |  | 102 |  |  | Release Action | Lot | 完成 | 2022 |  | 罗涛
1 | 1 |  |  | MixRun | 103 | View Mix Run Status |  |  | Lot | 未推进 | 2022 |  | 罗涛
1 | 1 |  |  | Auto YE Review Wafer Selection Config | 104 | Wafer Selection History For Auto YE Review |  |  | Lot | 未推进 | 2022 |  | 罗涛
1 | 1 |  |  | Auto YE Review Wafer Selection Config | 105 | Update Wafer List Of YE Review |  |  | Lot | 未推进 | 2022 |  | 罗涛
1 | 1 |  |  | Auto YE Review Wafer Selection Config | 106 | Setting By Capability |  |  | Lot | 未推进 | 2022 |  | 罗涛
1 | 1 |  |  | Auto YE Review Wafer Selection Config | 107 | Setting By Product |  |  | Lot | 未推进 | 2022 |  | 罗涛
1 | 1 |  |  | Wafer Randomization | 108 | Adhoc Recover |  |  | Lot | 未推进 | 2022 |  | 罗涛
1 | 1 |  |  | Reposition | 109 | Back Up Step |  |  | Lot | 未推进 | 2022 |  | 罗涛
11 | 1 | 1 |  | Release | 110 | Batch Release |  | Batch Release | Lot | 完成 | 2022 | 批量解锁Lot（Lot Hold State Y->N） | 罗涛
1 | 1 |  |  | Wafer Randomization | 111 | Config Random Recipe |  |  | Lot | 未推进 | 2022 |  | 罗涛
1 | 1 |  |  | Wafer Randomization | 112 | Lot Random History |  |  | Lot | 未推进 | 2022 |  | 罗涛
1 | 1 |  |  | Pilot | 113 | Add Measurement Step |  |  | Lot | 完成 | 2022 |  | 罗涛/李彬
11 | 1 | 1 |  | Pilot | 114 | Create Pilot |  | Create Pi Lot | Lot | 完成 | 2022 |  | 罗涛
11 | 1 | 1 |  | Pilot | 115 | End Pilot |  | End PiLot | Lot | 完成 | 2022 |  | 罗涛
1 | 1 |  |  | Doma Management | 116 | Doma Path Config History |  |  | Lot | 未推进 | 2022 |  | 罗涛
1 | 1 |  |  | Doma Management | 117 | Doma Path Maintain |  |  | Lot | 未推进 | 2022 |  | 罗涛
1 | 1 |  |  | Doma Management | 118 | Doma Path Setting |  |  | Lot | 未推进 | 2022 |  | 罗涛
1 | 1 |  |  | Doma Management | 119 | DOMA RCD History |  |  | Lot | 未推进 | 2022 |  | 罗涛
11 | 1 | 1 |  | Future | 120 | Batch Future Hold |  | Batch Future Hold | Lot | 完成 | 2022 |  | 罗涛
11 | 1 | 1 |  | Future | 121 | Cancel Batch Future Hold |  | Future Action List | Lot | 完成 | 2022 |  | 罗涛
11 | 1 | 1 |  | Future | 122 | Cancel Future Action |  | Future Action List | Lot | 完成 | 2022 |  | 罗涛
11 | 1 | 1 |  | Future | 123 | Future Hold |  | Set Future Hold | Lot | 完成 | 2022 |  | 罗涛
1 | 1 |  |  | Future | 124 | Future Hold By Customer |  |  | Lot | 未推进 | 2022 |  | 罗涛
11 | 1 | 1 |  | Future | 125 | Future Merge |  | Set Future Merge | Lot | 完成 | 2022 |  | 罗涛
11 | 1 | 1 |  | Future | 126 | Future Split |  | Set Future Split | Lot | 完成 | 2022 |  | 罗涛
1 | 1 |  |  | Future | 127 | Set Future Hold Step Group |  |  | Lot | 未推进 | 2022 |  | 罗涛
1 |  | 1 |  | Future | 128 |  |  | Future Reserve Machine | Lot | 完成 | 2022 | 提前设置需要在后续 Step 做的机台 | 罗涛
1 | 1 |  |  | SML | 129 | Inline Split For Special Lot |  |  | Lot | 未推进 | 2022 |  | 杨金杰
11 | 1 | 1 |  | SML | 130 | Inline Split Setting |  | Inline Split Setting | Lot | 完成 | 2022 |  | 杨金杰
1 | 1 |  |  | Doma Management | 131 | Lot Doma History |  |  | Lot | 未推进 | 2022 |  | 罗涛
11 | 1 | 1 |  | Sorter | 132 | View Wafer Verification Result |  | View Wafer Verification Result | Lot | 完成 | 2022 | 查询 Sorter 读取的Wafer 的T7 Code 结果 | 杨金杰
11 | 1 | 1 |  | Sorter | 133 | Wafer Rotate |  | Wafer Rotate | Lot | 完成 | 2022 | 对Carrier中Wafer转角度 | 杨金杰
11 | 1 | 1 |  | Sorter | 134 | Wafer Verification |  | Wafer Verification | Lot | 完成 | 2022 |  | 杨金杰
1 |  | 1 |  | Sorter | 135 |  |  | Transfer Lot | Lot | 完成 | 2022 |  | 杨金杰
11 | 1 | 1 |  | Merge/Split | 136 | Merge |  | Merge Lot | Lot | 完成 | 2022 | Unscheduled Lot Merge功能，支持多个相同Source lot的lot 分别与母Lot Merge | 杨金杰
11 | 1 | 1 |  | Merge/Split | 137 | Split |  | Split Lot | Lot | 完成 | 2022 | Lot 分批（Physical Remote/Local,Logical) | 杨金杰
11 | 1 | 1 |  |  | 138 | Rework/Split-Rework |  | Split Rework | Lot | 完成 | 2022 |  | 杨金杰
1 |  | 1 |  |  | 139 |  |  | Cancel Rework | Lot | 完成 | 2022 | 取消返工（Rework State：InRework->NotInRework） | 罗涛
1 |  | 1 |  |  | 140 |  |  | Rework | Lot | 完成 | 2022 | 计划返工/adhoc 返工（Rework State：NotInRework->InRework） | 罗涛
1 | 1 |  |  | Reposition | 141 | NPW Reposition |  |  | Lot | 未推进 | 2022 |  | 罗涛
1 | 1 |  |  | Reposition | 142 | Production Reposition |  |  | Lot | 未推进 | 2022 |  | 罗涛
1 |  | 1 |  | Reposition | 143 |  |  | Reposition Oper | Lot | 完成 | 2022 |  | 罗涛
1 |  | 1 |  | Reposition | 144 |  |  | Fetch Oper | Lot | 完成 | 2022 |  | 罗涛
1 |  | 1 |  | Reposition | 145 |  |  | Back Step | Lot | 完成 | 2022 |  | 罗涛
11 | 1 | 1 |  | Reposition | 146 | Reposition Rule |  | Reposition Rule | Lot | 完成 | 2022 | Reposition Rule | 罗涛
11 | 1 | 1 |  | Reposition | 147 | Skip Step |  | Skip Step | Lot | 完成 | 2022 |  | 罗涛
11 | 1 | 1 |  | Reposition | 148 | Special Reposition Step |  | Special Reposition Oper | Lot | 完成 | 2022 |  | 罗涛
1 | 1 |  |  | Simple Lot Transfer | 149 | Cancel Transfer Lot |  |  | Lot | 未推进 | 2022 |  | 罗涛
1 | 1 |  |  | Simple Carrier Transfer | 150 | Receive Transfer Carrier |  |  | Lot | 未推进 | 2022 |  | 罗涛
1 | 1 |  |  | Simple Carrier Transfer | 151 | Simple Transfer Carrier |  |  | Lot | 未推进 | 2022 |  | 罗涛
1 | 1 |  |  | Simple Lot Transfer | 152 | Receive Plan |  |  | Lot | 未推进 | 2022 |  | 罗涛
11 | 1 | 1 |  | Simple Lot Transfer | 153 | Receive Transfer Back Lot |  | Receive Transfer Lot Back | Lot | 完成 | 2022 |  | 罗涛
11 | 1 | 1 |  | Simple Lot Transfer | 154 | Receive Transfer Lot |  | Receive Transfer Lot | Lot | 完成 | 2022 |  | 罗涛
11 | 1 | 1 |  | Simple Lot Transfer | 155 | Simple Transfer Back Lot |  | Simple Transfer Lot Back | Lot | 完成 | 2022 |  | 罗涛
11 | 1 | 1 |  | Simple Lot Transfer | 156 | Simple Transfer Lot |  | Simple Transfer Lot | Lot | 完成 | 2022 |  | 罗涛
11 | 1 | 1 |  | Simple Lot Transfer | 157 | Transfer Mapping Configuration |  | Transfer Mapping | Lot | 完成 | 2022 |  | 罗涛
1 |  | 1 |  |  | 158 |  |  | Transfer Table Map | Lot | 完成 | 2022 |  | 罗涛
1 |  | 1 |  |  | 159 |  |  | Fab Attribute Mapping Config | Lot | 完成 | 2022 | From/To FAB 属性信息Mapping | 罗涛
1 |  | 1 |  |  | 160 |  |  | Fab Attribute Value Mapping | Lot | 完成 | 2022 | From/To FAB 属性的值信息Mapping | 罗涛
1 |  | 1 |  |  | 161 |  |  | View Transfer List | Lot | 完成 | 2022 |  | 罗涛
1 | 1 |  |  | Doma Management | 162 | Unprocessed DOMA Path View |  |  | Lot | 未推进 | 2022 |  | 罗涛
1 |  | 1 |  | Scrap/Terminate | 163 |  |  | Scrap Apply | Lot | 完成 | 2022 | 报废Lot | 罗涛
1 |  | 1 |  | Scrap/Terminate | 164 |  |  | Cancel Scrap Apply | Lot | 完成 | 2022 | 报废申请 | 罗涛
11 | 1 | 1 |  | Scrap/Terminate | 165 | UnScrap |  | UnScrap | Lot | 完成 | 2022 |  | 罗涛
11 | 1 | 1 |  | Scrap/Terminate | 166 | Scrap |  | Scrap | Lot | 完成 | 2022 |  | 罗涛
11 | 1 | 1 |  | Scrap/Terminate | 167 | Special UnTerminate Lot |  | Special Unterminate Lot | Lot | 完成 | 2022 | Special UnTerminate Lot | 罗涛
11 | 1 | 1 |  | Scrap/Terminate | 168 | Terminate Lot |  | Terminate Lot | Lot | 完成 | 2022 |  | 罗涛
11 | 1 | 1 |  | Scrap/Terminate | 169 | Terminate By Foup |  | Terminate Lot By Carrier | Lot | 完成 | 2022 |  | 罗涛
11 | 1 | 1 |  | Scrap/Terminate | 170 | Terminate Finish Lot |  | Terminate Finish Lot | Lot | 完成 | 2022 |  | 罗涛
11 | 1 | 1 |  | Scrap/Terminate | 171 | UnTerminate Lot |  | Unterminate Lot | Lot | 完成 | 2022 | UnTerminate Lot | 罗涛
11 | 1 | 1 |  | Pilot | 172 | View Pilot |  | View Pi Lot | Lot | 完成 | 2022 | 查看Pi Lot信息 | 罗涛
1 | 1 |  |  |  | 173 | YE Review Spec Configuration |  |  | Lot | 未推进 | 2022 |  | 罗涛
1 | 1 |  |  |  | 174 | YE Review Special Reposition |  |  | Lot | 未推进 | 2022 |  | 罗涛
1 | 1 |  |  |  | 175 | YE Select Wafers For Remeasure |  |  | Lot | 未推进 | 2022 |  | 罗涛
1 | 1 |  |  | MixRun | 176 | Mix Run |  |  | Lot | 未推进 | 2022 |  | 罗涛
11 | 1 | 1 |  | Pilot | 177 | Release Hold Pilot |  | Release Hold Pilot | Lot | 完成 | 2022 |  | 罗涛
1 | 1 |  |  | Pilot | 178 | Pilot Full Auto Information Setting |  |  | Lot | 未推进 | 2022 |  | 罗涛
1 | 1 |  |  | Pilot | 179 | Create Adhoc Pilot |  |  | Lot | 未推进 | 2022 |  | 罗涛
11 | 1 | 1 |  | Pilot | 180 | On Demand Pilot |  | On Demand Pilot Condition | Lot | 完成 | 2022 |  | 罗涛 | [5 empty] | Modeler
11 | 1 | 1 |  | Pilot | 181 | Pilot Success Condition |  | Pilot Success Condition | Lot | 完成 | 2022 |  | 罗涛 | [5 empty] | Modeler
11 | 1 | 1 |  | Pilot | 182 | Pilot Target Condition |  | Pilot Target Condition | Lot | 完成 | 2022 |  | 罗涛 | [5 empty] | Modeler
11 | 1 | 1 |  | Pilot | 183 | Stop Pilot |  | Stop Pilot | Lot | 完成 | 2022 |  | 罗涛
1 | 1 |  |  | Q'Time Control | 184 | Cancel Q'Time Reservation |  |  | Lot | 未推进 | 2022 |  | 申克楠
1 | 1 |  |  | Q'Time Control | 185 | Turn Off Q'Time Speed Up |  |  | Lot | 未推进 | 2022 |  | 申克楠
1 |  | 1 |  |  | 186 |  |  | Q-Time List | Lot | 完成 | 2022 |  | 申克楠
1 |  | 1 |  |  | 187 |  |  | Q-Time Control | Lot | 完成 | 2022 |  | 申克楠
|  |  |  | Dedication | 188 |  |  |  | Lot | 完成 | 2022 |  | 童海潮
11 | 1 | 1 |  |  | 189 | Full Lot Report |  | Full Lot Report | Lot | 完成 | 2022 |  | 童海潮
1 |  | 1 |  |  | 190 |  |  | View Lot Info | Lot | 完成 | 2022 |  | 童海潮
1 |  | 1 |  |  | 191 |  |  | View Lot List | Lot | 完成 | 2022 | 按照TPFO别查询Lot List | 童海潮
1 |  | 1 |  |  | 192 |  |  | Data Collect Lot History | Lot | 完成 | 2022 |  | 童海潮
1 |  | 1 |  |  | 193 |  |  | View Lot History | Lot | 完成 | 2022 |  | 童海潮
11 | 1 | 1 |  |  | 194 | Add Comment |  | Add Comment | Lot | 完成 | 2022 | 增加comment | 罗涛
11 | 1 | 1 |  |  | 195 | T7 Code Query |  | View T7 Code | Lot | 完成 | 2022 |  | 罗涛
11 | 1 | 1 |  |  | 196 | Furnace Batch History |  | View Furnace Batch History | Lot | 完成 | 2022 |  | 罗涛
11 | 1 | 1 |  |  | 197 | View Component Information |  | View Component Info | Lot | 完成 | 2022 |  | 罗涛
11 | 1 | 1 |  |  | 198 | Wafer Chamber Tracking History |  | View Wafer Chamber Tracking History | Lot | 完成 | 2022 |  | 罗涛
11 | 1 | 1 |  |  | 199 | Wafer History |  | View Wafer History | Lot | 完成 | 2022 |  | 罗涛
1 | 1 |  |  |  | 200 | Wafer Slot History |  |  | Lot | 未推进 | 2022 |  | 罗涛
11 | 1 | 1 | Lot Inventory |  | 201 | Bank In |  | Bank In | Inventory | 完成 | 2022 | 对选择的Lot进行移入Bank的操作(BankState:OnFloor->InBank)，支持批量操作 | 罗涛
11 | 1 | 1 |  |  | 202 | Bank Out |  | Bank Out | Inventory | 完成 | 2022 | 对选择的Lot进行移出Bank的操作(BankState:InBank->OnFloor)，支持批量操作 | 罗涛
11 | 1 | 1 |  |  | 203 | Batch Bank In |  | Bank In | Inventory | 完成 | 2022 | 对选择的Lot进行移入Bank的操作(BankState:OnFloor->InBank)，支持批量操作 | 罗涛
1 | 1 |  |  |  | 204 | Check Cust Maintain |  |  | Inventory | 未推进 | 2022 |  | 罗涛
1 | 1 |  |  |  | 205 | Continue |  |  | Inventory | 未推进 | 2022 |  | 罗涛
11 | 1 | 1 |  |  | 206 | Move Bank |  | Move Bank | Inventory | 完成 | 2022 | 将Lot在不同Bank之间进行转移 | 罗涛
1 | 1 |  |  |  | 207 | Move To Location |  |  | Inventory | 未推进 | 2022 |  | 罗涛
11 | 1 | 1 |  |  | 208 | Query Bank Info |  | View Bank Info | Inventory | 完成 | 2022 |  | 罗涛
11 | 1 | 1 |  |  | 209 | Ship |  | Ship | Inventory | 完成 | 2022 |  | 罗涛
11 | 1 | 1 |  |  | 210 | UnShipByWafer |  | Unship | Inventory | 完成 | 2022 |  | 罗涛
1 |  | 1 |  |  | 211 |  |  | RSP Label | Inventory | 完成 | 2022 |  | 罗涛
1 |  | 1 |  |  | 212 |  |  | Lot Card | Inventory |  | 2022 | Input Lot Print and Mapping FOUP ID(Validation条件考虑) | 罗涛
1 |  | 1 |  |  | 213 |  |  | Lot Label | Inventory |  | 2022 |  | 罗涛
1 |  | 1 |  |  | 214 |  |  | Reticle Label | Inventory | 完成 | 2022 |  | 罗涛
1 |  | 1 |  |  | 215 |  |  | FOSB Label | Inventory | 完成 | 2022 |  | 罗涛
1 |  | 1 | WIP Tracking | Plan | 216 |  |  | Product Order | WIP | 完成 | 2022 |  | 罗涛
1 |  | 1 |  | Plan | 217 |  |  | Work Order | WIP | 完成 | 2022 | 查询 Work Order, 可修改/删除/查询并Complte PM Card | 罗涛
1 |  | 1 |  | Plan | 218 |  |  | View PO/WO History | WIP | 完成 | 2022 | 查询 PO/WO 的操作履历 | 罗涛
11 | 1 | 1 |  | Plan | 219 | Create Production Lot |  | Create Lot | WIP | 完成 | 2022 |  | 罗涛
11 | 1 | 1 |  | Plan | 220 | Create NPW Lot |  | Create NPW Lot | WIP | 完成 | 2022 | 生成 NPW Lot | 罗涛
11 | 1 | 1 |  | Plan | 221 | Create Engineer Lot |  | Create Engineer Lot | WIP | 完成 | 2022 | 生成 Engineer Lot | 罗涛
1 |  | 1 |  | Plan | 222 |  |  | View Create Lot List | WIP | 完成 | 2022 |  | 罗涛
1 |  | 1 |  | Plan | 223 |  |  | View Transaction Raw Wafer List | WIP | 完成 | 2022 | 查询 ERP Raw Wafer 清单，需要手动 Create(ERP IF 接口没有时 | 罗涛
11 | 1 | 1 |  | Plan | 224 | Query Raw Material Info |  | View Raw Wafer List | WIP | 待确认 | 2022 | 查看当前库存，Confirm 时累加，Create Source Vendor Lot时消耗 | 罗涛
1 |  | 1 |  | Plan | 225 |  |  | FOSB Generate | WIP | 完成 | 2022 |  | 罗涛
11 | 1 | 1 |  | Plan | 226 | Create Source Lot |  | Create Source Vendor Lot | WIP | 完成 | 2022 | 基于 Raw Wafer 进行 Source Vendor Lot 生成(FOSB 匹配) | 罗涛
11 | 1 | 1 |  | Plan | 227 | Query Source Lot Info |  | View Source Lot List | WIP | 完成 | 2022 |  | 罗涛
1 |  | 1 |  | Plan | 228 |  |  | FOSB Generate Scan | WIP | 完成 | 2022 |  | 罗涛
1 |  | 1 |  | Plan | 229 |  |  | Start Lot Reserve | WIP | 完成 | 2022 |  | 罗涛
11 | 1 | 1 |  | Plan | 230 | Start Lot |  | Start Lot | WIP | 完成 | 2022 | 将Source Vendor Lot. Lot ID, Carrier ID三者匹配生成Lot/wafer的功能,支持Sort Local | 罗涛
1 |  | 1 |  | Plan | 231 |  |  | Insert T7 Code | WIP | 完成 | 2022 |  | 罗涛
1 |  | 1 |  | Plan | 232 |  |  | Start Lot Auto | WIP | 完成 | 2022 |  | 罗涛
1 |  | 1 |  | Plan | 233 |  |  | Wafer Start Reserve | WIP | 完成 | 2022 | Start Lot的自动模式，支持Sort Remote + 手动Load读取RFID，Sort自动读取T7 Code 保存 | 罗涛
1 |  | 1 |  | Plan | 234 |  |  | View Start Lot | WIP | 完成 | 2022 |  | 罗涛
1 |  | 1 |  | Plan | 235 |  |  | Skip Started Lot | WIP | 完成 | 2022 |  | 罗涛
11 | 1 | 1 |  |  | 236 | Confirm Raw Wafers |  | View Raw Wafer List | WIP | 完成 | 2022 | 查看当前库存，Confirm 时累加，Create Source Vendor Lot时消耗 | 罗涛
1 | 1 |  |  |  | 237 | Create Glass Lot |  |  | WIP | 未推进 | 2022 |  | 罗涛
11 | 1 | 1 |  |  | 238 | Modify/Cancel Create Lot |  | View Create Lot List | WIP | 完成 | 2022 |  | 罗涛
1 | 1 |  |  | N2Purge | 239 | Cancel N2Purge |  |  | WIP | 未推进 | 2023 1Q |  | 申克楠
1 | 1 |  |  | N2Purge | 240 | End N2Purge |  |  | WIP | 未推进 | 2023 1Q |  | 申克楠
1 | 1 |  |  | N2Purge | 241 | Load Port N2 Purge Flag Maintain |  |  | WIP | 未推进 | 2023 1Q |  | 申克楠
1 | 1 |  |  | N2Purge | 242 | Start N2Purge |  |  | WIP | 未推进 | 2023 1Q |  | 申克楠
11 | 1 | 1 |  | Run Card | 243 | Change RunCard Status |  | View/Change Run Card State | WIP | 完成 | 2022 |  | 申克楠
11 | 1 | 1 |  | Run Card | 244 | Create Recover RunCard |  | Recover Run Card | WIP | 完成 | 2022 |  | 申克楠
11 | 1 | 1 |  | Run Card | 245 | Create Split Run Card |  | Split Run Card | WIP | 完成 | 2022 |  | 申克楠
1 | 1 |  |  | Run Card | 246 | Get RunCard Information |  |  | WIP | 未推进 | 2022 |  | 申克楠
1 |  | 1 |  | Run Card | 247 |  |  | Release Split RunCard | WIP | 完成 | 2022
1 | 1 |  |  | Run Card | 248 | Merge RunCard Lot |  |  | WIP | 待确认 | 2022 |  | 申克楠
1 | 1 |  |  | PPID Control | 249 | Edit PPID Comment |  |  | WIP | 待确认 | 2022 |  | 李彬
1 | 1 |  |  | PPID Control | 250 | Hold/Release LayoutRecipe |  |  | WIP | 完成 | 2022 |  | 李彬
1 | 1 |  |  | PPID Control | 251 | Hold/Release LayoutRecipe History |  |  | WIP | 完成 | 2022 |  | 李彬
1 | 1 |  |  | PPID Control | 252 | Hold/Release PPID |  |  | WIP | 完成 | 2022 |  | 李彬
1 | 1 |  |  | PPID Control | 253 | Hold/Release PPID History |  |  | WIP | 完成 | 2022 |  | 李彬
1 | 1 |  |  | PPID Control | 254 | PPID Resolution History |  |  | WIP | 完成 | 2022 |  | 李彬
1 | 1 |  |  | PPID Control | 255 | Release PPID Constraint |  |  | WIP | 完成 | 2022 |  | 李彬
1 | 1 |  |  | PPID Control | 256 | Release PPID Constraint History |  |  | WIP | 完成 | 2022 |  | 李彬
1 |  | 1 |  | PPID Control | 257 |  |  | Machine Recipe Management | WIP | 完成 | 2022 |  | 李彬
1 |  | 1 |  | PPID Control | 258 |  |  | Machine Recipe Management History | WIP | 完成 | 2022 |  | 李彬
1 |  | 1 |  | PPID Control | 259 |  |  | Machine Recipe Constraint Release | WIP | 完成 | 2022 |  | 李彬
1 |  | 1 |  | PPID Control | 260 |  |  | Machine Recipe Constraint Release History | WIP | 完成 | 2022 |  | 李彬
1 | 1 |  |  | Bonding | 261 | Bonding Lot History |  |  | WIP | 待确认 | 2022 |  | 申克楠
1 | 1 |  |  | Bonding | 262 | Bonded Lot |  |  | WIP | 待确认 | 2022 |  | 申克楠
1 | 1 |  |  | Bonding | 263 | Bonding Lot Skip |  |  | WIP | 待确认 | 2022 |  | 申克楠
1 | 1 |  |  | Bonding | 264 | Bonding Lot Type Mapping |  |  | WIP | 待确认 | 2022 |  | 申克楠
1 | 1 |  |  | Bonding | 265 | Bonding Product Mapping |  |  | WIP | 待确认 | 2022 |  | 申克楠
1 | 1 |  |  | Bonding | 266 | Bonding Step Mapping |  |  | WIP | 待确认 | 2022 |  | 申克楠
1 | 1 |  |  | Bonding | 267 | Glass Lot Information |  |  | WIP | 待确认 | 2022 |  | 申克楠
1 | 1 |  |  | Bonding | 268 | Pair Port Setting |  |  | WIP | 待确认 | 2022 |  | 申克楠
1 | 1 |  |  | Bonding | 269 | Pair Port Setting |  |  | WIP | 待确认 | 2022 |  | 申克楠
1 | 1 |  |  | Bonding | 270 | Pre Bonding |  |  | WIP | 待确认 | 2022 |  | 申克楠
11 | 1 | 1 |  | Cancel Job | 271 | Cancel Sorter Reservation |  | Cancel Prepared Lot | WIP | 完成 | 2022 | 取消Prepare Lot | 申克楠
11 | 1 | 1 |  | Cancel Job | 272 | Cancel Job In |  | Cancel Track In | WIP | 完成 | 2022 |  | 申克楠
11 | 1 | 1 |  | Non-Sorter Job | 273 | Job Out |  | Track Out | WIP | 完成 | 2022 | Track Out UI | 申克楠
11 | 1 | 1 |  | Non-Sorter Job | 274 | Job In |  | Track In | WIP | 完成 | 2022 | Track In 作业 | 申克楠
11 | 1 | 1 |  | Non-Sorter Job | 275 | Job Out |  | Track Out | WIP | 完成 | 2022 | Track Out UI | 申克楠
11 | 1 | 1 |  | Non-Sorter Job | 276 | Job Preparation |  | Prepare Lot | WIP | 完成 | 2022 | Lot 预约 | 申克楠
11 | 1 | 1 |  | Cancel Job | 277 | Cancel Job Preparation |  | Cancel Prepare Lot | WIP | 完成 | 2022 |  | 申克楠
11 | 1 | 1 |  |  | 278 | Lot Queue Adjustment |  | Lot Queue Adjustment | WIP | 开发中 | 2022 |  | 申克楠
11 | 1 | 1 |  |  | 279 | Lot Queue Reservation |  | Lot Queue Reservation | WIP | 开发中 | 2022 |  | 申克楠
1 | 1 |  |  |  | 280 | Query FOUP-Lot Reservation |  |  | WIP | 待确认 | 2022 |  | 申克楠
1 |  | 1 |  |  | 281 |  |  | Reserve Machine In Current Step | WIP | 完成 | 2022 | Preprae Lot前手动将Lot绑定Machine | 申克楠
1 |  | 1 |  |  | 282 |  |  | Cancel Reserve Machine In Current Step | WIP | 完成 | 2022 | 取消Lot对Machine 的绑定 | 申克楠
1 |  | 1 |  |  | 283 |  |  | Restriction Machine | WIP | 完成 | 2022 |  | 申克楠
1 |  | 1 |  |  | 284 |  |  | View Cj And Pj | WIP | 完成 | 2022 |  | 申克楠
1 |  | 1 |  |  | 285 |  |  | Furnace Prepare Lot | WIP | 完成 | 2022 |  | 申克楠
1 |  | 1 |  |  | 286 |  |  | Create Batch | WIP | 完成 | 2022 | 1) Lot别Position 调整；2）Recipe Resolution; 3）Batch ID 生成 | 申克楠
1 |  | 1 |  |  | 287 |  |  | Cancel Create Batch | WIP | 完成 | 2022 | Batch ID 生成取消 | 申克楠
11 | 1 | 1 |  | WaferSelectionRule | 288 | Setting By EDC Plan |  | 设置EDC Plan 的Wafer Selection Rule | WIP | 未推进 | 2022 |  | 申克楠/李彬
1 | 1 |  |  | WaferSelectionRule | 289 | Setting By EQP |  |  | WIP | 未推进 | 2022 |  | 申克楠
1 | 1 |  |  |  | 290 | Setup Runtime Eqp State |  |  | WIP | 未推进 | 2022 |  | 杨金杰
1 | 1 |  |  |  | 291 | R2R Modeling Configuration |  |  | WIP | 未推进 | 2022 |  | 申克楠
1 | 1 |  |  |  | 292 | Sorter Capability Set By Carrier Type |  |  | WIP | 未推进 | 2023 1Q |  | 申克楠
1 | 1 |  |  |  | 293 | Sorter Capability Set By Wafer Kind |  |  | WIP | 未推进 | 2023 1Q |  | 申克楠
11 | 1 | 1 |  | Sorter Job | 294 | Sorter Job In |  | Sorter Track In | WIP | 完成 | 2022 | Sorter设备已经预约的lot 进行Track In 处理 | 申克楠
11 | 1 | 1 |  | Sorter Job | 295 | Sorter Job Out |  | Sorter Track Out | WIP | 完成 | 2022 | Sorter设备Track Out | 申克楠
11 | 1 | 1 |  | Sorter Job | 296 | Sorter Job Preparation |  | Sorter Job Prepare | WIP | 完成 | 2022 |  | 申克楠
1 |  | 1 |  |  | 297 |  |  | Sorter Cancel Job Prepare | WIP | 完成 | 2022 |  | 申克楠
1 |  | 1 |  |  | 298 |  |  | Sorter Cancel Track In | WIP | 完成 | 2022 |  | 申克楠
1 |  | 1 |  |  | 299 |  |  | Sorter Job Cancel | WIP | 完成 | 2022 |  | 申克楠
1 | 1 |  |  | Data Collection | 302 | Adhoc Data Collection |  |  | WIP | 待确认 | 2023 1Q | 对机台Lot的数据收集。 | 李彬 | 苏州 | 顾圣培 |  |  | 未进行
1 | 1 |  |  | Data Collection | 303 | Cancel ReSend To Spc |  |  | WIP | 未推进 | 2022 | 取消重新发送数据到SPC | 李彬 | 苏州 |  |  |  | 未进行
11 | 1 | 1 |  | Data Collection | 304 | Lot Data Collection |  | Data Collect Lot | WIP | 完成 | 2022 | Data Collect Lot | 李彬 | 苏州 |  |  |  | 进行中
11 | 1 | 1 |  | Data Collection | 305 | HoldPPID Action Setting |  | Data Collect Spec | WIP | 完成 | 2022 | OOS/OOC/DataMissing Hold Machine Recipe 的Action 配置 | 李彬 | 苏州 |  |  |  | 完成 | Modeler
1 | 1 |  |  | Data Collection | 306 | Non-Lot Data Collection |  |  | WIP | 待确认 | 2022 | 对Machine进行的数据收集 | 李彬 | 苏州 |  |  |  | 未进行
1 | 1 |  |  | Data Collection | 307 | ReSend To Spc |  |  | WIP | 未推进 | 2022 | 重新发送EDC 数据到SPC | 李彬 | 苏州 |  |  |  | 未进行
1 | 1 |  |  | Data Collection | 308 | YE SpecID Bincode Map |  |  | WIP | 未推进 | 2022 | 绑定EDC Spec 到 process Operation | 李彬 | 苏州 |  |  |  | 完成
1 | 1 |  |  | Data Collection | 309 | YE SpecID Bincode Map History |  |  | WIP | 未推进 | 2022 | 绑定EDC Spec 到 process Operation历史记录查询页面 | 李彬 | 苏州 |  |  |  | 未进行
1 | 1 |  |  | Data Collection | 310 | View Non Lot Dcoll Info |  |  | WIP | 待确认 | 2022 | 查询Non-Lot 数据收集页面 | 李彬 | 苏州 |  |  |  | 未进行
11 | 1 | 1 | CSN |  | 311 | Constraint |  | Constraint Setting | CSN | 完成 | 2022 |  | 申克楠 | 北京 | 鲁绍根 | 2022-08-30 | 2022-09-10 | 进行中 | Modeler
11 | 1 | 1 |  |  | 312 | Golden Tool |  | Golden Tool Setting | CSN | 完成 | 2022 |  | 申克楠 | 北京 | 鲁绍根 | 2022-08-30 | 2022-09-10 | 完成 | Modeler
11 | 1 | 1 |  |  | 313 | Mfg Dispatch |  | MFG Dispatch Setting | CSN | 完成 | 2022 |  | 申克楠 | 北京 | 鲁绍根 | 2022-08-30 | 2022-09-10 | 进行中 | Modeler
1 | 1 |  |  |  | 314 | Parts Life Time Control |  |  | CSN | 未推进 | 2022 |  | 申克楠
1 | 1 |  |  |  | 315 | CSN PPID Constraint |  |  | CSN | 未推进 | 2022 |  | 李彬
1 | 1 |  |  |  | 316 | Restrict Duration Recipe |  |  | CSN | 未推进 | 2022 |  | 申克楠
1 | 1 |  | Test Wafer | NPW Grade | 317 | Downgrade Wafer Quantity Limit |  |  | Test Wafer | 未推进 | 2022 |  | 童海潮
1 |  | 1 |  |  | 318 |  |  | Downgrade | Test Wafer | 完成 | 2022 |  | 童海潮
1 |  | 1 |  |  | 319 |  |  | Modify Wafer Information | Test Wafer | 完成 | 2022 |  | 童海潮
11 | 1 | 1 |  |  | 320 | Break Furnace Batch |  | Break Batch | Test Wafer | 完成 | 2022 |  | 童海潮
1 | 1 |  |  |  | 321 | Cancel Dummy In |  |  | Test Wafer | 未推进 | 2022 |  | 童海潮
1 | 1 |  |  |  | 322 | Cancel Reserve Dummy |  |  | Test Wafer | 未推进 | 2022 |  | 童海潮
1 |  | 1 |  |  | 323 |  |  | Downgrade Setting | Test Wafer | 完成 | 2022 |  | 童海潮
1 |  | 1 |  |  | 324 |  |  | NPW Inventory Setting | Test Wafer | 完成 | 2022 |  | 童海潮
11 | 1 | 1 |  |  | 325 | Configure Control ID |  | Furnace Monitor/Monitor/Dummy/Season/PM Season Control Rule Setting | Test Wafer | 完成 | 2022 |  | 童海潮
1 |  | 1 |  |  | 326 |  |  | PM Season Group | Test Wafer | 完成 | 2022 |  | 童海潮
1 | 1 |  |  |  | 327 | Configure Wafer Stock Level |  |  | Test Wafer | 未推进 | 2022 |  | 童海潮
11 | 1 | 1 |  |  | 328 | Dummy In |  | Dummy Load | Test Wafer | 完成 | 2022 |  | 童海潮
11 | 1 | 1 |  |  | 329 | Dummy Out |  | Dummy UnLoad | Test Wafer | 完成 | 2022 |  | 童海潮
11 | 1 | 1 |  |  | 330 | Furance Batch Waiting In Tool |  | View Furnace Wait Batch | Test Wafer | 完成 | 2022 |  | 童海潮
11 | 1 | 1 |  |  | 331 | InUse End |  | In Use End(Merge) | Test Wafer | 完成 | 2022 |  | 童海潮
1 |  | 1 |  |  | 332 |  |  | View In Use Start Lot | Test Wafer |  | 2022 |  | 童海潮
11 | 1 | 1 |  |  | 333 | Inuse Start With Split |  | In Use Start(Split) | Test Wafer | 完成 | 2022 |  | 童海潮
1 | 1 |  |  |  | 334 | Query Monitor Lot |  |  | Test Wafer | 未推进 | 2022 |  | 童海潮
1 | 1 |  |  |  | 335 | Reclaim End |  |  | Test Wafer | 未推进 | 2022 |  | 童海潮
1 | 1 |  |  |  | 336 | Re_Create Monitor Lot |  |  | Test Wafer | 未推进 | 2022 |  | 童海潮
11 | 1 | 1 |  |  | 337 | Recycle End |  | View Recycle End Lot List | Test Wafer | 完成 | 2022 |  | 童海潮
1 | 1 |  |  |  | 338 | Reserve Dummy |  |  | Test Wafer | 未推进 | 2022 |  | 童海潮
11 | 1 | 1 |  |  | 339 | Set Furnace batch boat information |  | Furnace Batch Boat Info Setting | WIP | 完成 | 2022 |  | 童海潮
11 | 1 | 1 |  |  | 340 | Reset Equipment Control State |  | View Machine Control Status | Test Wafer | 完成 | 2022 |  | 童海潮
1 |  | 1 |  |  | 341 |  |  | View NPW Inventory Status | Test Wafer | 完成 | 2022 |  | 童海潮
11 | 1 | 1 |  |  | 342 | View Equipment Control Status |  | View Machine Control Status | Test Wafer | 完成 | 2022 |  | 童海潮
11 | 1 | 1 |  |  | 343 | View Equipment Dummy Lot History |  | View Machine Dummy Lot History | Test Wafer | 完成 | 2022 |  | 童海潮
11 | 1 | 1 |  |  | 344 | View Equipment Dummy Status |  | View Machine Dummy Information | Test Wafer | 完成 | 2022 |  | 童海潮
11 | 1 | 1 |  |  | 345 | View Equipment Dummy Wafer History |  | View Machine Dummy Wafer History | Test Wafer | 完成 | 2022 |  | 童海潮
1 |  | 1 |  |  | 346 |  |  | View Monitor Status | Test Wafer | 完成 | 2022 |  | 童海潮
1 |  | 1 |  |  | 347 |  |  | View NPW PFO | Test Wafer | 完成 | 2022 |  | 童海潮
11 | 1 | 1 |  |  | 348 | View Monitor Lot History |  | View Monitor Lot History | Test Wafer | 完成 | 2022 |  | 童海潮
11 | 1 | 1 |  |  | 349 | View Season Lot History |  | View Season History | Test Wafer | 完成 | 2022 |  | 童海潮
1 | 1 |  | OCAP |  | 350 | Complete Double Confirm |  |  | OCAP | 未推进 | 2023 1Q |  | 李彬 |  |  |  |  | 未进行
1 | 1 |  |  |  | 351 | QUERY UI |  |  | OCAP | 完成 | 2023 1Q | 查询正在执行的OCAP逻辑 | 李彬 |  |  |  |  | 完成
1 | 1 |  | PCMS | Activity | 352 | Change Location |  |  | PCMS | 待确认
1 | 1 |  |  | Activity | 353 | Complete Use for RunCard |  |  | PCMS | 待确认
1 | 1 |  |  | Activity | 354 | EE Hold Card |  |  | PCMS | 待确认
1 | 1 |  |  | Activity | 355 | EE Validation |  |  | PCMS | 待确认
1 | 1 |  |  | Configuration | 356 | Equipment Capability With Probe Card Group |  |  | PCMS | 待确认
1 | 1 |  |  | Activity | 357 | Lend Out |  |  | PCMS | 待确认
1 | 1 |  |  | Activity | 358 | MFG Receive |  |  | PCMS | 待确认
1 | 1 |  |  | Run Time | 359 | Mounting Of Probe Card |  |  | PCMS | 待确认
1 | 1 |  |  | Configuration | 360 | Probe Card Group Maintenance |  |  | PCMS | 待确认
1 | 1 |  |  | Configuration | 361 | Probe Card Group Maintenance |  |  | PCMS | 待确认
1 | 1 |  |  | Configuration | 362 | Probe Card Group Maintenance |  |  | PCMS | 待确认
1 | 1 |  |  | Configuration | 363 | Probe Card Maintenance |  |  | PCMS | 待确认
1 | 1 |  |  | Configuration | 364 | Probe Card Maintenance |  |  | PCMS | 待确认
1 | 1 |  |  | Configuration | 365 | Probe Card Maintenance |  |  | PCMS | 待确认
1 | 1 |  |  | Configuration | 366 | Probe Card Maintenance |  |  | PCMS | 待确认
1 | 1 |  |  | Configuration | 367 | Probe Card Maintenance |  |  | PCMS | 待确认
1 | 1 |  |  | Activity | 368 | PE Hold Card |  |  | PCMS | 待确认
1 | 1 |  |  | Activity | 369 | PE Validation |  |  | PCMS | 待确认
1 | 1 |  |  | Configuration | 370 | Probe Card Group Maintenance |  |  | PCMS | 待确认
1 | 1 |  |  | Activity | 371 | Probe Card History |  |  | PCMS | 待确认
1 | 1 |  |  | Configuration | 372 | Probe Card Maintenance |  |  | PCMS | 待确认
1 | 1 |  |  | Configuration | 373 | RCP Probe Card Group Mapping |  |  | PCMS | 待确认
1 | 1 |  |  | Configuration | 374 | RCP Probe Card Group Mapping |  |  | PCMS | 待确认
1 | 1 |  |  | Configuration | 375 | RCP Probe Card Group Mapping |  |  | PCMS | 待确认
1 | 1 |  |  | Configuration | 376 | RCP Probe Card Group Mapping |  |  | PCMS | 待确认
1 | 1 |  |  | Configuration | 377 | RCP Probe Card Group Mapping |  |  | PCMS | 待确认
1 | 1 |  |  | Activity | 378 | Release To MFG |  |  | PCMS | 待确认
1 | 1 |  |  | Configuration | 379 | RCP Probe Card Group Mapping |  |  | PCMS | 待确认
1 | 1 |  |  | Activity | 380 | Release for RunCard |  |  | PCMS | 待确认
1 | 1 |  |  | Activity | 381 | Remove From Inventory |  |  | PCMS | 待确认
1 | 1 |  |  | Activity | 382 | Return From Repair |  |  | PCMS | 待确认
1 | 1 |  |  | Activity | 383 | Return To Inventory |  |  | PCMS | 待确认
1 | 1 |  |  | Activity | 384 | Return To PE |  |  | PCMS | 待确认
11 | 1 | 1 |  | Activity | 385 | Scrap |  | Scrap | Lot | 待确认
1 | 1 |  |  | Configuration | 386 | Location Maintenance |  |  | PCMS | 待确认
1 | 1 |  |  | Run Time | 387 | UnMounting Of Probe Card |  |  | PCMS | 待确认
11 | 1 | 1 |  | Activity | 388 | UnScrap |  | UnScrap | Lot | 待确认
1 | 1 |  |  | Activity | 389 | Send To Vendor Repair |  |  | PCMS | 待确认
1 | 1 |  | PRMS | MainGUI | 390 | Manage Resist Equipment Alarm |  |  | PRMS | 未推进 | 2023 2Q
1 | 1 |  |  | Configuration | 391 | PR Batch Assignment And Qualification |  |  | PRMS | 未推进 | 2023 2Q
1 | 1 |  |  | Activity | 392 | Change Location |  |  | PRMS | 未推进 | 2023 2Q
1 | 1 |  |  | Configuration | 393 | Location Maintenance |  |  | PRMS | 未推进 | 2023 2Q
1 | 1 |  |  | Activity | 394 | Photo Resist Consumable Events |  |  | PRMS | 未推进 | 2023 2Q
1 | 1 |  |  | Configuration | 395 | Photo Resist Equipment Maintenance |  |  | PRMS | 未推进 | 2023 2Q
1 | 1 |  |  | Activity | 396 | Photo Resist History |  |  | PRMS | 未推进 | 2023 2Q
1 | 1 |  |  | Configuration | 397 | Photo Resist Location Maintenance |  |  | PRMS | 未推进 | 2023 2Q
1 | 1 |  |  | Configuration | 398 | Photo Resist Part Maintenance |  |  | PRMS | 未推进 | 2023 2Q
1 | 1 |  |  | Configuration | 399 | PR Recipe |  |  | PRMS | 未推进 | 2023 2Q
1 | 1 |  |  | Activity | 400 | PR Recipe History |  |  | PRMS | 未推进 | 2023 2Q
1 | 1 |  |  | Configuration | 401 | Resist Consumables |  |  | PRMS | 未推进 | 2023 2Q
1 | 1 |  | PTMS | Create Part | 402 | Batch Create Part |  |  | PTMS | 未推进 | 2023 2Q
1 | 1 |  |  | Part Main GUI | 403 | Batch Create Part Master |  |  | PTMS | 未推进 | 2023 2Q
1 | 1 |  |  | Create Part | 404 | Create Part |  |  | PTMS | 未推进 | 2023 2Q
1 | 1 |  |  | Configuration | 405 | Cost Center |  |  | PTMS | 未推进 | 2023 2Q
1 | 1 |  |  | Part Group Maintain | 406 | Modify Part Group Relationship |  |  | PTMS | 未推进 | 2023 2Q
1 | 1 |  |  | Configuration | 407 | Part Cycle Limit |  |  | PTMS | 未推进 | 2023 2Q
1 | 1 |  |  | MainGUI | 408 | Part Main Screen View |  |  | PTMS | 未推进 | 2023 2Q
1 | 1 |  |  | Part Main GUI | 409 | Part Master MainGUI |  |  | PTMS | 未推进 | 2023 2Q
1 | 1 |  |  | Replace Parts | 410 | Replace Parts |  |  | PTMS | 未推进 | 2023 2Q
1 | 1 |  |  | Part Group Maintain | 411 | Query Part Group Relationship |  |  | PTMS | 未推进 | 2023 2Q
1 | 1 |  | RTD |  | 412 | Maintain Mark Lot |  |  | RTD | 未推进 | 2023 2Q
1 | 1 |  | Reticle | Maintain | 413 | Batch Reticle Properties |  |  | Reticle | 未推进 | 2022 |  | 杨金杰
11 | 1 | 1 |  | Create And Delete | 414 | Create Reticle |  | Create Reticle | Reticle | 完成 | 2022 |  | 杨金杰
11 | 1 | 1 |  | Reticle Activity | 415 | Scan In |  | Reticle Scan In | Reticle | 完成 | 2022 |  | 杨金杰
11 | 1 | 1 |  | Reticle Activity | 416 | Bank In |  | Bank In | Reticle | 完成 | 2022 |  | 杨金杰
11 | 1 | 1 |  | Reticle Activity | 417 | Bank Out |  | Reticle Bank Out | Reticle | 完成 | 2022 |  | 杨金杰
1 | 1 |  |  | Maintain | 418 | Batch IRIS Wafer Count |  |  | Reticle | 未推进 | 2022 |  | 杨金杰
1 | 1 |  |  | Maintain | 419 | Batch IRIS Wafer Count Import And Export |  |  | Reticle | 未推进 | 2022 |  | 杨金杰
1 | 1 |  |  | Maintain | 420 | Batch Pod Properties |  |  | Reticle | 未推进 | 2022 |  | 杨金杰
1 | 1 |  |  | Maintain | 421 | Batch Starlight |  |  | Reticle | 未推进 | 2022 |  | 杨金杰
1 | 1 |  |  | Maintain | 422 | Batch Wafer Count |  |  | Reticle | 未推进 | 2022 |  | 杨金杰
1 | 1 |  |  | Maintain | 423 | Batch XCDA Qtime |  |  | Reticle | 未推进 | 2022 |  | 杨金杰
1 | 1 |  |  | Maintain | 424 | Batch XCDA Qtime Import And Export |  |  | Reticle | 未推进 | 2022 |  | 杨金杰
1 | 1 |  |  | Reticle Activity | 425 | Change Location |  |  | Reticle | 未推进 | 2022 |  | 杨金杰
11 | 1 | 1 |  | Reticle Activity | 426 | Clean |  | View Reticle List | Reticle | 完成 | 2022 |  | 杨金杰
11 | 1 | 1 |  | Reticle Activity | 427 | Clean Complete |  | Reticle Clean Complete | Reticle | 完成 | 2022 |  | 杨金杰
1 | 1 |  |  | Maintain | 428 | Compatible Condition |  |  | Reticle | 未推进 | 2022 |  | 杨金杰
11 | 1 | 1 |  | Reticle Activity | 429 | Confirm Mask Quality |  | Quality Check | Reticle | 完成 | 2022 |  | 杨金杰
1 | 1 |  |  | Reticle Activity | 430 | Reticle Data Collection |  |  | Reticle | 未推进 | 2023 1Q | 对Reticle的数据收集 | 李彬 | 苏州
1 | 1 |  |  | Create And Delete | 431 | Delete Reticle |  |  | Reticle | 未推进 | 2022 |  | 杨金杰
11 | 1 | 1 |  | Reticle Activity | 432 | Hold Reticle |  | View Reticle List | Reticle | 完成 | 2022 |  | 杨金杰
1 | 1 |  |  | Reticle Activity | 433 | Inspection In |  |  | Reticle | 待确认 | 2022 |  | 杨金杰
1 | 1 |  |  | Reticle Activity | 434 | Inspection Out |  |  | Reticle | 待确认 | 2022 |  | 杨金杰
1 | 1 |  |  | Maintain | 435 | IRIS Wafer Count |  |  | Reticle | 未推进 | 2022 |  | 杨金杰
11 | 1 | 1 |  | Kit And Unkit | 436 | Kit And UnKit |  | View Pod List | Reticle | 完成 | 2022 |  | 杨金杰
1 | 1 |  |  | Reticle Activity | 437 | Load Reticle |  |  | Reticle | 待确认 | 2022 |  | 杨金杰
11 | 1 | 1 |  |  | 438 | Reticle Main Screen |  | View Reticle List | Reticle | 完成 | 2022 |  | 杨金杰
1 | 1 |  |  | Maintain | 439 | Maintain Equipment Type |  |  | Reticle | 未推进 | 2022 |  | 杨金杰
1 | 1 |  |  | Maintain | 440 | Maintain Reticle Location |  |  | Reticle | 未推进 | 2022 |  | 杨金杰
1 | 1 |  |  | Maintain | 441 | Maintain Reticle LocationType |  |  | Reticle | 未推进 | 2022 |  | 杨金杰
1 | 1 |  |  | Maintain | 442 | Maintain Reticle Grade |  |  | Reticle | 未推进 | 2022 |  | 杨金杰
1 | 1 |  |  | Maintain | 443 | Mask Clean |  |  | Reticle | 未推进 | 2022 |  | 杨金杰
1 | 1 |  |  | Reticle Activity | 444 | Modify Attribute |  |  | Reticle | 未推进 | 2022 |  | 杨金杰
1 | 1 |  |  | Reticle Activity | 445 | Offline Retrieve Reticle |  |  | Reticle | 未推进 | 2022 |  | 杨金杰
1 | 1 |  |  | Pod Activity | 446 | Change Location |  |  | Reticle | 未推进 | 2022 |  | 杨金杰
11 | 1 | 1 |  | Pod Activity | 447 | Change State |  | View Pod List | Reticle | 完成 | 2022 |  | 杨金杰
11 | 1 | 1 |  | Pod Activity | 448 | Clean |  | View Pod List | Reticle | 完成 | 2022 |  | 杨金杰
11 | 1 | 1 |  | Pod Activity | 449 | Clean Complete |  | Pod Clean Complete | Reticle | 完成 | 2022 |  | 杨金杰
1 | 1 |  |  | Pod Activity | 450 | Confirm Quality |  |  | Reticle | 未推进 | 2022 |  | 杨金杰
11 | 1 | 1 |  | Pod Activity | 451 | Exchange |  | Pod Exchange | Reticle | 完成 | 2022 |  | 杨金杰
11 | 1 | 1 |  | Pod Activity | 452 | Hold |  | View Pod List | Reticle | 完成 | 2022 |  | 杨金杰
11 | 1 | 1 |  |  | 453 | Pod Main Screen |  | View Pod List | Reticle | 完成 | 2022 |  | 杨金杰
1 | 1 |  |  | Create And Delete | 454 | Pod Mgt |  |  | Reticle | 未推进 | 2022 |  | 杨金杰
11 | 1 | 1 |  | Pod Activity | 455 | Release |  | Pod Release | Reticle | 完成 | 2022 |  | 杨金杰
11 | 1 | 1 |  | Pod Activity | 456 | Scrap |  | View Pod List | Reticle | 完成 | 2022 |  | 杨金杰
11 | 1 | 1 |  | Pod Activity | 457 | UnScrap |  | Pod Cancel Scrap | Reticle | 完成 | 2022 |  | 杨金杰
11 | 1 | 1 |  | Reticle Activity | 458 | Release Reticle |  | Reticle Release | Reticle | 完成 | 2022 |  | 杨金杰
1 | 1 |  |  | Maintain | 459 | Remount And Clean Count |  |  | Reticle | 未推进 | 2022 |  | 杨金杰
11 | 1 | 1 |  | Reticle Activity | 460 | Request Inspection |  | Inspection Request | Reticle | 待确认 | 2022 |  | 杨金杰
11 | 1 | 1 |  | Reticle Activity | 461 | Request Scan |  | View Reticle List | Reticle | 完成 | 2022 |  | 杨金杰
1 | 1 |  |  | Pod Activity | 462 | Reserve POD |  |  | Reticle | 未推进 | 2022 |  | 杨金杰
11 | 1 | 1 |  |  | 463 | History |  | Material History | Reticle | 完成 | 2022 |  | 杨金杰
1 | 1 |  |  | Reticle Activity | 464 | Cancel Scan |  |  | Reticle | 未推进 | 2022 |  | 杨金杰
11 | 1 | 1 |  | Reticle Activity | 465 | Reticle Scrap |  | View Reticle List | Reticle | 完成 | 2022 |  | 杨金杰
1 | 1 |  |  | Reticle Activity | 466 | Return To Customer |  |  | Reticle | 未推进 | 2022 |  | 杨金杰
11 | 1 | 1 |  | Reticle Activity | 467 | Scan Complete |  | Reticle Scan Out | Reticle | 完成 | 2022 |  | 杨金杰
11 | 1 | 1 |  | Maintain | 468 | Starlight |  | View Reticle List | Reticle | 完成 | 2022 | Inspection(Scan）周期 | 杨金杰
1 | 1 |  |  | Reticle Activity | 469 | Terminate |  |  | Reticle | 未推进 | 2022 |  | 杨金杰
11 | 1 | 1 |  | Reticle Activity | 470 | Unload Reticle |  | Reticle Unload | Reticle | 待确认 | 2022 |  | 杨金杰
11 | 1 | 1 |  | Reticle Activity | 471 | Reticle UnScrap |  | Cancel Scrap Reticle | Reticle | 完成 | 2022 |  | 杨金杰
1 |  | 1 | [5 empty] | View Reticle List | Reticle | 完成 | 2022 | Reticle Transfer In | 杨金杰
1 |  | 1 | [5 empty] | View Reticle List | Reticle | 完成 | 2022 | Reticle Transfer Out | 杨金杰
11 | 1 | 1 |  | Maintain | 472 | Wafer Count |  | View Reticle List | Reticle | 完成 | 2022 | Reticle Wafer Count | 杨金杰
1 | 1 |  |  | Reticle Activity | 473 | Batch XCDA Purge Time Remove |  |  | Reticle | 未推进 | 2022 |  | 杨金杰
11 | 1 | 1 |  | Maintain | 474 | XCDA Qtime |  | View Reticle List | Reticle | 完成 | 2022 | XCDA Time.Purge Time Spec | 杨金杰
1 | 1 |  |  | Reticle Activity | 475 | Batch XCDA Qtime Remove |  |  | Reticle | 未推进 | 2022 |  | 杨金杰
1 |  | 1 | Sampling |  | 476 |  |  | Set Scan Lot | Sampling | 完成 | 2022 |  | 申克楠 | [5 empty] | Modeler
1 |  | 1 |  |  | 477 |  |  | Set Sampling Skip Lot | Sampling | 完成 | 2022 |  | 申克楠 | [5 empty] | Modeler
1 |  | 1 |  |  | 478 |  |  | Sampling Reserve Lot List | Sampling | 完成 | 2022 |  | 申克楠 | [5 empty] | Modeler
1 |  | 1 |  |  | 479 |  |  | Sampling Skip Lot List | Sampling | 完成 | 2022 |  | 申克楠 | [5 empty] | Modeler
1 |  | 1 |  |  | 480 |  |  | Lot Sampling Run Time History | Sampling | 完成 | 2022 |  | 申克楠 | [5 empty] | Modeler
1 |  | 1 |  |  | 481 |  |  | Wafer Selection Rule | Sampling | 完成
1 |  | 1 |  |  | 482 |  |  | Machine Sampling | Sampling | 完成
1 |  | 1 |  |  | 483 |  |  | Pre-Post Sampling | Sampling | 完成
1 |  | 1 |  |  | 484 |  |  | Layer Change Sampling | Sampling | 完成
1 | 1 |  |  |  | 485 | Step Sampling |  |  | Sampling | 未推进 | 2022 |  | 申克楠 | [5 empty] | Modeler
1 | 1 |  |  |  | 486 | Default Sampling |  |  | Sampling | 待确认 | 2022 |  | 申克楠 | [5 empty] | Modeler
1 | 1 |  |  |  | 487 | Default Sampling |  |  | Sampling | 待确认 | 2022 |  | 申克楠 | [5 empty] | Modeler
11 | 1 | 1 |  |  | 488 | Furnace Monitor Sampling |  | FML Sampling | Sampling | 完成 | 2022 |  | 童海潮 | [5 empty] | Modeler
11 | 1 | 1 |  |  | 489 | YE Step Sampling |  | YE Step Sampling | Sampling | 测试中 | 2022 |  | 申克楠 | [5 empty] | Modeler
1 | 1 |  |  |  | 490 | Modify Key Lot Flag |  |  | Sampling | 待确认 | 2022 |  | 申克楠 | [5 empty] | Modeler
11 | 1 | 1 |  |  | 491 | Lot Sampling Runtime History |  | Lot Sampling Run Time History | Sampling | 测试中 | 2022 |  | 申克楠 | [5 empty] | Modeler
1 | 1 |  |  |  | 492 | Smart Sampling Special Flag |  |  | Sampling | 待确认 | 2022 |  | 申克楠 | [5 empty] | Modeler
1 | 1 |  |  |  | 493 | Smart Sampling Key Equipment |  |  | Sampling | 待确认 | 2022 |  | 申克楠 | [5 empty] | Modeler
1 | 1 |  |  |  | 494 | Smart Sampling Key Step Association |  |  | Sampling | 待确认 | 2022 |  | 申克楠 | [5 empty] | Modeler
1 | 1 |  |  | Sampling History | 495 | Smart Sampling MFG Skip History |  |  | Sampling | 待确认 | 2022 |  | 申克楠 | [5 empty] | Modeler
1 | 1 |  |  |  | 496 | YE Key Equipment |  |  | Sampling | 待确认 | 2022 |  | 申克楠 | [5 empty] | Modeler
1 | 1 |  |  |  | 497 | YE Key Step Association |  |  | Sampling | 待确认 | 2022 |  | 申克楠 | [5 empty] | Modeler
1 | 1 |  |  |  | 498 | YE Step By Flow |  |  | Sampling | 待确认 | 2022 |  | 申克楠 | [5 empty] | Modeler
1 | 1 |  |  |  | 499 | YE Step By Lot |  |  | Sampling | 待确认 | 2022 |  | 申克楠 | [5 empty] | Modeler
1 | 1 |  |  | Sampling History | 500 | YE Step Sampling History |  |  | Sampling | 待确认 | 2022 |  | 申克楠 | [5 empty] | Modeler
1 | 1 |  | Transportation |  | 501 | Cancel Reticle Transportation |  |  | Transportation | 未推进 | 2023 2Q
1 | 1 |  |  |  | 502 | Cancel Transportation |  |  | Transportation | 未推进 | 2023 2Q
1 | 1 |  |  | MCS Control | 503 | Reticle Transportation Request |  |  | Transportation | 未推进 | 2023 2Q
1 | 1 |  |  | MCS Control | 504 | Reticle Sync Stocker |  |  | Transportation | 未推进 | 2023 2Q
1 | 1 |  |  |  | 505 | MCS Inventory Info |  |  | Transportation | 未推进 | 2023 2Q
1 | 1 |  |  |  | 506 | Sync Reticle Stocker |  |  | Transportation | 未推进 | 2023 2Q
1 | 1 |  |  |  | 507 | Transportation Reticle Request |  |  | Transportation | 未推进 | 2023 2Q
1 | 1 |  |  |  | 508 | View Reticle Stocker |  |  | Transportation | 未推进 | 2023 2Q
1 | 1 |  |  |  | 509 | Sync Carrier Info |  |  | Transportation | 未推进 | 2023 2Q
1 | 1 |  |  |  | 510 | Transportation Request |  |  | Transportation | 未推进 | 2023 2Q
1 | 1 |  |  |  | 511 | Transportation Recovery |  |  | Transportation | 未推进 | 2023 2Q
1 | 1 |  | WAT |  | 512 | WAT Hold Information |  |  | WAT | 未推进 | 2023 2Q
1 | 1 |  |  |  | 513 | WAT Result Information |  |  | WAT | 未推进 | 2023 2Q
1 | 1 |  |  | Wafer Test | 514 | Final InkMap Prod Setting |  |  | WAT | 未推进 | 2023 2Q
1 | 1 |  |  | Wafer Test | 515 | Final InkMap Prod Setting |  |  | WAT | 未推进 | 2023 2Q
1 | 1 |  |  | Wafer Test | 516 | Wafer Test Information |  |  | WAT | 未推进 | 2023 2Q
1 | 1 |  |  | Wafer Test | 517 | Wafer Test Information |  |  | WAT | 未推进 | 2023 2Q
1 | 1 |  |  | Wafer Test | 518 | Wafer Test Result History |  |  | WAT | 未推进 | 2023 2Q
1 | 1 |  |  | Wafer Test | 519 | WT Hold Information |  |  | WAT | 未推进 | 2023 2Q
1 | 1 |  |  | Wafer Test | 520 | WT Product Yield Setting |  |  | WAT | 未推进 | 2023 2Q
1 | 1 |  |  | Wafer Test | 521 | WT Product Yield Setting |  |  | WAT | 未推进 | 2023 2Q
1 | 1 |  |  | Wafer Test | 522 | WT Retest Recipe Setting |  |  | WAT | 未推进 | 2023 2Q
1 | 1 |  |  | Wafer Test | 523 | WT Test Step Recipe Configuration |  |  | WAT | 未推进 | 2023 2Q

## cvMES
一级名字 | 二级名字 | 三级名字
WIP | Plan | Product Order
WIP | Plan | Work Order
WIP | Plan | View PO/WO History
WIP | Plan | Create Lot
WIP | Plan | Create NPW Lot
WIP | Plan | Create Engineer Lot
WIP | Plan | View Create Lot List
WIP | Source Lot | View Transaction Raw Wafer List
WIP | Source Lot | View Raw Wafer List
WIP | Source Lot | FOSB Generate
WIP | Source Lot | Create Source Vendor Lot
WIP | Source Lot | View Source Lot List
WIP | Source Lot | FOSB Generate Scan
WIP | Wafer Start | Start Lot Reserve
WIP | Wafer Start | Start Lot
WIP | Wafer Start | Insert T7 Code
WIP | Wafer Start | Start Lot Auto
WIP | Wafer Start | Wafer Start Reserve
WIP | Wafer Start | View Start Lot
WIP | Wafer Start | Skip Started Lot
WIP | Tracking | Prepare Lot
WIP | Tracking | Prepare Lot
WIP | Tracking | Cancel Prepared Lot
WIP | Tracking | Track In
WIP | Tracking | Cancel Track In
WIP | Tracking | Track Out
WIP | Tracking | Reserve Machine In Current Step
WIP | Tracking | Cancel Reserve Machine In Current Step
WIP | Tracking | Restriction Machine
WIP | Tracking | View Cj And Pj
WIP | Tracking | Test
WIP | Tracking | Lot Queue
WIP | Tracking | Furnace Prepare Lot
WIP | Batch | Cancel Create Batch
WIP | Batch | Break Batch
WIP | Batch | Create Batch
WIP | Run Card | Split Run Card
WIP | Run Card | Recover Run Card
WIP | Run Card | Release Split Run Card
WIP | Run Card | View/Change Run Card State
WIP | Run Card | Run Card Reform
WIP | Sorter | Sorter Track In
WIP | Sorter | Sorter Track Out
WIP | Sorter | Sorter Job Prepare
WIP | Sorter | Sorter Cancel Job Prepare
WIP | Sorter | Sorter Cancel Track In
WIP | Sorter | Sorter Job Cancel
WIP | Machine Recipe Control | Machine Recipe Management
WIP | Machine Recipe Control | Machine Recipe Management History
WIP | Machine Recipe Control | Machine Recipe Constraint Release
WIP | Machine Recipe Control | Machine Recipe Constraint Release History
Lot | Hold Lot | Hold Lot
Lot | Hold Lot | Batch Release
Lot | Hold Lot | Batch Hold
Lot | Hold Lot | Release Lot
Lot | Hold Lot | Edit Hold
Lot | Hold Lot | Release Action
Lot | Future Action | Future Reserve Machine
Lot | Future Action | Set Future Hold
Lot | Future Action | Set Future Merge
Lot | Future Action | Batch Future Hold
Lot | Future Action | Set Future Split
Lot | Future Action | Future Action List
Lot | Rework | Rework
Lot | Rework | Cancel Rework
Lot | Rework | Split Rework
Lot | Reposition | Reposition Oper
Lot | Reposition | Special Reposition Oper
Lot | Reposition | Fetch Oper
Lot | Reposition | Skip Step
Lot | Reposition | Back Step
Lot | Reposition | Reposition Rule
Lot | Sorter | Split Lot
Lot | Sorter | Merge Lot
Lot | Sorter | Transfer Lot
Lot | Sorter | Exchange Carrier
Lot | Sorter | Change Slot Map Info
Lot | Sorter | Wafer Rotate
Lot | Sorter | Wafer Verification
Lot | Reassign | Reassign Lot
Lot | Reassign | Reassign Lot For NPW
Lot | Reassign | Future Reassign
Lot | Terminate | Terminate Lot
Lot | Terminate | Terminate Lot By Carrier
Lot | Terminate | Unterminate Lot
Lot | Terminate | Terminate Finish Lot
Lot | Terminate | Special Unterminate Lot
Lot | Scrap Lot | Scrap Apply
Lot | Scrap Lot | Cancel Scrap Apply
Lot | Scrap Lot | Scrap
Lot | Scrap Lot | UnScrap
Lot | Pilot | Create Pi Lot
Lot | Pilot | View Pi Lot
Lot | Pilot | Stop Pilot
Lot | Pilot | Release Hold Pilot
Lot | Pilot | End PiLot
Lot | Lot Attribute | Add Steps
Lot | Lot Attribute | Add Comment
Lot | Lot Attribute | Modify Lot Attribute
Lot | Lot Attribute | Batch Modify Lot Attribute
Lot | Lot Attribute | Modify Lot Attribute For MFG
Lot | Lot Attribute | Modify Lot Attribute For QC
Lot | Lot Attribute | Modify Lot Contamination Level
Lot | Sampling | Set Scan Lot
Lot | Sampling | Set Sampling Skip Lot
Lot | Sampling | Sampling Reserve Lot List
Lot | Sampling | Sampling Skip Lot List
Lot | Sampling | Lot Sampling Run Time History
Lot | Dedication | Break Dedication
Machine | Port | Change Port Access Mode
Machine | Machine | Change Machine Control Mode
Machine | Machine | View Machine Auto Mode
Machine | Port | Change Port State
Machine | Machine | Change Machine State
Machine | Machine | Change Machine AMA Mode
Machine | PMS | Create Work Order
Machine | PMS | View Work Order
Machine | PMS | Work Order Approval
Machine | PMS | Calendar
Carrier | Management | View Carrier List
Carrier | Management | Create Carrier
Carrier | Management | Change Carrier Info
Carrier | Management | Scrap Carrier
Carrier | Management | Cancel Scrap Carrier
Carrier | Management | Change Carrier Clean State
Carrier | Management | Carrier RFID Management
Carrier | Management | Modify Carrier Attributes
Carrier | Management | Hold Carrier
Carrier | Management | Release Carrier
Carrier | Management | Assign Carrier
Carrier | Management | Deassign Carrier
Carrier | Management | Cancel Reserve Target Carrier
Transport | Transport | View Transport Queue
Transport | Stocker | Stocker Capacity
Transport | Stocker | Stocker Inventory
Transport | Transport | Re Transport Failed Lot
Transport | View | Transport Storage Info
Transport | View | Transfer Job List
Transport | View | Inventory List
Transport | View | Machine State List
Transport | View | Stocker CAPA.
Transport | View | Default Storage
Transport | Command | Manual Transfer
Transport | Command | Change Destination
Transport | Command | Change Transfer Priority
Transport | Command | Cancel Transfer Job
Transport | Command | Retry Alternative Job
Transport | Command | Synchronization
Inventory | Bank | Bank In
Inventory | Bank | Move Bank
Inventory | Bank | View Bank Info
Inventory | Bank | Bank Out
Inventory | Transfer | Transfer Mapping
Inventory | Transfer | Transfer Table Map
Inventory | Transfer | Fab Attribute Mapping Config
Inventory | Transfer | Fab Attribute Value Mapping
Inventory | Transfer | Simple Transfer Lot
Inventory | Transfer | Receive Transfer Lot Back
Inventory | Transfer | Receive Transfer Lot
Inventory | Transfer | Simple Transfer Lot Back
Inventory | Transfer | View Transfer List
Inventory | Ship | Ship
Inventory | Ship | Unship
Inventory | Label Print | RSP Label
Inventory | Label Print | Lot Card
Inventory | Label Print | Lot Label
Inventory | Label Print | Reticle Label
Inventory | Label Print | FOSB Label
NPW | Spec | Furnace Monitor Control Rule Setting
NPW | Spec | Dummy Control Rule Setting
NPW | Spec | Monitor Control Rule Setting
NPW | Spec | Season Control Rule Setting
NPW | Spec | Downgrade Setting
NPW | Spec | NPW Inventory Setting
NPW | NPW Main Flow | In Use Start(Split)
NPW | NPW Main Flow | View In Use Start Lot
NPW | NPW Main Flow | In Use End
NPW | NPW Main Flow | Downgrade
NPW | NPW Main Flow | Modify Wafer Information
NPW | Dummy | Dummy Load
NPW | Dummy | Dummy UnLoad
NPW | Furnace Monitor | View Furnace Wait Batch
NPW | Furnace Monitor | Furnace Batch Boat Info Setting
NPW | Season | PM Season Group
NPW | Season | PM Season Control Rule Setting
NPW | Inquiry | View NPW Inventory Status
NPW | Inquiry | View Machine Dummy Information
NPW | Inquiry | View Season History
NPW | Inquiry | View Machine Control Status
NPW | Inquiry | View Recycle End Lot List
Reticle | Reticle | View Reticle List
Reticle | Reticle | Create Reticle
Reticle | Reticle | Quality Check
Reticle | Reticle | Reticle Clean Complete
Reticle | Reticle | Reticle Release
Reticle | Reticle | Reticle Bank Out
Reticle | Reticle | Cancel Scrap Reticle
Reticle | Reticle | Reticle Scan In
Reticle | Reticle | Reticle Scan Out
Reticle | Reticle | Material History
Reticle | Pod | View Pod List
Reticle | Pod | Pod Exchange
Reticle | Pod | Pod Cancel Scrap
Reticle | Pod | Pod Release
Reticle | Pod | Pod Clean Complete
Inquiry | Lot | View Lot Info
Inquiry | Lot | View Lot List
Inquiry | Lot | Data Collect Lot History
Inquiry | Lot | View Lot History
Inquiry | Carrier | View Carrier Status
Inquiry | Carrier | View Carrier History
Inquiry | Lot | View Hold Lot Info
Inquiry | Lot | View T7 Code
Inquiry | Lot | Full Lot Report
Inquiry | Alarm | View Current Alarm
Inquiry | Alarm | AlarmRun
Inquiry | Machine | View Machine Info
Inquiry | Machine | View Machine Process History
Inquiry | Machine | View Machine History
Inquiry | Machine | View Machine Status
Inquiry | Wafer | View Wafer History
Inquiry | Wafer | View Wafer Chamber Tracking History
Inquiry | Wafer | View Component Info
Inquiry | Q-Time | Q-Time List
Inquiry | Q-Time | Q-Time Control
Inquiry | NPW | View Monitor Status
Inquiry | NPW | View Monitor Lot History
Inquiry | NPW | View NPW PFO
Inquiry | NPW | View Machine Dummy Lot History
Inquiry | NPW | View Machine Dummy Wafer History
Inquiry | NPW | View Furnace Batch History

## raw
序号 | 一级模块 | 二级模块 | 三级模块(Function Name) | UI | Access String Full Name
1 | Main | Main | Main WIP | #N/A | Update Recipe:弹出Update Recipe框
15 |  |  | PHOTO WIP | #N/A | Search：通过条件查询ProcessOperationList数据
16 |  |  |  | #N/A | Scanner Queue Add:新增Scanner Q
17 |  |  |  | #N/A | Scanner Queue Delete:删除Scanner Q
18 |  |  |  | #N/A | check：移动后保存RunLotList的Lot顺序
19 |  |  |  | #N/A | Pause Add:阻止Scanner Q生成
20 |  |  |  | #N/A | Pause Delete:删除阻止Scanner Q生成
21 |  |  |  | #N/A | Track Recipe:选择TrackRecipe
22 |  |  |  | #N/A | Scanner Recipe:选择ScannerRecipe
28 |  |  | Sorter WIP | #N/A
45 |  |  | WIP UI(Lot View) | #N/A
55 | WIP | Plan | Product Order | #N/A | Create:创建Product Order
56 |  |  |  | #N/A | Remove:删除Product Order
57 |  |  |  | #N/A | Modify :修改Produt Order
58 |  |  | Work Order | #N/A | Create:创建Work Order
59 |  |  |  | #N/A | Remove:删除Work Order
60 |  |  |  | #N/A | Modify :修改Work Order
61 |  |  | View PO/WO History | View PO/WO History | History：查看History
62 |  |  | Create Lot | Create Lot | Confirm：确认生成Lot Name
63 |  |  | Create NPW Lot | Create NPW Lot | Confirm：确认生成Lot Name
64 |  |  | Create Engineer Lot | Create Engineer Lot | Confirm：确认生成Lot Name
65 |  |  | View Create Lot List | View Create Lot List | Modify：对Lot 的Plan Data 编辑进行保存
66 |  |  |  | #N/A | Cancel：删除已生成的Lot Name
67 |  |  |  | #N/A | Release : 针对qty<create qty的lot强制Release
68 |  | Source Lot | View Transaction Raw Wafer List | View Transaction Raw Wafer List | Confirm：接收Raw Wafer
69 |  |  | View Raw Wafer List | View Raw Wafer List | History：查看History
70 |  |  | Create Source Vendor Lot | Create Source Vendor Lot | Confirm：生成Source Vendor Lot
71 |  |  | View Source Vendor Lot List | #N/A | Search
72 |  | Wafer Start | Start Lot | Start Lot | Confirm：manual start lot
73 |  |  | Start Lot(PDA) | #N/A | Confirm：使用PDA start lot
74 |  |  | Insert T7 Code | Insert T7 Code | Confirm：对T7 Code 进行手动编辑
75 |  |  | Start Lot (Auto) | #N/A | Confirm：Auto start lot
76 |  |  | Wafer Start Reserve | Wafer Start Reserve | Confirm：fast track in
77 |  |  | Zero Layer Wafer Start | #N/A | Confirm
78 |  |  | View Start Lot | View Start Lot | Cancel Reserve：取消Sorter 操作
79 |  |  |  | #N/A | Manual Track Out
80 |  |  | Skip Started Lot | Skip Started Lot | Skip：从虚拟栈点skip 到实际第一栈
81 |  |  | Input Plan Report | #N/A
82 |  | Tracking | Prepare Lot | Prepare Lot | WaferSelect:量测lot选择wafer
83 |  |  |  | #N/A | Confirm：提交页面数据，执行JobPrepare操作
84 |  |  | Cancel Prepared Lot | Cancel Prepared Lot | Confirm：提交页面数据，执行CancelJobPrepare操作
85 |  |  | Track In | Track In | Confirm：提交页面数据，执行TrackIn操作
86 |  |  | Cancel TrackIn | #N/A | Confirm：提交页面数据，执行CancelTrackIn操作
87 |  |  | Track Out | Track Out | Search：查看Lot/同Batch Lot的信息
88 |  |  |  | #N/A | Reset：清空查询框的数据
89 |  |  |  | #N/A | Confirm：提交页面数据，执行TrackOut操作
90 |  |  | Sorter Prepare Lot | #N/A | Confirm：提交页面数据，执行JobPrepare操作
91 |  |  | Sorter Cancel Prepared Lot | #N/A | Confirm：提交页面数据，执行CancelJobPrepare
92 |  |  | Sorter Track In | Sorter Track In | Confirm：提交页面数据，执行TrackIn操作
93 |  |  | Sorter Cancel TrackIn | #N/A | Confirm：提交页面数据，执行CancelTrackIn操作
94 |  |  | Sorter Track Out | Sorter Track Out | Confirm：提交页面数据，执行TrackOut操作
95 |  |  | Cancel Sorter Job | #N/A | Confirm：提交页面数据，执行CancelSorterjob操作
96 |  |  | Reserve Machine in Current Step | Reserve Machine In Current Step | Confirm：提交页面数据，执行设备预约操作
97 |  |  | Cancel Reserve Machine in Current Step | Cancel Reserve Machine In Current Step | Confirm：提交页面数据，执行取消设备预约操作
98 |  |  | Multi Prepare Lot | #N/A
99 |  | Batch | Create Batch | Create Batch | Confirm：提交页面数据，执行CreateBatch操作
100 |  |  | Cancel Create Batch | Cancel Create Batch | Confirm：提交页面数据，执行CancelCreateBatch操作
101 |  |  | Set Furnace batch boat information | #N/A
102 |  | Machine Recipe Control | Machine Recipe Hold/Realase | #N/A
103 |  |  | Machine Recipe Event History | #N/A
104 |  |  | Release PPID Constraint | #N/A
105 |  |  | Release PPID Constraint History | #N/A
106 |  |  | Machine Recipe Resolution History | #N/A
107 |  |  | R2R Modeling Configuration | #N/A
108 |  | Data Collection | LOT DC UI | #N/A | 数据提交Comfirm、OOS 信息 确认按钮
109 |  |  | Non Lot DC | #N/A | 数据提交Comfirm、OOS 信息确认按钮
110 |  |  | Adhoc DC | #N/A | 数据提交Comfirm、OOS 信息确认按钮
111 |  |  | Reticle DC | #N/A
112 |  |  | Carrier DC | #N/A
113 |  | ETC | InLine Data BoatSlot | #N/A
114 |  |  | VIEW FOUP-Lot Reservation | #N/A
115 |  | Run Card | Create Split Run Card | #N/A | Save Draft
116 |  |  |  | #N/A | Confirm
117 |  |  |  | #N/A | Copy
118 |  |  | Start Run Card | #N/A
119 |  |  | Change Lot Process State | #N/A
120 |  |  | View Run Card State | #N/A | Confirm: 变更Run Card State
121 |  |  | Change Run Card State | #N/A
122 |  |  | Create Recover Run Card | #N/A | Save Draft: 保存草稿
123 |  |  |  | #N/A | Confirm: 提交申请
124 | Lot | Hold Lot | Hold Lot | Hold Lot | Confirm：对Lot 进行Hold
125 |  |  | Batch Hold | Batch Hold | Confirm：对批量Lot 进行Hold
126 |  |  | Release Lot | Release Lot | Confirm：对Lot 进行Release
127 |  |  | Batch Release | Batch Release | Confirm：对批量Lot 进行Release
128 |  |  | Edit Hold | Edit Hold | Confirm：对已Hold Lot 信息进行编辑
129 |  |  | PHOTO Reject Action | #N/A
130 |  |  | CUST. Hold Rule | #N/A
131 |  |  | Release Action | #N/A | Confirm：Release+ Rework..等合并操作
132 |  | Rework | Rework | Rework | Confirm：lot Rework
133 |  |  | Cancel Rework | Cancel Rework | Confirm：cancel Rework
134 |  |  | Split-Rework | #N/A | Confirm：Split-Rework
135 |  | Sorter | Split Lot | Split Lot | Confirm：Spilt
136 |  |  | Merge Lot | Merge Lot | Confirm：Merge
137 |  |  | Inline Split For Special Lot | #N/A
138 |  |  | Transfer Lot | #N/A | Confirm：更换同类型盒子
139 |  |  | Exchange Carrier | Exchange Carrier | Confirm：更不同类型盒子
140 |  |  | Change Slot Map Info | Change Slot Map Info | Confirm：更换slot 顺序
141 |  |  | Wafer Rotate | Wafer Rotate | Confirm：转角
142 |  |  | Wafer Verfication | #N/A | Confirm：读片
143 |  | Scrap | Scrap Apply | Scrap Apply | Confirm：申请报废
144 |  |  | Cancel Scrap Apply | Cancel Scrap Apply | Confirm：取消申请
145 |  |  | Scrap | #N/A | Confirm：报废
146 |  |  | Cancel Scrap | #N/A | Confirm：取消报废
147 |  | Terminate | Terminate Lot | #N/A | Confirm
148 |  |  | Terminate By Foup | #N/A | Confirm
149 |  |  | Special UnTerminate Lot | Special Unterminate Lot | Confirm
150 |  |  | UnTerminate Lot | Unterminate Lot | Confirm
151 |  | Future Action | Ser Future Hold | #N/A | Confirm：设定Future Hold
152 |  |  | Future Hold By Customer | #N/A
153 |  |  | Batch Futrure Hold | #N/A | Confirm：设定批量Future Hold
154 |  |  | Set Future Hold Step Group | #N/A
155 |  |  | Ser Future Rework | #N/A | Confirm：设定Future Rework
156 |  |  | Future Reserve Machine | Future Reserve Machine | Confirm：设定Future Reserve
157 |  |  | Set Future Split | #N/A | Confirm：设定Future Spilt
158 |  |  | FutureActionList | #N/A | Delete：删除Future 信息
159 |  | Q'Time Control | Cancel Q'Time Reservation | #N/A
160 |  |  | Turn Off Q'Time Speed Up | #N/A
161 |  | Reposition | Skip Step | Skip Step | Confirm：Skip Step
162 |  |  | Back Step | Back Step | Confirm：Back Step
163 |  |  | Reposition Step | #N/A | Confirm：Reposition Step
164 |  |  | NPW Reposition | #N/A
165 |  |  | Production Reposition | #N/A
166 |  |  | Special Reposition Step | #N/A
167 |  |  | Reposition Rule | Reposition Rule
168 |  | Samping | Set Scan Lot | Set Scan Lot | Confirm：提交数据手动设置Special YE Step Scan Lot
169 |  |  | Set Chamber Scan Lot | #N/A | 页面待改造.....
170 |  |  | Sampling Reserve Lot List | Sampling Reserve Lot List | Modify：修改Sampling Reserve Lot Remove：清除SamplingReserveLot的信息
171 |  |  | Set Sampling Skip Lot | Set Sampling Skip Lot | Confirm：提交数据设置Sampling Skip Lot
172 |  |  | Sampling Skip Lot List | Sampling Skip Lot List | Delete：清除Sampling Skip Lot信息
173 |  |  | Lot Sampling Run Time History | Lot Sampling Run Time History | Search：查询Lot Sampling 的Run time信息
174 |  | Pilot | Create Pilot | #N/A | Confirm：创建Pilot
175 |  |  | View Pilot | #N/A | Search：查看Pilot
176 |  |  | Stop Pilot | Stop Pilot | Confirm：中止 Pilot
177 |  |  | Release Hold Pilot | Release Hold Pilot | Confirm：Release Hold Pilot
178 |  |  | End Pilot | End PiLot | Confirm：终止Pilot
179 |  | Wafer Randomization | Config Random Recipe | #N/A
180 |  |  | Lot Random History | #N/A
181 |  |  | Adhoc Recover | #N/A
182 |  | Reassign | Reassign Lot | Reassign Lot | Confirm: 对PW 进行Reassign
183 |  |  | Reassign Lot For NPW | Reassign Lot For NPW | Confirm：对NPW 进行Reassign
184 |  |  | Future Reassign | Future Reassign | Confirm：Future Reassign
185 |  | FeedForward Attribute | Copy FeedForward Information | #N/A
186 |  |  | Modify FeedForward Information | #N/A
187 |  |  | Delete FeedForward Information | #N/A
188 |  | Lot Attribute | Add Steps | Add Steps | Confirm：Add Steps
189 |  |  | Add Comment | Add Comment | Confirm：Add Comment
190 |  |  | Set Stepper | #N/A
191 |  |  | Choose Alter Step | #N/A
192 |  |  | Lot Process Version | #N/A
193 |  |  | Lot Specialization | #N/A
194 |  |  | Maintain RMS Flag | #N/A
195 |  |  | Modify Lot Attribute | Modify Lot Attribute | Confirm：Modify Lot Attribute
196 |  |  | Batch Modify Lot Attribute | Batch Modify Lot Attribute | Confirm：对批量Lot 进行Modify Lot Attribute
197 |  |  | Modify Lot Attribute For QC | Modify Lot Attribute For QC | Confirm：权限管控QC 可Modify
198 |  |  | Modify Lot Attribute For MFG | Modify Lot Attribute For MFG | Confirm：权限管控MFG 可Modify
199 |  |  | Modify Lot Contamination Level | Modify Lot Contamination Level | Confirm：Modify Contamination Level
200 | Inventory | Bank | Bank In | Bank In | Confirm：Bank In
201 |  |  | Batch Bank In | #N/A
202 |  |  | Bank Out | Bank Out | Confirm：Bank Out
203 |  |  | View Bank Info. | #N/A | Search：查看Bank 信息
204 |  |  | Move Bank | Move Bank | Confirm：Move Bank
205 |  | Transfer | Transfer Lot Plan | #N/A | Create:创建Plan
206 |  |  |  | #N/A | Remove:删除Plan
207 |  |  |  | #N/A | Modify :修改Plan
208 |  |  | Transfer Lot Report | #N/A | Confirm：更改day Plan数量
209 |  |  | FAB Attribute Mapping Config | Fab Attribute Mapping Config | Create:创建
210 |  |  |  | #N/A | Remove:删除
211 |  |  |  | #N/A | Modify :修改
212 |  |  | FAB Attribute Value Mapping | Fab Attribute Value Mapping | Modify：更改Value及MappingValue
213 |  |  | Transfer Lot To Other FAB | #N/A | Confirm：Transfer Lot To Other FAB
214 |  |  | Recieve Own FAB Transfer Lot | #N/A | Confirm：Recieve Own FAB Transfer Lot
215 |  |  | Recieve Other FAB Lot | #N/A | Confirm：Recieve Other FAB Lot
216 |  |  | Cancel Transfer | #N/A | Confirm：Cancel Transfer
217 |  |  | View Transfer Lot List | #N/A
218 |  | Label | Lot Label | #N/A | Confirm：Lot Label
219 |  |  | Lot Card | Lot Card | Confirm：生成Barcode
220 |  |  | RSP Label | #N/A | Confirm：RSP Label
221 |  |  | Reticle Label | #N/A | Confirm：Reticle Label
222 |  |  | FOSB Label | #N/A | Confirm：生成FOSB ID
223 |  | Ship | Ship | Ship | Confirm：fab out
224 |  |  | Cancel Ship | #N/A | Confirm：cancel fab out
225 | Machine | EQP State | Change Machine State | Change Machine State | Comfirm: 数据提交
226 |  |  | Change Port State | Change Port State | Comfirm: 数据提交
227 |  |  | Change Machine Mode | #N/A | Comfirm: 数据提交
228 |  |  | Change Port Mode | #N/A | Comfirm: 数据提交
229 |  | Capability | Set Machine Capability | #N/A
230 |  |  | Set Chamber Capability | #N/A
231 |  | Tank Control | Tank Control | #N/A
232 |  |  | Wet Tank Control | #N/A
233 |  |  | Tank Count Info | #N/A
234 |  |  | Tank Running History | #N/A
235 |  |  | Tank OOS History | #N/A
236 |  | PMS | Create Work Order | Create Work Order
237 |  |  | Work Order | Work Order
238 |  |  | Work Order Approval | Work Order Approval
239 |  |  | PM Card | #N/A
240 |  |  | Calendar | Calendar
241 |  |  | Manual CBM | #N/A
242 |  |  | Reset CBM | #N/A
243 |  |  | EC Work Order | #N/A
244 |  | Inform Note | Inform Note | #N/A
245 |  |  | [Inform Type Data Tab] | #N/A
246 |  |  | [History Type Data Tab] | #N/A
247 |  |  | Inform Notice | #N/A
248 |  | One Key Touch | Control Action History | #N/A
249 |  |  | One Key Touch | #N/A
250 |  |  | One Key Touch Detail History | #N/A
251 |  |  | Power Source Setup | #N/A
252 |  |  | Power Source Setup History | #N/A
253 |  | Other | View Equipment Auto Mode | #N/A
254 |  |  | Modify Equipment Current Lots | #N/A
255 |  |  | Delete Chamber Current Lots | #N/A
256 |  |  | Modify Equipment Attribute | #N/A
257 |  |  | Modify Eqp Chamber Run Count | #N/A
258 |  |  | Buffer Tool Physical Foup Maintain | #N/A
259 |  |  | MFG Eqp Security Control Maintenance | #N/A
260 |  |  | Customize(定制) EQP Information | #N/A
261 |  |  | Equipment Couple Port | #N/A
262 | Carrier | Carrier Management | Create Carrier | Create Carrier | Create:创建Carrier Name
263 |  |  | Carrier RFID Managerment | #N/A | Print: 打印标签 RFID Clear: 清除RFID上Carrier信息 Confirm: 数据提交
264 |  |  | Assign Carrier | Assign Carrier | Assign: Lot与Carrier绑定
265 |  |  | Deassign Carrier | Deassign Carrier | Deassign: Lot与Carrier解绑
266 |  |  | Hold Carrier | Hold Carrier | Hold: 锁定Carrier
267 |  |  | Release Carrier | Release Carrier | Release: 解锁Carrier
268 |  |  | Reserve Target Carrier | #N/A
269 |  |  | Cancel Reserve Target Carrier | Cancel Reserve Target Carrier
270 |  |  | Scrap Carrier | Scrap Carrier | Scrap: 报废Carrier
271 |  |  | Cancel Scrap Carrier | Cancel Scrap Carrier | Confirm: 数据提交,取消报废Carrier
272 |  |  | Change Carrer Info | #N/A | Confirm: 数据提交,更改Carrier信息
273 |  | Carrier Clean | Set Carrier Clean | #N/A | Confirm: 数据提交,手动预约Carrier Clean
274 |  |  | Start Carrier Clean | #N/A | Confirm: 数据提交,手动Start Carrier Clean Cancel Carrier Clean: 跳转到Cancel Carrier Clean页面
275 |  |  | End Carrier Clean | #N/A | Confirm: 数据提交,手动End Carrier Clean Cancel Carrier Clean: 跳转到Cancel Carrier Clean页面
276 |  |  | Change Carrier Clean State | #N/A | Confirm: 数据提交,更改Clean State
277 |  |  | Cancel Clean | #N/A | Cancel Start Carrier Clean: 手动Cancel Start Carrier Clean数据 Cancel Set Carrier Clean: 手动Cancel Set Carrier Clean数据
278 |  | Carrier Down Grade | Carrier Downgrade Maps | #N/A
279 |  |  | Carrier Model Number Maps | #N/A
280 |  | Carrier Parts Management | Carrier Part | #N/A
281 |  |  | Carrier Part & Carrier Part Maps | #N/A
282 |  |  | View Carrier Part Info | #N/A
283 |  |  | Repair FOUP | #N/A
284 |  |  | Update Carrier Component | #N/A
285 |  |  | Add Carrier Comment | #N/A
286 |  | Carrier Inspection | Set Inspection | #N/A
287 |  |  | Cancel Inspection | #N/A
288 |  |  | Start Inspection | #N/A
289 |  |  | Set Disposal | #N/A
290 |  |  | Cancel Disposal | #N/A
291 |  |  | End Inspection | #N/A
292 |  |  | Carrier Data Collection | #N/A
293 |  |  | Inspection Flow Control | #N/A
294 | NPW | SPEC | Monitor Control Rule Setting | Monitor Control Rule Setting | Create,Modify,Remove,Copy,Confirm
295 |  |  | Dummy Control Rule Setting | Dummy Control Rule Setting | Create,Modify,Remove,Copy,Confirm
296 |  |  | Season Control Rule Setting | Season Control Rule Setting | Create,Modify,Remove,Copy,Confirm
297 |  |  | Furnace Monitor Control Rule Setting | #N/A | Create,Modify,Remove,Copy,Confirm
298 |  |  | NPW Inventory Setting | NPW Inventory Setting | Create,Modify,Remove,Copy,Confirm
299 |  |  | Downgrade Setting | Downgrade Setting | Create,Modify,Remove,Confirm
300 |  | NPW Main Flow | In Use Start | #N/A | Split: Split Lot
301 |  |  |  | #N/A | Confirm: Split & In Use Start
302 |  |  | In Use Start Auto Split Sorter Job Create(Time) | #N/A
303 |  |  | Auto Change Control ID Flag N->Y(Time) | #N/A
304 |  |  | View Machine Monitor Status | #N/A | Complete Monitor
305 |  |  |  | #N/A | Delay Monitor
306 |  |  | Complete Monitor Control | #N/A
307 |  |  | Delay Monitor Control | #N/A
308 |  |  | NPW In Use Start Adhoc Merge Sorter Job Create (Time) | #N/A
309 |  |  | In Use End | In Use End | Confirm: Merge Lot (In Use End站点), 25张后Skip当前站点
310 |  |  | Auto In Use End Merge Sorter Job Create | #N/A
311 |  |  | In Use Start (Adhoc Merge) | #N/A | Confirm: Merge Lot (In Use Start 站点)
312 |  |  | View Recycle End Lot List | #N/A | Downgrade
313 |  |  |  | #N/A | Scrap Apply
314 |  |  |  | #N/A | Reuse
315 |  |  | Make Recycle End Lot To Re Use | #N/A
316 |  |  | Downgrade | Downgrade | Confirm: Downgrade Lot
317 |  |  | Change NPW Product Spec | #N/A | Confirm
318 |  |  | Modify Wafer Information | Modify Wafer Information | Confirm: 修改Wafer信息
319 |  |  | Time Auto Change Wafer Clean State Clean->Dirty | #N/A
320 |  | Furnace Monitor | View Furnace Wait Batch | View Furnace Wait Batch | Reset DC Result,
321 |  |  |  | #N/A | REQ Track In
322 |  |  | FML Safety Inventory 维护功能（Time） | #N/A
323 |  | Dummy | Dummy Load | Dummy Load | Modify MC Dummy Info
324 |  |  |  | #N/A | Confirm
325 |  |  | Dummy UnLoad | Dummy UnLoad | Modify MC Dummy Info
326 |  |  |  | #N/A | Confirm
327 |  | Season | Recipe Group | #N/A
328 |  |  | View Machine Control Status(Season) | #N/A
329 |  |  | View Season History | View Season History | Search
330 |  |  | PM Season Control ID | #N/A
331 |  |  | PM Season Group | PM Season Group | Reset DC Result,
332 |  |  |  | #N/A | REQ Track In
333 |  | Inquiry | View Machine Dummy Infomation | #N/A | Search
334 |  |  | View NPW Lot Information | #N/A
335 |  |  | View Machine Dummy Wafer History | #N/A | Search
336 |  |  | Farnace Batch History | #N/A
337 | Reticle | Reticle | Reticle List | #N/A | Hold: 锁住Reticle Inspect Request: 检测请求 Clean: 更改Reticle Clean State Scan Request: 扫描请求 Scrap: 报废Reticle Bank In：Bank In
338 |  |  | Create Reticle | #N/A | Generate: 创建生成Reticle Name Confirm：数据提交
339 |  |  | Quallity Check | #N/A | Confirm：数据提交
340 |  |  | Reticle Process Attach | #N/A | Add：新增Reticle与机台绑定 Modify：编辑Reticle与机台绑定信息 Remove: 删除Reticle与机台绑定
341 |  |  | Reticle Load/Unload | #N/A | Load: Load Reticle Unload: Uload Reticle
342 |  |  | Reticle Transport | #N/A | Reticle Out: 将Reticle调出Stocker
343 |  |  | Special Dismount | #N/A
344 |  |  | Reticle Inspect In | #N/A | Inspect In: Manual Inspect Start
345 |  |  | Reticle Inspect Out | #N/A | Inspect Out: Manual Inspect End
346 |  |  | Reticle Clean Complete | Reticle Clean Complete | Clean Complete: Manual Clean End
347 |  |  | Reticle Release | #N/A | Release: Reticle解锁
348 |  |  | BankOut | #N/A | Bank Out：Bank Out
349 |  |  | Cancel Scrap Reticle | #N/A | Confirm：数据提交，取消报废Reticle
350 |  |  | Reticle Scran In | #N/A | Scran In: Manual Scan Start
351 |  |  | Reticle Scan Out | Reticle Scan Out | Scan Out: Manual Scan End
352 |  |  | Return | #N/A
353 |  |  | Retrive | #N/A
354 |  |  | Maual Data Collection | #N/A
355 |  |  | Reticle Info. Maintenence | #N/A
356 |  | RSP | RSPList | #N/A | Create: 弹框操作，创建生成RSP Name Change Info: 弹框操作，更改RSP Info Assign: 弹框操作,Rsp 与Reticle绑定 Deassign: 弹框操作,Rsp 与Reticle解绑 Hold: 弹框操作，锁住RSP Clean: 弹框操作，更改Rsp Clean State Scrap：弹框操作，报废RSP
357 |  |  | Create RSP | #N/A | Confirm：数据提交 Cancel: 关掉页面
358 |  |  | Change RSP Info | #N/A | Confirm：数据提交 Cancel: 关掉页面
359 |  |  | Assign reticle to RSP | #N/A | Confirm：数据提交 Cancel: 关掉页面
360 |  |  | Deassign reticle from RSP | #N/A | Confirm：数据提交 Cancel: 关掉页面
361 |  |  | Hold RSP | #N/A | Confirm：数据提交 Cancel: 关掉页面
362 |  |  | Clean RSP | #N/A | Confirm：数据提交 Cancel: 关掉页面
363 |  |  | Scrap RSP | #N/A | Confirm：数据提交 Cancel: 关掉页面
364 |  |  | RSP Clean Complete | #N/A | Confirm：数据提交，Manual Clean Complete
365 |  |  | Exchange RSP | #N/A | Exchange: 给两个Reticle交换RSP
366 |  |  | Release RSP | #N/A | Release: RSP解锁
367 |  |  | RSP Cancel Scrap | #N/A | RSP Cancel Scrap: 取消报废
368 |  |  | Repair RSP | #N/A
369 | Inquiry | Lot/Wafer | Add Comment | Add Comment
370 |  |  | Lot Info. | #N/A
371 |  |  | ViewLotList | #N/A
372 |  |  | View Wafer Info. | #N/A
373 |  |  | T7 Code View | #N/A
374 |  |  | Lot History | #N/A
375 |  |  | Wafer History | #N/A
376 |  |  | View Wafer Verification Result | #N/A
377 |  |  | View Component Information | #N/A
378 |  |  | Wafer Chamber Tracking History | #N/A
379 |  |  | Wafer Slot History | #N/A
380 |  |  | Furnace Batch History | #N/A
381 |  | Machine | View Machine Status | View Machine Status
382 |  |  | View Machine History | View Machine History
383 |  |  | PM,BM History | #N/A
384 |  |  | Equipment Process History | #N/A
385 |  | Carrier | View Carrier List | #N/A | Scrap Carrier：跳转按钮，跳转到Scrap Carrier页面 Cancel Scrap Carrier：跳转按钮，跳转到Cancel Scrap Carrier页面 Change Carrier Info: 跳转按钮，跳转至Change Carrier Info页面 Clean Carrier: 跳转按钮，跳转至Change Carrier Clean State Release Carrier: 跳转按钮，跳转至Release Carrier页面 Hold Carrier；跳转按钮，跳转至Hold Carrier页面
386 |  |  | View Carrier Cycle | #N/A
387 |  |  | View Carrier Status | View Carrier Status | Search: 页面数据搜索 Reset: 清空搜索栏内数据
388 |  |  | View Carrier History | View Carrier History | Search: 页面数据搜索 Reset: 清空搜索栏内数据
389 |  | Sampling | Lot Sampling Runtime History | #N/A
390 |  |  | YE Step Sampling History | #N/A
391 | CSN | CSN | JP Fail Lot List | #N/A
392 | OCAP |  | OCAP MGMT | #N/A
393 |  |  | Show OCAP Detail Info | #N/A
394 |  |  | Change Measure Machine | #N/A
395 |  |  | Modify Reason Code | #N/A
396 |  |  | Dispatch | #N/A
397 |  |  | Change Flow | #N/A
398 |  |  | Change Step | #N/A
399 |  |  | Remeasurement | #N/A
400 |  |  | Add Measurement | #N/A
401 |  |  | Engineer Confirm | #N/A